## Sheet1
Action Reference | Description of Action | Target Date | Owner | Update | Status
Action 120418: 0401 | National Grid to review Annex B Section 1.3.2 (k) in relation to the 01 August Charges Publication Date and consider if this should be earlier for certain items. National Grid to confirm a) what information should be published and when; b) which elements are to be included in UNC. | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0402 | National Grid to provide more information in relation to Annex B Section 1.5 Allowed Revenue – Formula Years. In particular, to confirm what revenue is moving or contributing towards Transmission revenue and what is moving or contributing towards Non-Transmission revenue and to provide an example of how it works. This includes the revenue from short term capacity and if legal text should be amended. A5 | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0403 | National Grid to a) check if the word ‘average’ should be included into Annex B Section 2.5.1 (a) in relation to Forecast Contracted Capacity; b) Review Section 2.5.3 and consider if timescales should be added relating to the first time something is used moving from transition into the enduring. | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0404 | National Grid to review the definition of ‘materially inaccurate’ within Annex B Section 3.3.1 and consider if any changes are required. | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0405 | National Grid to consider if ‘k’ tolerances should be used as mitigating factors to inform price re-setting Annex A 3.3.1 (links to 404). | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0406 | National Grid to review the drafting in Annex A to clarify that the Optional Charge is Transmission Services revenue. | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0407 | National Grid to remove the typo in Annex A Section 3.12.1 (b). The sentence should read “National Grid NTS shall pay NTS Offtake…” | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0408 | National Grid to review Legal Text front page TPD Section G2.5.8(b) and check if the paragraph to be deleted should be (iii) and not (c). | 2018-04-25 | National Grid |  | Carried Forward
Action 120418: 0409 | National Grid to provide examples in relation to Annex C Section 24.6.5 to illustrate 3 scenarios. This included IP to IP, Non IP to IP and IP to Non IP (all scenarios where IP is either the Entry or Exit Point for any NTS optional charge nomination. | 2018-04-26 | National Grid |  | Carried Forward
Action 120418: 0410 | CDSP (EL) to a) highlight the implications of implementation of any of the 0621 Modifications and to set out what is needed for TAR compliance. In addition, to provide a view on whether the timescales are feasible; b) provide some text for the Workgroup report on the key risks and how they can be mitigated for Modification 0621 and the corresponding alternatives. |  | CDSP (EL) | Update provided | Closed
Action 120418: 0411 | SSE (JCh) to confirm whether the FCC Baseline analysis applies to Modification 0621B. |  | SSE (JCh) |  | Carried Forward
Action 120418: 0412 | National Grid in relation to Agenda item 6.3 Analysis to provide supporting commentary for all analysis to provide a summary conclusion to aid Workgroup discussion. In addition, to provide a view of how the data conclusions help to support and further the relevant objectives in reference to Modification 0621. |  | National Grid |  | Carried Forward
Action 120418: 0413 | National Grid (AB) in relation to Analysis 8 - Impact of the Optional Charge on Revenue Recovery Rates to provide more examples to illustrate as per 409. In addition, to provide details of the revenue recovered in terms of money rather than percentages. |  | National Grid |  | Carried Forward
Action 120418: 0414 | Pavanjit Dhesi to review Analysis 8 - Impact of the Optional Charge on Revenue Recovery Rates to provide a view from IUK on the impact on IP flows. |  | Interconnector (PD) |  | Carried Forward
Action 120418: 0415 | Energy UK (JC) in relation to existing contracts: TAR compliance and relevant objectives to provide a summary of the key issues that need consideration for the Workgroup Report. |  | Energy UK (JC) | Chris Shanley to liaise with Julie Cox for Workgroup Report input carried forward | Carried Forward
Action 120418: 0416 | GDN Workgroup participants to update workgroup for Modification 0621 on how NTS pricing changes will change DN Charges and articulate the potential impact on consumers. |  | GDN Workgroup participants |  | Carried Forward
Action 120418: 0417 | Joint Office (RH) to circulate the Workgroup Report and highlight the sections that need to be reviewed. |  | Joint Office |  | Carried Forward
New Action: 200418 0401: | Joint Office to send letter to Ofgem seeking a View | 2018-04-20 | Joint Office | Completed 20 April | Closed
New Action: 200418 0402: | National Grid to update the presentation material to provide a commentary explaining the impact on the Relevant Objectives. |  | National Grid |  | Carried Forward
New Action 200418 0403: | Number 11 Analysis: National Grid to add in peak flow to slide 6. |  | National Grid |  | Carried Forward
New Action 200418 0404: | Number 11 Analysis: National Grid to provide historic variance against K factor figures. |  | National Grid |  | Carried Forward
New Action 200418 0405: | Number 11 Analysis: Workgroup to make a statement in the Workgroup Report based on the figures from National Grid in Action 0404 If there is volatility to link it back to the relevant objectives. |  | All Workgroup participants |  | Carried Forward
New Action 200418 0406: | National Grid (CW) to provide example for WG’s review. |  | National Grid |  | Carried Forward
New Action 200418 0407: | Proposers asked to check the table and confirm it is as expected. Please notify if there are any inaccuracies by close of play Monday 23 April. |  | All Workgroup participants |  | Carried Forward
New Action 230418 0401: | Decision to be made for topic to be covered on 27 April. Should this meeting be cancleed or run a Relevant Obnjectives session. All to provide view 24 April | 2018-04-24 | All Workgroup participants |  | Carried Forward