## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - Rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Incrementing Reads on Isolation Supply Meter Points | 1839.3 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 Deferred | Rejected at ChMC on 14th February. Xoserve are awaiting further clarification from the parties who rejected the change. XRN4622 has been raised - propose to remove from implementation plan as this is on the Change Register
4538 | NA | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File | 1898.1 | 2018-03-21 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | 2018-05-02 | First Change Pack for Release 3
4273 | NA | Introducing IHD (In-Home Display) Installed Status of Failed | 1898.2 1901.1 | 21/03/2018 27/03/2018 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | 2018-05-02 | First Change Pack for Release 3
4337 | NA | To change the optionality of the Supply Point confirmation reference for the T51 file | 1898.3 | 2018-03-21 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | 2018-05-02 | First Change Pack for Release 3
4443 | NA | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | 1898.2 | 2018-03-21 | 2018-04-06 | 2018-04-11 | X |  |  |  |  | 2018-05-02 | First Change Pack for Release 3
4453 | NA | File Format Changes | 1856.3 1897 | 31/01/2018 20/03/2018 | 21/02/2018 23/03/2018 | 2018-02-28 | X | X | X | X | X | 2018-05-09 | Proposed for Release 3, Change Pack to follow with amended file formats.
NA | NA | Ability to Accept Extended Reading Indexes of up to 12 Characters – Confirmation Requested | 1884.3 | 2018-03-09 | NA | NA | X | X |  |  |  |  | Release to be confirmed

## IP - For Approval
UK Link Modification Implementation Plan - For Approval
Documentation changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
There are no documentation changes
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
4249.A | NA | Address Maintenance Solution - Code | 1856.2 | 2018-01-31 | 2018-02-14 | 2018-02-21 | X | X |  | X |  | 2018-04-11 | Proposed for Release 2
4249.B | NA | Address Maintenance Solution - PAF Validation updates - Data Migration Plan | 1905.1 | 2018-03-29 | 2018-04-09 | 2018-04-10 | X |  |  |  |  | 2018-04-11 | 2018-07-07
4465 | 0576 | Annual Production and notification of LIS-3years read | 1884.1 | 2018-03-09 | NA | NA | X |  |  |  |  | Retrospective approval 11/04/2018 | 2018-04-01

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 7th March
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
NA | NA | Changes Proposed for Removal from the Change Log | 1856.1 | 2018-01-31 | 2018-02-14 | 2018-02-21 | X | X | X | X | X | 2018-03-07 | 2018-03-08
NA | NA | New User Notification Method | 1866.1 | 2018-02-09 | 2018-02-23 | 2018-03-02 | X |  |  |  |  | 2018-03-07 | 2018-05-07
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Approval date | Implementation Date
[7 empty] | Shipper | DNs | NTS | iGT | Other
No functional changes approved last meeting

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
As of 11th April - there are no outages to notify