## CMC_Summary
Totals by Budget Area (£,000's) | [11 empty] | Current Year Value of Work Done Split By Customer Class
|  |  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) |  | Expenditure Type | Approved Budget Value 17/18 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget 17-18 | MKT_1718_01 | External | 1255.041 | 1895.0627 | 1129.329 | 80.291 | 559.3748 | 0 | 489.6632 | G | G | 2.8737 | 498.1644 | 29.48 | 0.44522 | 28.4519
|  | Internal |  | 547.4276 | 295.0298 | 76.864 | 158.1658 | 0 | 60 | NA | G | 0 | 153.2228 | 4.943 | 0 | 0
|  | Total |  | 2437.6053 | 1424.3588 | 157.155 | 717.5406 | 0 | 549.6632 | NA | G | 2.8737 | 651.3872 | 34.423 | 0.44522 | 28.4519
PAC Subset DSC Change Budget 17-18 |  | External | 50 | 50 | 0 | 0 | 0 | 0 | 0 | NA | G
*This has already been included in above DSC figures,and this sub table is for visibility only |  | Internal | [7 empty] | NA | G
|  | Total |  | 50 | 0 | 0 | 0 | 0 | 0 | NA | G
Note that project expenditure & budget values shown do not include margin | [9 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [9 empty] | Red - Above target | [7 empty] | PIE VALUES
[18 empty] | Budget | 1255.041
[18 empty] | Budget Remaining | 695.6662
Details of Changes | [17 empty] | Potential Additional Spend | -0.040474 | Sums Estimated Cost Current Year IF: Budget is DSC Change Budget & Cost Type is External
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year | [14 empty] | VOWR for Approved Projects | 0
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining | [11 empty] | VOWD Transmission | 2.8737
4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - External | 0 | 4.2 | 0 | 4.2 | 0 | 0 | [11 empty] | VOWD DNs | 498.1644
4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Internal | 0 | 0.9 | 0 | 0.9 | 0 | 0 | [11 empty] | VOWD Shippers | 28.4519
4361 UK Link Future Release 2 (DSC Change Budget) - External [C] | 0 | -37.5 | 0 | 90.8 | -128.3 | 0 | [11 empty] | VOWD DNs & IGTs | 29.48
4572 Retail & Network Release 3 (DSC Change Budget) - External [O] | 0 | -21 | 0 | 40.5 | -18.3 | -43.2 | [10 empty] | LABEL > | VOWD iGTs | 0.44522
2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | 0 | 1.3 | 0 | 1.3 | 0 | 0 | [11 empty] | Total VOWD £559.4
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## CMC_Current
Values in £ 0,000s unless marked otherwise |  |  |  |  | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [6 empty] | SORT FIELD 2 |  | SORT FIELD 1 |  |  |  |  | Formulas do not delete |  | 5 | 7 | 8 | 10 | 11 | 12 | 13 | 14
Budget Pot Reference | Project Ref No | Project Title | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | Line Sequence Sort (THEN BY THIS) | PM | StageNum for Show or No Show(SORT BY THIS) | Show Approved Money? | Show Reported Money? | Auto Assess of CMC Friendly? | Progress Sort | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | External | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 419 | R Hinsley | 0.0 | Show | Show | Y | N/A | xxxx.A.PACExternal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | Internal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 420 | R Hinsley | 0.0 | Show | Show | Y | N/A | xxxx.A.PACInternal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | xxxx.A.PAC | PAC Change Budget Placeholder (subset of DSC Change Budget) | N/A | Total | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 421 | R Hinsley | 0.0 | Show | Show | Y | N/A | xxxx.A.PACTotal | xxxx.A.PAC PAC Change Budget Placeholder (subset of DSC Change Budget) - Total | SAME | 50 | 0 | 0 | 0 | 0 | 0 | DIFF | YES | 0 | TRUE |  | 0
MKT_1718_01 | 4572 | Retail & Network Release 3 (DSC Change Budget) | BER/Bus Case | External [O] | 101.9476 | 80.949 | 20.9986 | 0 | 40.4745 | 0 | 40.4745 | 39.6% | 7.1% | 52.3% | 0% | 1.1% | 16.0279 | 2.8737 | 21.1682 | 0 | 0.44522 |  |  | 449 | P Duvvuri | 7.0 | Show | Show | Y | 7 | 4572External [O] | 4572 Retail & Network Release 3 (DSC Change Budget) - External [O] | SAME | 0 | -21 | 0 | 40.5 | -18.3 | -43.2 | DIFF | YES | 22.2 | TRUE |  | 0
MKT_1718_01 | 4572 | Retail & Network Release 3 (DSC Change Budget) | BER/Bus Case | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.6% | 7.1% | 52.3% | 0% | 1.1% | 0 | 0 | 0 | 0 | 0 |  |  | 450 | P Duvvuri | 7.0 | Show | Show | Y | 7 | 4572Internal [O] | 4572 Retail & Network Release 3 (DSC Change Budget) - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4572 | Retail & Network Release 3 (DSC Change Budget) | BER/Bus Case | Total | 101.9476 | 80.949 | 20.9986 | 0 | 40.4745 | 0 | 40.4745 | 39.6% | 7.1% | 52.3% | 0% | 1.1% | 16.0279 | 2.8737 | 21.1682 | 0 | 0.44522 |  |  | 451 | P Duvvuri | 7.0 | Show | Show | Y | 7 | 4572Total | 4572 Retail & Network Release 3 (DSC Change Budget) - Total | SAME | 0 | -21 | 0 | 40.5 | -18.3 | -43.2 | DIFF | YES | 22.2 | TRUE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | External [C] | 1107.0172 | 842.9323 | 264.0849 | 0 | 458.0293 | 0 | 384.903 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 458.0293 | 0 | 0 |  |  | 212 | C Francis | 11.0 | Show | Show | Y | 11 | 4361External [C] | 4361 UK Link Future Release 2 (DSC Change Budget) - External [C] | SAME | 0 | -37.5 | 0 | 90.8 | -128.3 | 0 | DIFF | YES | -37.5 | TRUE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | Internal [C] | 329.7006 | 179.0548 | 150.6458 | 0 | 119.0548 | 0 | 60 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 119.0548 | 0 | 0 |  |  | 213 | C Francis | 11.0 | Show | Show | Y | 11 | 4361Internal [C] | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal [C] | SAME | 0 | 0 | 0 | 20 | -20 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | External [O] | 128.5714 | 64.2857 | 64.2857 | 0 | 0 | 0 | 64.2857 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 214 | C Francis | 11.0 | Show | Show | Y | 11 | 4361External [O] | 4361 UK Link Future Release 2 (DSC Change Budget) - External [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 215 | C Francis | 11.0 | Show | Show | Y | 11 | 4361Internal [O] | 4361 UK Link Future Release 2 (DSC Change Budget) - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4361 | UK Link Future Release 2 (DSC Change Budget) | Delivery | Total | 1565.2892 | 1086.2728 | 479.0165 | 0 | 577.0841 | 0 | 509.1887 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 577.0841 | 0 | 0 |  |  | 216 | C Francis | 11.0 | Show | Show | Y | 11 | 4361Total | 4361 UK Link Future Release 2 (DSC Change Budget) - Total | SAME | 0 | -37.5 | 0 | 110.8 | -148.3 | 0 | DIFF | YES | -37.5 | TRUE |  | 0
MKT_1718_01 | 4361 | UKL Release 2 (DSC CB) Additional Scope Items (Cadent Billing HLIA) | Delivery | External [C] | 213.5315 | 10 | 203.5315 | 0 | 10 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 10 | 0 | 0 |  |  | 422 | C Francis | 11.0 | Show | Show | Y | 11 | 4361External [C] | 4361 UKL Release 2 (DSC CB) Additional Scope Items (Cadent Billing HLIA) - External [C] | SAME | -893.5 | -870.4 | 0 | -357.2 | -128.3 | -384.9 | DIFF | YES | -485.5 | TRUE |  | 0
MKT_1718_01 | 4361 | UKL Release 2 (DSC CB) Additional Scope Items (Cadent Billing HLIA) | Delivery | Internal [C] | 39.29 | 0 | 39.29 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | 423 | C Francis | 11.0 | Show | Show | Y | 11 | 4361Internal [C] | 4361 UKL Release 2 (DSC CB) Additional Scope Items (Cadent Billing HLIA) - Internal [C] | SAME | -290.4 | -179.1 | 0 | -99.1 | -20 | -60 | DIFF | YES | -119.1 | TRUE |  | 0
MKT_1718_01 | 4361 | UKL Release 2 (DSC CB) Additional Scope Items (Cadent Billing HLIA) | Delivery | Total | 252.8215 | 10 | 242.8215 | 0 | 10 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 10 | 0 | 0 |  |  | 424 | C Francis | 11.0 | Show | Show | Y | 11 | 4361Total | 4361 UKL Release 2 (DSC CB) Additional Scope Items (Cadent Billing HLIA) - Total | SAME | -1312.5 | -1113.8 | 0 | -456.3 | -148.3 | -509.2 | DIFF | YES | -604.6 | TRUE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | External | 89 | 64.477 | 24.523 | 60.288 | 4.189 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 4.189 | 0 | 0 |  |  | 140 | M Pollard | 12.0 | Show | Show | Y | 12 | 4110External | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - External | SAME | 0 | 4.2 | 0 | 4.2 | 0 | 0 | DIFF | YES | 4.2 | TRUE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | Internal | 31.05 | 37.357 | -6.307 | 24.18 | 13.177 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 13.177 | 0 | 0 |  |  | 141 | M Pollard | 12.0 | Show | Show | Y | 12 | 4110Internal | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Internal | SAME | 0 | 0.9 | 0 | 0.9 | 0 | 0 | DIFF | YES | 0.9 | TRUE |  | 0
MKT_1718_01 | 4110 | Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] | Closedown | Total | 120.05 | 101.834 | 18.216 | 84.468 | 17.366 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 17.366 | 0 | 0 |  |  | 142 | M Pollard | 12.0 | Show | Show | Y | 12 | 4110Total | 4110 Creation of a Service to Release Domestic Consumer Data to PCW’s & TPI’s [ANALYSIS] - Total | SAME | 0 | 5.1 | 0 | 5.1 | 0 | 0 | DIFF | YES | 5.1 | TRUE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | External [C] | 20 | 12.424 | 7.576 | 0 | 12.424 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 12.424 | 0 | 0 | 0 | 0 | Sent |  | 372 | D Jones | 12.0 | Show | Show | Y | 12 | 4510External [C] | 4510 Negative Consumption Period For Rolling AQ - External [C] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | External [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Sent |  | 373 | D Jones | 12.0 | Show | Show | Y | 12 | 4510External [O] | 4510 Negative Consumption Period For Rolling AQ - External [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | Internal [C] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Sent |  | 374 | D Jones | 12.0 | Show | Show | Y | 12 | 4510Internal [C] | 4510 Negative Consumption Period For Rolling AQ - Internal [C] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | Internal [O] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Sent |  | 375 | D Jones | 12.0 | Show | Show | Y | 12 | 4510Internal [O] | 4510 Negative Consumption Period For Rolling AQ - Internal [O] | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 4510 | Negative Consumption Period For Rolling AQ | Closedown | Total | 20 | 12.424 | 7.576 | 0 | 12.424 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 12.424 | 0 | 0 | 0 | 0 | Sent |  | 376 | D Jones | 12.0 | Show | Show | Y | 12 | 4510Total | 4510 Negative Consumption Period For Rolling AQ - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 0
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closed | External | 33.273 | 11.541 | 21.732 | 9.032 | 2.509 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.509 | 0 | 0 | Approved |  | 56 | M Pollard | 100.0 | Show | Show | Y | 100 | 2949External | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - External | DIFF | 0 | 1.3 | 0 | 1.3 | 0 | 0 | DIFF | YES | 1.3 | TRUE |  | 1
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closed | Internal | 25.714 | 22.721 | 2.993 | 22.684 | 0.037 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0.037 | 0 | 0 | Approved |  | 57 | M Pollard | 100.0 | Show | Show | Y | 100 | 2949Internal | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Internal | DIFF | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 2949 | UNC Mod 458 Seasonal LDZ Capacity Rights | Closed | Total | 58.987 | 34.262 | 24.725 | 31.716 | 2.546 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 2.546 | 0 | 0 | Approved |  | 58 | M Pollard | 100.0 | Show | Show | Y | 100 | 2949Total | 2949 UNC Mod 458 Seasonal LDZ Capacity Rights - Total | DIFF | 0 | 1.3 | 0 | 1.3 | 0 | 0 | DIFF | YES | 1.3 | TRUE |  | 2
MKT_1718_01 | 3995a | TRAS Tip-off Hotline Data Provision | Closed | External | 9.7 | 10.224 | -0.524 | 8.955 | 1.269 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.269 | 0 | 0 | Approved |  | 95 | M Pollard | 100 | Show | Show | Y | 100 | 3995aExternal | 3995a TRAS Tip-off Hotline Data Provision - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 3995a | TRAS Tip-off Hotline Data Provision | Closed | Internal | 3.12 | 2.267 | 0.853 | 2.3 | -0.033 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -0.033 | 0 | 0 | Approved |  | 96 | M Pollard | 100 | Show | Show | Y | 100 | 3995aInternal | 3995a TRAS Tip-off Hotline Data Provision - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 3995a | TRAS Tip-off Hotline Data Provision | Closed | Total | 12.82 | 12.491 | 0.329 | 11.255 | 1.236 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1.236 | 0 | 0 | Approved |  | 97 | M Pollard | 100 | Show | Show | Y | 100 | 3995aTotal | 3995a TRAS Tip-off Hotline Data Provision - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closed | External | 15.016 | 3.016 | 12 | 2.016 | 1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 1 | 0 | 0 |  |  | 104 | M Pollard | 100.0 | Show | Show | Y | 100 | 3991External | 3991 Pafa Administrator Role [Usr Pys] - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closed | Internal | 57.5 | 45.306 | 12.194 | 22.7 | 22.606 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 22.606 | 0 | 0 |  |  | 105 | M Pollard | 100.0 | Show | Show | Y | 100 | 3991Internal | 3991 Pafa Administrator Role [Usr Pys] - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 3991 | Pafa Administrator Role [Usr Pys] | Closed | Total | 72.516 | 48.322 | 24.194 | 24.716 | 23.606 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 23.606 | 0 | 0 |  |  | 106 | M Pollard | 100.0 | Show | Show | Y | 100 | 3991Total | 3991 Pafa Administrator Role [Usr Pys] - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | Approved |  | 155 | L Cave | 100.0 | Show | Show | Y | 100 | 4161External | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | Internal | 9.923 | 3.381 | 6.542 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.619 | 0 | 0 | Approved |  | 156 | L Cave | 100.0 | Show | Show | Y | 100 | 4161Internal | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4161 | Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] | Closed | Total | 9.923 | 3.381 | 6.542 | 5 | -1.619 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | -1.619 | 0 | 0 | Approved |  | 157 | L Cave | 100.0 | Show | Show | Y | 100 | 4161Total | 4161 Provision of Access to Domestic Consumer Data for PCW’s and TPI’s via Data Enquiry (DESIGN) [Usr Pys] - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Closed | External [C] | 127.006 | 29.48 | 97.526 | 0 | 29.48 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 29.48 | 0 |  |  | 203 | M Rider | 100.0 | Show | Show | Y | 100 | 4340External [C] | 4340 UK Link Future Release 1.1 (DSC Change Budget) - External [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Closed | Internal [C] | 51.13 | 4.943 | 46.187 | 0 | 4.943 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 4.943 | 0 |  |  | 204 | M Rider | 100.0 | Show | Show | Y | 100 | 4340Internal [C] | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Internal [C] | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NEW | NO | 0 | FALSE |  | 1
MKT_1718_01 | 4340 | UK Link Future Release 1.1 (DSC Change Budget) | Closed | Total | 173.251 | 34.423 | 138.828 | 0 | 34.423 | 0 | 0 | 0% | 0% | 0% | 100% | 0% | 0 | 0 | 0 | 34.423 | 0 |  |  | 205 | M Rider | 100.0 | Show | Show | Y | 100 | 4340Total | 4340 UK Link Future Release 1.1 (DSC Change Budget) - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | DIFF | NO | 0 | FALSE |  | 2
Note on AQ2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual