## Sheet1
Action Reference | Description of Action | Target Date | Owner | Update | Status
Action 120418: 0401 | National Grid to review Annex B Section 1.3.2 (k) in relation to the 01 August Charges Publication Date and consider if this should be earlier for certain items. National Grid to confirm a) what information should be published and when; b) which elements are to be included in UNC. | 2018-05-01 | National Grid | Carried forward and links with new action 250418: 0403 | Carried Forward
Action 120418: 0402 | National Grid to provide more information in relation to Annex B Section 1.5 Allowed Revenue – Formula Years. In particular, to confirm what revenue is moving or contributing towards Transmission revenue and what is moving or contributing towards Non-Transmission revenue and to provide an example of how it works. This includes the revenue from short term capacity and if legal text should be amended. | 2018-05-02 | National Grid | Table to be added to the commentary in relation to Interruptible. To also include discretionary capacity. | Carried Forward
Action 120418: 0403 | National Grid to a) check if the word ‘average’ should be included into Annex B Section 2.5.1 (a) in relation to Forecast Contracted Capacity; b) Review Section 2.5.3 and consider if timescales should be added relating to the first time something is used moving from transition into the enduring. | 2018-04-25 | National Grid | Actioned | Closed
Action 120418: 0404 | National Grid to review the definition of ‘materially inaccurate’ within Annex B Section 3.3.1 and consider if any changes are required. | 2018-04-25 | National Grid | Actioned - see 25.2.2 transition document | Closed
Action 120418: 0405 | National Grid to consider if ‘k’ tolerances should be used as mitigating factors to inform price re-setting Annex A 3.3.1 (links to 404). | 2018-04-30 | National Grid | Carried forward - No as licence states best endeavours. | Closed
Action 120418: 0406 | National Grid to review the drafting in Annex A to clarify that the Optional Charge is Transmission Services revenue. | 2018-04-30 | National Grid | Actioned | Closed
Action 120418: 0407 | National Grid to remove the typo in Annex A Section 3.12.1 (b). The sentence should read “National Grid NTS shall pay NTS Offtake…” | 2018-04-25 | National Grid | Actioned | Closed
Action 120418: 0408 | National Grid to review Legal Text front page TPD Section G2.5.8(b) and check if the paragraph to be deleted should be (iii) and not (c). | 2018-04-25 | National Grid | Actioned | Closed
Action 120418: 0409 | National Grid to provide examples in relation to Annex C Section 24.6.5 to illustrate 3 scenarios. This included IP to IP, Non IP to IP and IP to Non IP (all scenarios where IP is either the Entry or Exit Point for any NTS optional charge nomination. | 2018-05-01 | National Grid | To be discussed on 01 May 2018. | Carried Forward
Action 120418: 0410 | CDSP (EL) to a) highlight the implications of implementation of any of the 0621 Modifications and to set out what is needed for TAR compliance. In addition, to provide a view on whether the timescales are feasible; b) provide some text for the Workgroup report on the key risks and how they can be mitigated for Modification 0621 and the corresponding alternatives. |  | CDSP (EL) | Update provided | Closed
Action 120418: 0411 | SSE (JCh) to confirm whether the FCC Baseline analysis applies to Modification 0621B. |  | SSE (JCh) | Doesn't apply | Closed
Action 120418: 0412 | National Grid in relation to Agenda item 6.3 Analysis to provide supporting commentary for all analysis to provide a summary conclusion to aid Workgroup discussion. In addition, to provide a view of how the data conclusions help to support and further the relevant objectives in reference to Modification 0621. | 2018-05-02 | National Grid | to be provided for 02/05 | Carried Forward
Action 120418: 0413 | National Grid (AB) in relation to Analysis 8 - Impact of the Optional Charge on Revenue Recovery Rates to provide more examples to illustrate as per Action 0409. In addition, to provide details of the revenue recovered in terms of money rather than percentages. | 2018-05-01 | National Grid | Completed to be shared 01 May | Carried Forward
Action 120418: 0414 | Pavanjit Dhesi to review Analysis 8 - Impact of the Optional Charge on Revenue Recovery Rates to provide a view from IUK on the impact on IP flows. | 2018-05-03 | Interconnector (PD) | action details to be sent PD | Carried Forward
Action 120418: 0415 | Energy UK (JC) in relation to existing contracts: TAR compliance and relevant objectives to provide a summary of the key issues that need consideration for the Workgroup Report. |  | Energy UK (JC) | Chris Shanley to liaise with Julie Cox for Workgroup Report input carried forward | Closed
Action 120418: 0416 | GDN Workgroup participants to update workgroup for Modification 0621 on how NTS pricing changes will change DN Charges and articulate the potential impact on consumers. | 2018-04-26 | GDN Workgroup participants | To be discussed on 26 April under DN Impacts | Closed
Action 120418: 0417 | Joint Office (RH) to circulate the Workgroup Report and highlight the sections that need to be reviewed. | 2018-04-23 | Joint Office | CS provided a presentation on workgroup report appraoch. | Closed
Action: 200418 0401: | Joint Office to send letter to Ofgem seeking a View | 2018-05-01 | Joint Office(RH) | Completed 20 April. Need to publish the letter. | Carried Forward
Action: 200418 0402: | National Grid to update the presentation material (analysis 3 - RPM Sensitivity Analysis and 11 Assessment of Spare Capacity on the Network ) to provide a commentary drawing out the conclusions and also explaining the impact on the Relevant Objectives. | 2018-05-02 | National Grid |  | Carried Forward
Action 200418 0403: | Number 11 Analysis: National Grid to repeat the analysis for slide 6 (Obligated Capacity Utilisation: GDN Offtakes – SC) using using peak flow. Updated results to be provided to the Workgroup. | 2018-05-01 | National Grid | Completed. Need to publish the update. | Carried Forward
Action 200418 0404: | Number 11 Analysis (Assessment of Spare Capacity on the Network Utilisation of Obligated Capacity): National Grid to provide historic variance against K factor figures. | 2018-05-01 | National Grid | Colin to provide figures | Carried Forward
Action 200418 0405: | Number 11 Analysis (Assessment of Spare Capacity on the Network Utilisation of Obligated Capacity): Workgroup to make a statement in the Workgroup Report based on the figures from National Grid in Action 0404 If there is volatility to link it back to the relevant objectives. | 2018-05-02 | All Workgroup participants |  | Carried Forward
Action 200418 0406: | National Grid (CW) to provide example for WG’s review in relation to formula year and gas year . | 2018-04-27 | National Grid | No longer needed | Closed
Action 200418 0407: | Proposers asked to check the comparison table and confirm it is as expected. Please notify if there are any inaccuracies by close of play Monday 23 April. | 2018-05-08 | All Workgroup participants | No comments received. Left open to allow for changes. Review daily | Carried Forward
Action 230418 0401: | Joint office to contact Ofgem re: attendance | 2018-04-23 | Joint Office | JO emailed Ofgem 23 April | Closed
Action 230418 0402: | Decision to be made for topic to be covered on 27 April. Should this meeting be cancelled or run a Relevant Obnjectives session. All to provide view 24 April | 2018-04-24 | All Workgroup participants | Meeting to go ahead | Closed
Action 240418 0401: | Danishtah Parker on behalf of DNs to confirm what material will be provided for the discussion on DN Impacts scheduled for 26 April 2018 whether it will be a single response or individual responses. | 2018-04-25 | DP | Completed | Closed
Action 240418 0402: | National Grid to consider the interaction between 0621 decision date (potentially March 2019) and the implementation date and QSEC 2019 and provide clarity on which prices would apply to the auction and which woule be the payable prices. | 2018-05-02 | National Grid | timeline to be provided. | Carried Forward
Action 250418 0401: | TPD Annex B Section Y Charging Methodologies - National Grid to review the Modification Approval Date, Implementation Date and Effective Date in the context of the QSEC Allocation Date. | 2018-05-02 | National Grid |  | Carried Forward
Action 250418 0402: | TPD Annex B Section Y Charging Methodologies - National Grid to clarify if a legal text commentary table would be provided, what it will cover and when it would be available. | 2018-05-04 | National Grid | NG confirmed it will be provided but need to confirm what will be available when (possibly before 17 May Panel). | Carried Forward
Action 250418 0403: | TPD Annex B Section Y Charging Methodologies - National Grid to review the TAR Code Information publication date and consider how these are reflected in the Modifications. | 2018-05-01 | National Grid | Links to Action 120418: 0401 | Carried Forward
Action 260418 0401: | Proposers of K and L to assist in the Workgroup Report Drafting to advise of any wording amendments or additions on the topics that have been covered so far. | 2018-05-04 | K = Gateway LNG Company Ltd L = Shell |  | Carried Forward
Action 260418 0402: | GDN Workgroup participants to add some words to the summary slide of the presentation provided - non transmission services, elaborate on DN customers. Statement about obligations; obligation for NTS to provide 1in20 demand, is the NTS designed to meet that obligation; brief summary of how charges are collected. To be provided as a Word document | 2018-05-02 | GDN Workgroup participants |  | Carried Forward
Action 260418 0403: | GDN Workgroup participants to add some words to the summary slide of the presentation provided - Make it clear on the slides that Commodity is not included in the figures quoted on slide 5 | 2018-05-02 | GDN Workgroup participants |  | Carried Forward
Action 260418 0404: | National Grid to advise when the Indicitive and Final Charges are going to be published - consider offline interactions with DN | 2018-05-02 | DN and National Grid |  | Carried Forward
Action 260418 0405: | WWU Impacts - Direct Connects (slide 9) - on the example of the Very large customer provide a comparison and show if it was a direct connect | 2018-05-02 | WWU (RW/SC)) |  | Carried Forward
Action 260418 0406: | Wording for Workgroup Report to be provided from all 4 DNs by 30 April highlighting concerns and expanding on the Summary slide. | 2018-04-30 | GDN Workgroup participants | this may be duplicated so closed. No responses received. | Closed
Action 260418 0407: | Nations Grid to outline how the validation and assurance of the CWD model takes place | 2018-05-04 | National Grid | update to be provided Friday | Carried Forward
Action 270418 0401: | Joint Office to provide printed copies of the Relevant Objectives document for Workgroup on Monday 30 April. | 2018-04-30 | Joint Office | Completed | Closed
Action 270418 0402: | All Proposers of Alternative Modifications to review the Relevant Objectives document published here: https://www.gasgovernance.co.uk/0621/300418 | 2018-04-30 | Joint Office | on-going, to be picked up in RO discussions. | Closed
Action 270418 0403: | National Grid to provide an updated and amended version of Impact of Optional Charge on Revenue Recovery Rates | 2018-05-01 | National Grid |  | Carried Forward
Action 270418 0404: | Workgroup to review the Optional Charge Impacts - Under Recovery at Respective Points slide and provide comments to National Grid | 2018-05-01 | National Grid |  | Carried Forward
Action 300418 0401 | Christiane Sykes to update 0621L to add further clarifications specific to the Transmission Services Revenue Recovery charge | 2018-05-03 | Shell |  | Pending
Action 300418 0402 | Colin Williams to progress the request for existing capacity to be demonstrated within the CWD model up to the year when existing capacity expires with Julie Cox, and explore how this can accommodated within the time we have remaining. | 2018-05-03 | National Grid |  | Pending
Action 300418 0403 | National Grid to provide all CWD Models and Assumptions document for publishing | 2018-05-02 | National Grid |  | Pending
Action 300418 0404 | National Grid to check the 0621 Modification matches Legal Tex Section Y paragraph 2.4.3 with regards to Exit Nearest Point. | 2018-05-03 | National Grid | Mod to be amended to clarify this. | Closed
Action 300418 0405 | Workgroup to review 0621 Workgroup Relevant Objectives | 2018-05-03 | National Grid |  | Pending