## Slide 1
XRN4361 – UK Link Release 2
XRN4249 – Part B Data Migration Plan
30/04/18

## Slide 2: Introduction/Problem Statement
Change XRN4249 is part of the scope of changes planned to be implemented as part of UK Link Release 2 on the 29th June 2018.
Following analysis of this change, discussion was held with Customers at both ChMC and DSG. Concerns were raised around the migration of the PAF updates from when the process was suspended in April 2017. These concerns relate to the volume of updates required over the period April 17 through to June 18 that could have a downstream impact to Customer systems and business processes.
To minimise the impact of loading all retrospective PAF updates from April 2017, Xoserve are recommending a staggered approach to migrate the data over a number of weekends. This would have checkpoints built into the plan to review the process and agree the volume of updates to be loaded on the next planned date. This approach is expected to reduce the impacts to Customer systems and business processes.

## Slide 3: Data Migration Plan
No | Activity | Start Date | End Date
1 | Part A - Code Deployment as part of R2 Cutover/Implementation | 30/06/2018 | 01/07/2018
2 | Load agreed initial 10K volume of records into SAP ISU | 07/07/2018 | 07/07/2018
3 | NAC File / Portfolio Files / Daily Delta on the back of the initial 10K address update | 08/07/2018 | 08/07/2018
4 | Data Load to SAP BW | 09/07/2018 | 09/07/2018
5 | Agreement with Shippers to load safe volume (100k) records | 09/07/2018 | 13/07/2018
5 | Load the safe volume (100k) records into SAP ISU | 14/07/2018 | 14/07/2018
6 | NAC File / Portfolio Files / Daily Delta on the back of the initial safe volume (100K) address update | 15/07/2018 | 15/07/2018
7 | Daily Load to SAP BW | 16/07/2018 | 16/07/2018
8 | Agreement with Shippers to load the next set of safe volume records (100k) | 16/07/2018 | 20/07/2018
9 | Load the 2nd set of safe volume (100K) records into SAP ISU | 21/07/2018 | 21/07/2018
10 | NAC File / Portfolio Files / Daily Delta on the back of the 2nd set of safe volume (100K) address update | 22/07/2018 | 22/07/2018
11 | Agreement with Shippers to load the remaining updates (approx. 40K) | 23/07/2018 | 27/07/2018
12 | GB places the first Regular PAF file received | 28/07/2018 | 28/07/2018
13 | Load the remaining updates (approx. 40K) into SAP ISU | 28/07/2018 | 28/07/2018
14 | NAC File / Portfolio File / Daily Delta on the back of the remaining (approx. 40K) address updates | 29/07/2018 | 29/07/2018
15 | Daily Load to SAP BW | 30/07/2018 | 30/07/2018
16 | PO Team to pull the first regular file from GB Mailing shared area | 01/08/2018 | 01/08/2018
17 | First regular file load into SAP ISU and BW - 1st production BAU run | 05/08/2018 | 05/08/2018
18 | NAC File / Daily Delta on the back of the first regular PAF file | 06/08/2018 | 06/08/2018

## Slide 4: Next Steps
Present options to Customers at the Delivery Sub Group on 23rd April - Link
Agree if proposed approach is acceptable to Customers
Split XRN4249 into 2 Change Packs, to agree:
  Implementation of the SAP ISU solution to reinstate the GB Mailing Update file process
  Agreement of the proposed Data Migration Plan to apply updates from April 17 to June 18
Update the DSC ChMC Implementation Plan to reflect XRN4249 code implementation and Data Migration Plan - Link
Seek approval of the proposed Data Migration plan at the ChMC on 09th May