## Intro Page
Xoserve Change Delivery Plan on a Page |  | Legend
|  | XXX | Completed Task
| The attached plans give a view of the all change currently being managed by Xoserve via mutiple delivery platforms, UK link, Gemini, and Data. |  | Forcast Activity
| Tab 1 - provides all UK Link impacting change, release 2 & 3 are currently in delivery, releases June-19 and Nov-19 have not yet had the scope for inclusion in the release agreed, therefore any change detailed in these releases are placeholders only. Also sets out potential delivery timelines for CSS (Central Switching Services) and UIG (unidentified Gas). At present RAASP is considered for inclusion in November 2019 release |  | Baseline Activity
| Tab 2 - lists all current live change that feeds into the plans in this publication |  | Potential Actibity
| Tab 3 - Provides a 'look ahead' 2 year view of change for UK Link | RAG | Activity at risk
|  | RAG | Activity with potential risk
|  | RAG | Activity on Track
|  | RAG | Activity under replan/Review

## UK Link POAP
* Excludes Gemini changes
* This is a view of change taken form a point in time and it subject to change

## UK Link_Live_Changes
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritsation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implenmentation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Percieved Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
1154 | 2. Change sanction/approved and in project delivery | R1.0 (Nexus) | UK Link Programme | CP | LIVE | D1 - Change in delivery | 50.75% |  |  | R & N | 2008-03-03 | Chris Smith | Paul Toolan | 1 |  | Project Delivery |  | 2018-09-16 | No Date | 2017-06-01 | Other | Other | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4645 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 2 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 34.23% |  |  | R & N | 2018-04-03 | Rachel Hinsley | Rachel Hinsley | 75 |  | Project Delivery |  | No Date | No Date | 2018-11-02 | ISU | Invoicing | 60-100 days | TRUE | Xoserve | Daily | One | High | 43406 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4468 | 2. Change sanction/approved and in project delivery | Defect R1.16 (Feb'18) | Proposal for the process improvement for SI files | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% | TBP | Medium | R & N | 2017-03-14 | Linda Whitcroft | Donna Johnson | 1.16 | UKLP IADBI307 | Project Delivery |  | 2018-03-30 | No Date | 2017-12-01 | ISU | Invoicing | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4601 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | US01 Exception Remove Dummy Meter Occurrences | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 28.23% |  |  | R & N | 2018-01-30 | Jo Duncan/Dean Johnson | Donna Johnson | 50 |  | ME | XO3650 | No Date | No Date | 2018-06-30 | ISU | Invoicing | 30-60 days | TRUE | Xoserve | Daily | One | Low | 43281 | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4627 | 1. Start-Up (Progressing through change governance) | CSS | Consequential Central Switching Services | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 57.36% |  |  | R & N | 2018-03-09 | Andy Earnshaw | Andy Earnshaw | 0 |  | Project Delivery |  | No Date | No Date | 2020-06-01 | ISU | SPA | 100+ days | FALSE | [5 empty] | License Condition | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Five to Twenty | High | TRUE | TRUE | TRUE | FALSE | FALSE | TRUE | No Date | No Date | No Date | No Date
4347 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0619 - Application of proportionate ratchet charges to daily read sites | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 44.44% |  |  | R & N | 2017-08-17 | Murray Thomson on behalf of JO | Murray Thomson | 0 |  | Project Delivery |  | 2017-09-07 | 2017-09-07 | 2018-10-01 | No Application | No Process | 60-100 days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4528 | 3. Change delivered, awaiting closure approval/sign-off | Minor Enhancement Delivered Change | The word ‘PLOT’ as a prefix | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.03% |  |  | R & N | 2017-11-07 | Mike Orsler/Emma Smith | Donna Johnson | 50 |  | ME | XO3592 | 2018-03-30 | 2018-03-30 | 2018-03-23 | Other | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4510 | 3. Change delivered, awaiting closure approval/sign-off | R1.2 (Dec'17) | Negative Consumption Period For Rolling AQ20171023 | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | R & N | 2017-10-25 | Linda Whitcroft | Debi ¦Jones | 1.2 |  | Project Delivery |  | 2017-12-08 | 2017-12-08 | 2017-12-01 | Other | Other | 0-30days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-08 | No Date | 2017-11-08 | No Date
4529 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0619A Protection from ratchet charges for daily read customers with AQ of 73,200kWh and below MOD0619A | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 44.44% |  |  | R & N | 2017-11-09 | Steve Ganney | Padmini Duvvuri | 0 |  | Project Delivery | 3595 | 2017-12-13 | 2017-12-13 | 2018-10-01 | ISU | Invoicing | 0-30days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-12-13 | No Date | No Date | No Date
4513 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Change to validation of address fields | CR (Internal) | LIVE | D1 - Change in delivery | 25.23% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI359 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | CMS | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | TRUE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4543 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | UNC Modification 0636 - - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 46.25% |  |  | R & N | 2017-11-28 | Debra Hawkin | Padmini Duvvuri | 50 |  | Project Delivery |  | 2017-12-11 | 2017-12-13 | 2018-06-01 | ISU | Reads | 0-30days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4554 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Amendment Invoice validation Reports | CR (Internal) | LIVE | D1 - Change in delivery | 22.82% |  |  | R & N | 2017-12-05 | Vicky Spiller | Donna Johnson | 50 |  | ME | XO3613 | 2018-06-30 | No Date | 2018-06-30 | ISU | Invoicing | 0-30days | TRUE | Xoserve | Monthly | One | High | 43800 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4465 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Annual Production and notification of LIS-3years read | CR (Internal) | LIVE | D1 - Change in delivery | 54.35% | TBP | Low | R & N | 2017-02-21 | Emma Smith | Donna Johnson | 50 | UKLP IADBI301 | ME | XO3624 | 2018-05-15 | No Date | 2018-05-15 | ISU | Reads | 30-60 days | TRUE | Xoserve | Annually | One | LOW | 43465 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4514 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | MIV File Changes for MUR Invoice - CMS | CR (Internal) | LIVE | D1 - Change in delivery | 44.74% |  |  | R & N | 2017-10-25 | Richard Cresswell | Christina Francis | 2 | UKLP IADBI367 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | CMS | Invoicing | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4316 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Meter Point Details Report & Sector Breakdown Report | CR (Internal) | LIVE | D1 - Change in delivery | 39.04% | TBP | Low | R & N | 2017-04-07 | Mark Cockayne | Christina Francis | 2 | UKLP315 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4449 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | PSR requirements – Vulnerable Customer data requirements | CP | LIVE | D1 - Change in delivery | 18.02% | High | High | R & N | 2016-11-11 | Steve Nunnington | Christina Francis | 2 | UKLP273 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3995a | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Energy Theft Tip-off Service Data Provision | CP | LIVE | D1 - Change in delivery | 44.74% | TBP | High | R & N | 2016-03-15 | Alex Ross-Shaw | Christina Francis | 2 | UKLP222 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4469 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | UMR Hierarchy Amendment in AMT | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 29.43% | TBP | Low | R & N | 2017-03-27 | Karen Marklew | Matt Rider | 75 | UKLP IADBI309 | Project Delivery | 3628 | 2018-06-11 | No Date | 2018-10-01 | AMT | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4249 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Address Maintenance Solution | CR (Internal) | LIVE | D1 - Change in delivery | 44.74% |  |  | R & N | 2017-03-22 | Steve Ganney | Christina Francis | 2 |  | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4484 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | Remove restriction on nominated SOQ (as per MOD 445 | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 38.44% |  |  | R & N | 2017-06-06 | Bhupinder Basra | Matt Rider | 75 | UKLP IADBI336 | Project Delivery |  | 2018-06-11 | No Date | 2018-10-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4299 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Reports required under UNC TPD V16.1 in Nexus (reports required by Mod 520A) | CP | LIVE | D1 - Change in delivery | 50.75% | High | High | R & N | 2016-08-12 | Steve Nunnington | Christina Francis | 2 | UKLP251 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4303 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Remove ‘n’ as an allowable value from the .SFN file in ‘Fault corrected’ field and remove as allowable value from AMT & SAP ISU. | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% | TBP | Low | R & N | 2016-10-18 | Dean Johnson | Christina Francis | 2 | UKLP267 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4304 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Amend referral rules for class 2 smaller LSP’s | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% | TBP | Medium | R & N | 2016-11-03 | Dean Johnson | Christina Francis | 2 | UKLP270 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4309 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Back billing for domestic (SSP) sites needs to be reflect thecorrect adjustment start date | CR (Internal) | LIVE | D1 - Change in delivery | 50.75% | TBP | Low | R & N | 2016-01-19 | Dean Johnson | Christina Francis | 2 | UKLP287 | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | CMS | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
2831.5b | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Changes to the upper parameter of the XDO partial refresh file. Post Nexus (R2) | CR (Internal) | LIVE | D1 - Change in delivery | 25.83% | TBP | High | R & N | 2017-02-07 | Jon Follows | Christina Francis | 2 | UKLP292 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | FALSE | FALSE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4524 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | Change to generation logic of RDP data flows to include all recorded iGT Supply Points within UK Link systems | CR (Internal) | LIVE | D1 - Change in delivery | 40.84% |  |  | R & N | 2017-10-31 | Paul Orsler | Donna Johnson | 50 |  | ME | XOS3657 | 2018-11-09 | No Date | 2018-11-09 | ISU | Other | 30-60 days | FALSE | [5 empty] | License Condition | Multiple Market Participants | TRUE | TRUE | TRUE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | No Date | No Date | No Date | No Date
4527 | 3. Change delivered, awaiting closure approval/sign-off | New Service Line (Mar'18) | New Service Line for Reporting Services to Performance Assurance Committee (PAC) | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | R & N | 2017-11-01 | John Welsh/Rachel Hinsley | Andy Miller | 0 |  | Non PM delivery (Commercial) |  | No Date | No Date | 2017-12-01 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-15 | No Date | No Date | No Date
3477 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Missing Key Data Item from iGT’s to Shippers (Plot Number) | CP | LIVE | D1 - Change in delivery | 30.93% | High | High | R & N | 2015-07-07 | Lee Chambers | Christina Francis | 2 | UKLP IADBI112 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | BW | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-10 | 2018-01-10 | No Date
4288 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | DDS/DDU file amendment | CP | LIVE | D1 - Change in delivery | 25.23% | Low | High pending discussions with all Networks | R & N | 2015-10-14 | Matt Smith | Christina Francis | 2 | UKLP IADBI147 | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3699 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | IA for strategic solution options for the GDE Offline database | CR (Internal) | LIVE | X1 - Xoserve propose change not required | 27.63% | Low | Low | R & N | 2015-05-15 |  | Padmini Duvvuri | 99 | UKLP IADBI096 | Project Delivery |  | No Date | No Date | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3283 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Recording of DN Siteworks’ / New Network Connection Reference in Central systems (ON HOLD PENDING NEW CO) | CP | LIVE | D1 - Change in delivery | 28.83% | Low | Low | R & N | 2013-12-16 | Joel Martin | Christina Francis | 2 | n/a | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | ISU | SPA | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 21: Data Flows and Services to Network Operators | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
3386 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Create new “role” for CMS to cover all activities undertaken within a Distribution Network (ON HOLD PENDING NEW CO) | CP | LIVE | D1 - Change in delivery | 34.23% | Low | Low | R & N | 2014-05-08 | Jo Ferguson | Christina Francis | 2 | n/a | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | CMS | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 22: Specific Services | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4248 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Quarterly smart metering reporting for HS&E and GDNs (post Nexus R2) | CP | LIVE | D1 - Change in delivery | 39.34% | High | High | R & N | 2017-03-22 | Joanna Ferguson | Christina Francis | 2 | n/a | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4556 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Process to provide a report when Gas Safety Regulations requests return no MPRN’s | CP | LIVE | C1 - Delivery Business Case/BER in progress | 34.83% |  |  | R & N | 2017-12-06 | Andy Clasper | Matt Rider | 50 |  | ME | XO3614 | 2018-05-25 | No Date | 2018-02-23 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | TRUE | FALSE | Service Area 22: Specific Services | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | No Date | No Date | No Date
4361 | 2. Change sanction/approved and in project delivery | R2.0 (Jun'18) | Release 2 Delivery | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | R & N | 2017-10-11 | Christina Francis | Christina Francis | 2 |  | Project Delivery |  | 2018-06-29 | No Date | 2018-05-01 | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-11 | 2017-10-11 | 2018-01-10 | No Date
4598 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | Changes to settlement regime to address Unidentified Gas issues issues including retrospective correction(MOD 643) | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 27.03% |  |  | R & N | 2018-01-25 | Lorna Lewin (Orsted) Lorna Lewin (Orsted) Lorna Lewin ( Orsted ) | Steve Ganney | 0 |  | Project Delivery |  | 2018-02-07 | 2018-02-08 | 2018-02-07 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4599 | 1. Start-Up (Progressing through change governance) | MOD (Not yet landed as a CP) | Changes to settlement regime to address Unidentified Gas issues (642A) | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 27.03% |  |  | R & N | 2018-01-25 | Kirsty Dudley (Eon) | Steve Ganney | 0 |  | Project Delivery |  | 2018-02-07 | 2018-02-08 | 2018-02-07 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4439 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | GDE Cashout – Daily Curtailment Volume (DCV) for Daily Metered sites | CR (Internal) | LIVE | X1 - Xoserve propose change not required | 27.63% | Low | Low | R & N | 2016-08-04 | Lorraine Cave | Padmini Duvvuri | 99 | UKLP IADBI244 | Project Delivery |  | No Date | No Date | 2000-02-02 | Gemini | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4521 | 2. Change sanction/approved and in project delivery | Minor Enhancement Delivered Change | NTS Datalogged Site not being loaded into Gemini | CR (Internal) | LIVE | D1 - Change in delivery | 39.64% |  |  | R & N | 2017-10-31 | Liz Ryan/Emma Lyndon | Donna Johnson | 50 |  | ME | XOS3587 | 2018-05-15 | No Date | 2018-04-30 | Gemini | Other | 0-30days | TRUE | Both Xoserve & Customer | Daily | One | Medium | 43800 | License Condition | One Market Participant | FALSE | TRUE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4358 | 3. Change delivered, awaiting closure approval/sign-off | Minor Enhancement Delivered Change | Offline Systems Database D096 Phase 2 | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 15.02% |  |  | R & N | 2017-09-04 | Dan Donovan | Donna Johnson | 50 |  | ME | XO3558 | 2018-04-30 | 2018-04-12 | 2018-10-31 | Other | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4534 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Amendment to RGMA Validation Rules for Meter Asset Installation Date | CP | LIVE | D1 - Change in delivery | 54.65% |  |  | R & N | 2017-11-20 | Andrew Margan | Padmini Duvvuri | 3 |  | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | No Process | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | 2018-01-10 | 2018-02-07 | 2018-04-11 | No Date
4186 | 3. Change delivered, awaiting closure approval/sign-off | R1.1 (Dec'17) | UK Link Future Release Analysis | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 15.62% |  |  | R & N | 2017-01-30 | Jane Rocky | Lee Chambers | 0 |  | Project Delivery |  | 2017-10-11 | 2017-11-16 | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4538 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Insertion of Maximum Number of Occurrences in Meter Inspection Date Notice (MID) File. | CR (Internal) | LIVE | D1 - Change in delivery | 18.02% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Project Delivery |  | 2018-11-09 | No Date | 2018-11-09 | ISU | No Process | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4539 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | New File Level Rejection | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | R & N | 2017-11-21 | Rachel Hinsley/Dave Addison | Padmini Duvvuri | 3 |  | Project Delivery |  | 2018-11-09 | No Date | 2018-11-01 | ISU | Invoicing | 0-30days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4453 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | File Format Should Have Changes | CR (Internal) | LIVE | D1 - Change in delivery | 35.44% | TBP | Low | R & N | 2016-12-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI280v3 | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4454 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Cadent Billing - DN Sales (Outbound Services) | CP | LIVE | D1 - Change in delivery | 57.96% | TBP | High | R & N | 2016-12-16 | Linda Whitcroft | Padmini Duvvuri | 3 | UKLP IADBI281 | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | TRUE | Both Xoserve & Customer | Daily | Two to Five | High | 43252 | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | High | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | 2017-12-13 | 2018-02-07 | 2018-04-11 | No Date
4273 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Introducing IHD (In-Home Display) Installed Status of Failed MOD614 | CP | LIVE | D1 - Change in delivery | 27.03% |  |  | R & N | 2017-05-10 | Alex Cebo | Padmini Duvvuri | 3 |  | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Other | 31-100days | FALSE | [5 empty] | SPAA Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-08 | 2018-02-07 | 2018-04-11 | No Date
4337 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | To change the optionality of the Supply Point confirmation reference for the T51 file | CR (Internal) | LIVE | D1 - Change in delivery | 40.24% |  |  | R & N | 2017-07-24 | Sue prosse/Emma Lyndon | Padmini Duvvuri | 3 |  | Project Delivery |  | 2018-11-09 | No Date | 2018-04-01 | ISU | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4495 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Energy Tolerance Rejection code | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | R & N | 2017-06-28 | Nick Timm | Padmini Duvvuri | 3 | UKLP IADBI356 | Project Delivery | 3627 | 2018-11-09 | No Date | 2018-11-01 | ISU | Reads | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
3656 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Read Validation Tolerances | CP | LIVE | D1 - Change in delivery | 25.23% | TBP | Low | R & N | 2014-12-24 | Michelle Downes | Padmini Duvvuri | 3 | UKLP IADBI060 | Project Delivery |  | 2018-11-09 | No Date | 2018-05-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4431 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Reads failing market breaker tolerance to be accepted for correct date following AQ Correction | CR (Internal) | LIVE | D1 - Change in delivery | 36.04% | TBP | High | R & N | 2016-05-04 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI202 | Project Delivery |  | 2018-11-09 | No Date | 2018-10-01 | ISU | Reads | 31-100days | TRUE | External Customer | Daily | No Xoserve FTEs | Low | 43465 | MOD/Ofgem | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4443 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | File Format Changes Aug 16 Unique Sites (deferred items from CR252) | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% | TBP | Low | R & N | 2016-09-16 | Marie Berlin | Padmini Duvvuri | 3 | UKLP IADBI258 | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | Low | 43465 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | TRUE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4461 | 4. Change proposed to be rejected by Xoserve (awaiting closure approval) | Out for industry sponsorship/approval to reject | Splitting of the DXI inbound and DXR outbound file from the DCC. | CR (Internal) | LIVE | X1 - Xoserve propose change not required | 22.82% | TBP | Consensus is Medium, One DN had a recommendation of high | R & N | 2017-02-07 | Jon Follows | Paul Orsler | 99 | UKLP IADBI293 | Project Delivery |  | No Date | No Date | 2018-12-31 | ISU | SPA | 31-100days | TRUE | Xoserve | No Workaround Frequency | No Xoserve FTEs | LOW | 43465 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4458 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Class 4 CSEPS Reconciliation Variance Identification | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% | TBP | Medium | R & N | 2017-01-26 | Karen Marklew | Padmini Duvvuri | 3 | UKLP IADBI289 | Project Delivery |  | 2018-11-09 | No Date | 2018-12-31 | ISU | Reads | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | LOW | 43465 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4486 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Meter Type O = Oriffice to be an acceptable value in file formats and reports | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | R & N | 2017-06-05 | Emma Smith | Padmini Duvvuri | 3 | UKLP IADBI338 | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | SPA | 31-100days | TRUE | Both Xoserve and Customer | No Workaround Frequency | No Xoserve FTEs | Low | 43465 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4481 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Resolution of penny mismatches within invoice supporting information for Core invoices. | CR (Internal) | LIVE | D1 - Change in delivery | 33.63% |  |  | R & N | 2017-05-30 | Kiran Kumar | Padmini Duvvuri | 3 | UKLP IADBI332 | Project Delivery |  | 2018-11-09 | No Date | 2018-06-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4480 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | Capacity reconciliation charge (MOD445) calculation functionality | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 50.45% |  |  | R & N | 2017-05-30 | Kiran Kumar | Matt Rider | 75 | UKLP IADBI331 | Project Delivery |  | 2018-06-11 | No Date | 2018-10-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4572 | 2. Change sanction/approved and in project delivery | R3.0 (Nov'18) | Retail & Network Release 3 | CP | LIVE | D1 - Change in delivery | 15.62% |  |  | R & N | 2018-01-03 | Padmini Duvvuri | Padmini Duvvuri | 3 |  | Project Delivery |  | 2018-11-09 | No Date | 2018-10-31 | ISU | No Process | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | 2018-02-07 | 2018-04-11 | No Date
4482 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP Meter Read Entry Screen | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 18.62% |  |  | R & N | 2017-05-30 | Emma Smith | Donna Johnson | 50 | UKLP IADBI333 | ME | XO3629 | No Date | No Date | 2018-07-27 | ISU | Reads | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4496 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | iGT Address Amendments - SAP | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 37.24% |  |  | R & N | 2017-06-30 | Richard Cresswell | Matt Rider | 75 | UKLP IADBI358 | Project Delivery |  | 2018-06-11 | No Date | 2018-12-31 | ISU | SPA | 31-100days | TRUE | Xoserve | Daily | No Xoserve FTEs | High | 43465 | ChMC endorsed Change Proposal | One Market Group | FALSE | FALSE | TRUE | Service Area 1: Manage Supply Point Registration | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4612 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | RGMA Activity on Transfer Date | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 69.97% |  |  | R & N | 2018-02-20 | John Harris | Matt Rider | 75 |  | Project Delivery |  | 2018-06-11 | No Date | 2018-04-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | Two to Five | High | TRUE | TRUE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4574 | 2. Change sanction/approved and in project delivery | R&N New Environment (Apr'18) | Provision of a New Project Track UK Link Environment | CR (Internal) | LIVE | D1 - Change in delivery | 21.62% |  |  | R & N | 2018-01-08 | Lee Chambers | Lee Chambers | 0 |  | Project Delivery |  | 2018-06-29 | No Date | 2018-06-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4573 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | AQ Market Breaker Tolerance validation values Error | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 31.53% |  |  | R & N | 2018-01-03 | Sue Prosser | Donna Johnson | 50 |  | ME | XO3623 | No Date | No Date | 2018-02-16 | ISU | Reads | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4576 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | Class 4 Transfer Reads not visible to shippers in DES | CP | LIVE | C1 - Delivery Business Case/BER in progress | 18.02% |  |  | R & N | 2018-01-09 | Alison Cross | Matt Rider | 75 |  | Project Delivery | XO3630 | No Date | No Date | No Date | BW | Portal | 30-60 days | TRUE | External Customer | Monthly | One | Low | 43189 | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-03-07 | No Date | No Date | No Date
4584 | 1. Start-Up (Progressing through change governance) | CSS | Central Switching Services | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 21.02% |  |  | R & N | 2018-01-17 | Andy Earnshaw | Smitha Pichrikat | 0 |  | Project Delivery |  | 2022-02-28 | No Date | 2020-12-01 | No Application | No Process | 100+ days | FALSE | [5 empty] | MOD/Ofgem | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4587 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Test of the Bulk upload facility | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 69.97% |  |  | R & N | 2018-01-22 | Dawn Gallacher | Donna Johnson | 50 |  | ME | XO3648 | No Date | No Date | 2018-04-30 | ISU | SPA | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | TRUE | FALSE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4593 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | Removal of Backbiling Exceptions (BB02, BB04, BB05) | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 25.83% |  |  | R & N | 2018-01-23 | Jo Duncan | Donna Johnson | 50 |  | ME | XO3645 | No Date | No Date | 2018-06-30 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 43281 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4595 | 1. Start-Up (Progressing through change governance) | Minor Enhancement Delivered Change | SAP T-Code Access – Modification to ISU & BW Permissions for Data Office Aligned Resources | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 27.63% |  |  | R & N | 2018-01-23 | Steve Concannon | Donna Johnson | 50 |  | ME | XO3646 | No Date | No Date | 2018-02-28 | AMT | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4651 | 1. Start-Up (Progressing through change governance) | Candidate for Minor Release 1 | Analysis for the development of a Bulk Transfer Tool (for use in scenarios outside of the “Supplier of Last Resort” Process) | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 27.63% |  |  | R & N | 1205780 | James Verdon | Matt Rider | 75 |  | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | SPA | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4658 | 1. Start-Up (Progressing through change governance) | Out for industry sponsorship/approval to reject | Read validation – increasing outer tolerance value for specific AQ bands for Class 3 & 4 Meter Points | CP | LIVE | A2 - Capture in Progress | 58.26% |  |  | R & N | 2018-04-25 | Emma Smith | Dave Addison | 0 |  | Project Delivery |  | No Date | No Date | 2018-06-01 | ISU | Reads | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Medium | TRUE | TRUE | TRUE | FALSE | TRUE | TRUE | No Date | No Date | No Date | No Date
4642 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Address Maintenance Solution | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 42.04% |  |  | R & N | 2018-04-03 | Nandini Kundu | Linda Whitcroft | 4 |  | No Delivery Team |  | No Date | No Date | 2018-10-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | License Condition | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4621 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Suspension of the Validation between Meter Index and Uncoverted Converter Index | CP | LIVE | A6 - Change Proposal out for Shipper Consultation | 24.62% | 0 | 0 | R & N | 2018-02-27 | Rachel Hinsley | Lee Chambers | 4 | 176 & 182 | Project Delivery |  | No Date | No Date | 2019-02-01 | ISU | Reads | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Low | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4545 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | UNC Modification 0619B - Application of proportionate ratchet charges to daily read sites | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 44.44% |  |  | R & N | 2017-11-29 | Steve Ganney | Murray Thomson | 4 |  | Project Delivery |  | 2017-12-13 | 2017-12-13 | 2018-10-01 | ISU | No Process | 60-100 days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-12-13 | No Date | No Date | No Date
4597 | 1. Start-Up (Progressing through change governance) | R4.0 (Jun'19) | Changes to settlement regime to address Unidentified Gas issues (MOD642) | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 27.03% |  |  | R & N | 2018-01-25 | Justine Price (Corona Energy) | Steve Ganney | 4 |  | Project Delivery |  | 2018-02-07 | 2018-02-08 | 2018-02-07 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4541 | 1. Start-Up (Progressing through change governance) | R5.0 (Nov'19) | Read Design Gaps - Missing Overide Flags In RGMA and Retro Files Linked to Retro (4474) | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 29.43% | Low | Low - to be reviewed in 3 months time | R & N | 2015-02-10 | Emma Smith | Lee Chambers | 5 | UKLP IADBI073 | Project Delivery |  | 2018-06-28 | No Date | 2018-11-01 | ISU | RGMA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | Two to Five | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4474 | 1. Start-Up (Progressing through change governance) | R5.0 (Nov'19) | Delivery of Retro | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 37.24% | TBP | High | R & N | 2017-04-21 | Lee Chambers | Lee Chambers | 5 | UKLP IADBI319 | Project Delivery |  | 2019-06-28 | No Date | 2019-02-01 | ISU | Other | 31-100days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 1: Manage Supply Point Registration | Five to Twenty | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4378 | 3. Change delivered, awaiting closure approval/sign-off | Solution Manager Update (Feb'18) | Solution Manager Upgrade | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | R & N | 2017-10-02 | Smitha Pichrikat | Smitha Pichrikat | 0 |  | Project Delivery |  | 2018-04-16 | 2018-04-16 | 2018-04-03 | ISU | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4575 | 2. Change sanction/approved and in project delivery | R&N Minor Release/Impact Assessment (Mar'18) | Introduction of a R&N Minor Release Delivery Mechanism | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | R & N | 2018-01-09 | Lee Chambers | Lee Chambers | 0 |  | Project Delivery |  | 2018-05-15 | No Date | 2018-05-15 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date

## UK Link_2yr_view
|  | Change Allocation | Count of XRNs
|  | Solution Manager Update (Feb'18) | 1
|  | Release Nov 19 | 2
|  | Release Jun 19 | 4
|  | Release Feb 19 | 0
|  | R3.0 (Nov'18) | 15
|  | R2.0 (Jun'18) | 17
|  | R1.2 (Dec'17) | 1
|  | R1.1 (Dec'17) | 1
|  | R1.0 (Nexus) | 1
|  | R&N New Environment (Apr'18) | 1
|  | R&N Minor Release/Impact Assessment (Mar'18) | 1
|  | Out for industry sponsorship/approval to reject | 4
|  | New Service Line (Mar'18) | 1
|  | MOD (Not yet landed as a CP) | 5
|  | Minor Enhancement Delivered Change | 13
|  | Defect R1.16 (Feb'18) | 1
|  | CSS | 2
|  | Candidate for Minor Release 2 | 1
|  | Candidate for Minor Release 1 | 7
|  | Grand Total | 78
Please filter in column C within the 'R&N_Live_Changes' tab to view specific XRNs
Release Jun 19 | Only 4 XRNs are shown assigned in the Change Register, 3 changes are Mods from the bubbling under report that are yet to be approved.
Release Nov 19 | Only 2 XRNs are shown assigned in the Change Ragister the other 1 change is a Mod from the bubbling under report that is yet to be approved.

## Sheet4 (hidden)
Row Labels | Count of XRN Ref
(blank)
Solution Manager Update (Feb'18) | 1 | X
R5.0 (Nov'19) | 2 | X
R4.0 (Jun'19) | 4 | X
R3.0 (Nov'18) | 15 | X
R2.0 (Jun'18) | 17 | X
R1.2 (Dec'17) | 1 | X
R1.1 (Dec'17) | 1 | X
R1.0 (Nexus) | 1 | X
R&N New Environment (Apr'18) | 1 | X
R&N Minor Release/Impact Assessment (Mar'18) | 1 | X
Out for industry sponsorship/approval to reject | 4
New Service Line (Mar'18) | 1 | X
MOD (Not yet landed as a CP) | 5 | X
Minor Enhancement Delivered Change | 13 | X
Defect R1.16 (Feb'18) | 1 | X
CSS | 2 | X
Candidate for Minor Release 2 | 1 | X
Candidate for Minor Release 1 | 7 | X
Grand Total | 78

## Gemini & Data Stream POAP (hidden)
Gemini
Data Platform

## Gemini & Data Stream_Live_Chang (hidden)
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritsation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implenmentation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Percieved Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4618 | 2. Change sanction/approved and in project delivery |  | ASR - Billing History by all NTS Capacity & Commodity Sites | CR (ASR) | LIVE | D1 - Change in delivery | 33.63% |  |  | Data Office | 2018-02-26 | Greg Causon | Jo Duncan | 50 |  | ME | XO3672 | 2018-05-15 | No Date | 2018-05-15 | Gemini | No Process | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Group | FALSE | TRUE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4619 | 1. Start-Up (Progressing through change governance) |  | SAP BW MPRL Delta Table Creation | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 19.82% |  |  | Data Office | 2018-02-26 | Steve Concannon | Donna Johnson | 50 |  | ME | XO3665 | 2018-08-30 | No Date | 2018-08-30 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4620 | 1. Start-Up (Progressing through change governance) |  | UNC Modification 0636B - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 30.03% |  |  | Data Office | 2018-02-27 | Steve Pownall | Murray Thomson | 0 |  | Project Delivery |  | 2018-03-12 | 2018-03-13 | 2018-03-12 | Gemini | Other | 0-30 days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Participants | TRUE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4639 | 2. Change sanction/approved and in project delivery |  | Customer KVI Reporting | CR (Internal) | LIVE | D1 - Change in delivery | 57.96% |  |  | Data Office | 2018-03-27 | Michele Downes | Jo Duncan | 0 |  | Project Delivery |  | 2018-06-01 | No Date | 2018-05-01 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 43217 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 19: Network Operator and User Relationship Management | All | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4643 | 1. Start-Up (Progressing through change governance) |  | Shipper Read Performance Reporting | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 41.14% |  |  | Data Office | 2018-04-03 | Rachel Hinsley | Rachel Hinsley | 0 |  | Project Delivery |  | No Date | No Date | 2018-06-30 | BW | Reads | 30-60 days | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4644 | 2. Change sanction/approved and in project delivery |  | Analysis related to Meter Reading Tolerance Failures | CR (Internal) | LIVE | D1 - Change in delivery | 44.44% |  |  | Data Office | 2018-04-03 | Rachel Hinsley | Harfan Ahmed | 0 |  | Project Delivery |  | 2018-05-25 | No Date | 2018-04-16 | BW | Reads | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | FALSE | Service Area 5: Metered Volume and Metered Quantity | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4646 | 1. Start-Up (Progressing through change governance) |  | Amendment to plot to postal report | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 34.83% |  |  | Data Office | 2018-04-10 | Tahera Choudhury | Jo Duncan | 0 |  | Project Delivery |  | No Date | No Date | 2018-05-04 | BW | SPA | 0-30 days | FALSE | [5 empty] | MOD/Ofgem | One Market Group | FALSE | TRUE | TRUE | No DSC Service Area | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4647 | 1. Start-Up (Progressing through change governance) |  | IS Operations - Service Management Performance Birst Dashboards | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 31.23% |  |  | Data Office | 2018-04-13 | Luke Moise | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-11 | No Date | 2018-05-15 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Low | 43235 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4623 | 2. Change sanction/approved and in project delivery |  | XEC Customer Dashboard Development | CR (Internal) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2018-02-05 | James Verdon | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-11 | No Date | 2018-05-11 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4605 | 1. Start-Up (Progressing through change governance) |  | ASR - Orsted Asset Report (PPN) | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 30.03% |  |  | Data Office | 2018-02-12 | Ryan Larner | Jo Duncan | 0 |  | Project Delivery |  | No Date | No Date | 2018-02-28 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Xoserve Only | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4606 | 1. Start-Up (Progressing through change governance) |  | UNC Modification 0636A - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 27.03% |  |  | Data Office | 2018-02-15 | Nick Wye | Murray Thomson | 0 |  | Project Delivery |  | 2018-03-01 | 2018-03-01 | 2018-03-01 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4625 | 1. Start-Up (Progressing through change governance) |  | Retrospective - Change of Supply API Prototype Development for British Gas | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 17.42% |  |  | Data Office | 2018-02-05 | Iain Snookes | Mark Pollard | 0 |  | Project Delivery |  | 2018-12-31 | No Date | 2018-12-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | Service Area 23: Internal | One | Low | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4602 | 1. Start-Up (Progressing through change governance) |  | ASR - BUS NS S1 Report | CR (ASR) | LIVE | B3 - ASR/PAC HLE awaiting customer approval | 28.83% |  |  | Data Office | 2018-01-31 | Greg Causon | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-25 | No Date | 2018-05-25 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4565 | 2. Change sanction/approved and in project delivery |  | Request to add a new report to production and schedule on a weekly basis. (Npower) | CR (ASR) | LIVE | D1 - Change in delivery | 33.63% |  |  | Data Office | 2017-12-19 | Emma partlett | Jo Duncan | 0 |  | Project Delivery |  | 2018-04-27 | No Date | 2018-04-27 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Group | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4542 | 2. Change sanction/approved and in project delivery |  | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | CP | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2017-11-24 | Emma Smith | Jo Duncan | 0 |  | Project Delivery | XO3605 | 2018-05-25 | No Date | 2018-11-01 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 43495 | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-01-10 | No Date | 2018-04-11 | No Date
4380 | 3. Change delivered, awaiting closure approval/sign-off |  | Monthly Nomination Referral Report | CP | LIVE | F1 - CCR/Closedown document in progress | 39.04% |  |  | Data Office | 2017-10-25 | Matt Smith | Tom Lineham | 0 | UKLP IADBI337 | Project Delivery |  | 2018-02-23 | 2018-02-23 | 2018-01-19 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | FALSE | TRUE | FALSE | Service Area 21: Data Flows and Services to Network Operators | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-11-27 | No Date | 2017-12-13 | 2018-03-07
4563 | 1. Start-Up (Progressing through change governance) |  | Assurance of the Annual AQ activities | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 56.76% |  |  | Data Office | 2017-12-18 | Sue Prosser | Donna Johnson | 50 |  | ME | 3632 | No Date | No Date | 2018-03-17 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 6: Annual Quantity / DM Supply Point and Offtake Rate Reviews | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4579 | 3. Change delivered, awaiting closure approval/sign-off |  | Monthly EUC1 and 2 Report | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 36.94% |  |  | Data Office | 2018-01-16 | Ryan Larner | Jo Duncan | 0 |  | Project Delivery |  | 2018-02-23 | 2018-02-23 | 2018-02-23 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4580 | 1. Start-Up (Progressing through change governance) |  | Shipper Performance Birst Dashboard (by Data Cleansing Topic) | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 19.82% |  |  | Data Office | 2018-01-16 | James Verdon | Jo Duncan | 0 |  | Project Delivery |  | 2018-08-10 | No Date | 2018-08-10 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4328 | 2. Change sanction/approved and in project delivery |  | Report of iGT Meter Points where the confirming shipper is not the elected shipper | CP | LIVE | D1 - Change in delivery | 34.23% |  |  | Data Office | 2017-07-05 | Emma Smith | Jo Duncan | 50 |  | ME | XOS3615 | 2018-08-10 | No Date | 2018-08-10 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | TRUE | Service Area 18: Provision of User Reports and Information | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-07-13 | 2018-03-07 | 2018-04-11 | No Date
4426 | 1. Start-Up (Progressing through change governance) |  | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of Ofgem RFI | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 47.45% | TBP | High | Data Office | 2016-04-28 | Paul Orsler | Jo Duncan | 0 | UKLP IADBI192 | Project Delivery |  | No Date | No Date | 2018-02-28 | BW | Other | 31-100days | FALSE | [5 empty] | CMA Order | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4525 | 1. Start-Up (Progressing through change governance) |  | Transparency of the Rolling AQ Process | CP | LIVE | C3 - BER Awaiting ChMC approval | 34.83% |  |  | Data Office | 2017-10-31 | Shane Preston/Rachel Hinsley | Jo Duncan | 0 |  | Project Delivery | XOS3584 | 2018-05-25 | No Date | 2018-05-25 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-02-07 | No Date | No Date | No Date
4610 | 1. Start-Up (Progressing through change governance) |  | ASR Request - Reporting to SPAA Secretariat in Support of SPAA Schedule 25 – Management of Prepayment Activities | CR (ASR) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 24.02% |  |  | Data Office | 2018-02-20 | Greg Causon | Jo Duncan | 0 |  | Project Delivery |  | No Date | No Date | 2018-06-30 | BW | SPA | 60-100 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Participants | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4611 | 1. Start-Up (Progressing through change governance) |  | Replacement/Upgrade of Demand Estimation Systems and Processes | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 28.23% |  |  | Data Office | 2018-02-20 | Fiona Cottam | Fay Morris | 0 |  | Project Delivery |  | 2019-02-28 | No Date | 2019-03-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4493 | 3. Change delivered, awaiting closure approval/sign-off |  | BIRST Connect integration | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 27.63% |  |  | Data Office | 2017-06-26 | Steve Concannon | Emma Rose | 50 | UKLP IADBI353 | Project Delivery |  | 2018-01-26 | 2018-01-26 | 2017-11-30 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4555 | 1. Start-Up (Progressing through change governance) |  | Provision of a web portal to enable GDNs to access customer contact details | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 27.03% |  |  | Data Office | 2017-12-06 | Richard Pomroy | Murray Thomson | 0 |  | Project Delivery |  | 2018-02-20 | 2018-03-26 | 2018-02-20 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | FALSE | TRUE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4551 | 3. Change delivered, awaiting closure approval/sign-off |  | Amendment to TOG reporting | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 34.83% |  |  | Data Office | 2017-12-06 | Kieran McNulty/Dave Acker/Sat Salsi | Jo Duncan | 0 |  | Project Delivery | XO3611 | 2018-02-23 | 2018-02-23 | 2018-02-28 | CMS | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4596 | 1. Start-Up (Progressing through change governance) |  | Setup of File Transfer mechanism from BO to IX | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 27.63% |  |  | Data Office | 2018-01-23 | Steve Concannon | Donna Johnson | 50 |  | ME | XO3647 | 2018-05-12 | No Date | 2018-04-30 | IX | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4616 | 1. Start-Up (Progressing through change governance) |  | Introduction of New EUCs and Improvements in the CWV MOD 644 | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 27.03% |  |  | Data Office | 2018-02-22 | Steve Ganney | Steve Ganney | 0 |  | Project Delivery |  | 2018-05-11 | 2018-04-30 | 2018-05-11 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | No Change Beneficiary | TRUE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4615 | 2. Change sanction/approved and in project delivery |  | Measurement of history for all NTS Entry and Exit points | CR (ASR) | LIVE | D1 - Change in delivery | 33.63% |  |  | Data Office | 2018-02-22 | Greg Causon | Jo Duncan | 0 |  | Project Delivery |  | 2018-04-27 | No Date | 2018-04-30 | BW | No Process | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Group | FALSE | TRUE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4631 | 1. Start-Up (Progressing through change governance) |  | UNC Modification 0636C - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | A5 - Change Proposal awaiting MOD approval (ROM complete) | 30.03% |  |  | Data Office | 2018-03-16 | Steve Pownall | Murray Thomson | 0 |  | Project Delivery |  | 2018-04-05 | 2018-04-05 | 2018-03-30 | Gemini | Other | No Delivery Effort | FALSE | [5 empty] | MOD/Ofgem | Multiple Market Participants | TRUE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4473 | 1. Start-Up (Progressing through change governance) |  | Sybase NLS Solution Design Gap | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 18.62% | TBP | Low | Data Office | 2017-04-11 | Lee Chambers | Jo Duncan | 0 | UKLP IADBI317 | Project Delivery |  | No Date | No Date | 2018-06-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4511 | 3. Change delivered, awaiting closure approval/sign-off |  | Monthly AQ performance statistics | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 33.03% |  |  | Data Office | 2017-10-25 | Sue Prosser | Jo Duncan | 0 |  | Project Delivery | XOS3588 | 2018-01-19 | 2018-01-19 | 2018-06-01 | BW | RGMA | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4354 | 2. Change sanction/approved and in project delivery |  | Request for New DNO Report Nested CSEPs Hierarchy Report | CP | LIVE | D1 - Change in delivery | 33.03% |  |  | Data Office | 2017-09-01 | Cadent Gas /Emma Smith | Jo Duncan | 50 |  | ME | XOS3577 | 2018-06-15 | No Date | 2018-02-23 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-10 | 2018-03-07 | 2018-03-07 | No Date
4608 | 1. Start-Up (Progressing through change governance) |  | SAP BW Accelerator: Data Gap Analysis | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 27.63% |  |  | Data Office | 2018-02-14 | Steve Concannon | Jo Duncan | 0 |  | Project Delivery |  | 2018-06-01 | No Date | 2018-03-26 | BW | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4613 | 1. Start-Up (Progressing through change governance) |  | Market Intelligence Service (MIS) | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 60.36% |  |  | Data Office | 2018-02-21 | Mark Pollard | Mark Pollard | 0 |  | Project Delivery |  | 2018-12-30 | No Date | 2018-03-29 | No Application | No Process | 100+ days | FALSE | [5 empty] | MOD/Ofgem | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | TRUE | No Date | No Date | No Date | No Date
4634 | 1. Start-Up (Progressing through change governance) |  | Data Catalogue | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 19.82% |  |  | Data Office | 2018-03-21 | Rachel Hinsley | Jo Duncan | 0 |  | Project Delivery |  | No Date | No Date | 2019-02-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4635 | 1. Start-Up (Progressing through change governance) |  | Creation of a Web Portal Service for MNO Helpline (Proof of Concept) - Link to XRN4626 | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 41.14% |  |  | Data Office | 2018-03-21 | Charlie Hayley | Charlie Hayley | 0 |  | Project Delivery |  | 2018-04-30 | No Date | 2018-04-30 | Other | Portal | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | TRUE | TRUE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | Two to Five | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4567 | 2. Change sanction/approved and in project delivery |  | Amendment to plot to postal report | CR (Internal) | LIVE | D1 - Change in delivery | 30.03% |  |  | Data Office | 2018-01-02 | Tahera Choudhury | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-25 | No Date | 2018-02-28 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4571 | 1. Start-Up (Progressing through change governance) |  | MAM and MAP asset data analysis and reporting | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 24.62% |  |  | Data Office | 2018-01-03 | Andy Miller Andy Miller | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-25 | No Date | 2018-03-23 | BW | Reads | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4570 | 1. Start-Up (Progressing through change governance) |  | BW Reports - RA/ RANTS Reporting Logic | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 28.83% |  |  | Data Office | 2017-01-03 | Michael Maguire | Jo Duncan | 50 |  | ME | XO3639 | No Date | No Date | 2018-01-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4582 | 1. Start-Up (Progressing through change governance) |  | Amendment Invoice Reporting Automation | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 63.96% |  |  | Data Office | 2018-01-16 | Dean Johnson | Donna Johnson | 50 |  | ME | XO3635 | No Date | No Date | 2018-03-31 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Weekly | Two to Five | High | 43190 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | Two to Five | High | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4590 | 2. Change sanction/approved and in project delivery |  | SLSP - Incorrect Seasonal Large Supply Point charging | CR (Internal) | LIVE | D1 - Change in delivery | 41.44% |  |  | Data Office | 2018-01-12 | Carole Elwell | Donna Johnson | 50 |  | ME | XO3644 | 2018-08-31 | No Date | 2018-08-31 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 43190 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | Service Area 23: Internal | Two to Five | Medium | FALSE | FALSE | FALSE | FALSE | TRUE | FALSE | No Date | No Date | No Date | No Date
4591 | 1. Start-Up (Progressing through change governance) |  | FOF environment for GDE Lookup tables in SAP BW | CR (Internal) | LIVE | A4 - ICAF - Capture Complete, Awaiting CIO PM Assignment | 31.53% |  |  | Data Office | 2018-01-23 | Julie Bretherton | Jo Duncan | 0 |  | Project Delivery |  | No Date | No Date | 2018-03-06 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4592 | 2. Change sanction/approved and in project delivery |  | BIRST work item inclusion & multiple daily updates | CR (Internal) | LIVE | D1 - Change in delivery | 35.74% |  |  | Data Office | 2018-01-23 | Jo Duncan | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-11 | No Date | 2018-05-11 | Birst | SPA | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 43189 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4594 | 1. Start-Up (Progressing through change governance) |  | Customer Inclusion for BIRST Exceptions | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 28.83% |  |  | Data Office | 2018-01-23 | Jo Duncan/Thomas Elce | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-11 | No Date | 2018-03-23 | Birst | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 43189 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4649 | 2. Change sanction/approved and in project delivery |  | ASR - SCP Weekly Portfolio Report (Phase 2) | CR (ASR) | LIVE | D1 - Change in delivery | 28.83% |  |  | Data Office | 2018-04-17 | Greg Causon | Jo Duncan | 0 | N/A | Project Delivery |  | 2018-05-25 | No Date | 2018-04-30 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4650 | 1. Start-Up (Progressing through change governance) |  | M-Number DVD Automation | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 37.24% |  |  | Data Office | 2018-04-17 | MarkPollard | Mark Pollard | 0 |  | Project Delivery |  | No Date | No Date | 2018-05-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | Service Area 23: Internal | One | Medium | FALSE | FALSE | TRUE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4636 | 1. Start-Up (Progressing through change governance) |  | ASR – AS20180277 ENGIE Enhanced Portfolio shipper pack (VOL) | CR (ASR) | LIVE | B3 - ASR/PAC HLE awaiting customer approval | 25.83% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-25 | No Date | 2018-05-25 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4637 | 2. Change sanction/approved and in project delivery |  | ASR – Corona Bypass AS20180273 | CR (ASR) | LIVE | D1 - Change in delivery | 25.83% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan | 0 |  | Project Delivery |  | 2018-05-25 | No Date | 2018-05-25 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4638 | 2. Change sanction/approved and in project delivery |  | ASR – NGS Asset AS20180274 | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan | 0 |  | Project Delivery |  | 2018-06-29 | No Date | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | One | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4657 | #N/A |  | UNC Modification 0636D - Updating the parameters for the NTS Optional Commodity Charge | CP | LIVE | A3 - ROM In Progress | 21.02% |  |  | Data Office | 2018-04-24 | Steve Pownall | Steve Ganney | 0 |  | Data Office |  | 2018-05-08 | No Date | 2018-04-08 | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
3667a | 1. Start-Up (Progressing through change governance) |  | Provision of Formula Year AQ/SOQ to Proposing Users | CP | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 45.05% |  |  | Data Office | 2018-04-04 | James Rigby | Emma Lyndon | 0 |  | Project Delivery |  | No Date | No Date | 2018-12-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | One | Medium | TRUE | TRUE | FALSE | FALSE | TRUE | FALSE | 2018-04-11 | No Date | No Date | No Date
4073 | 3. Change delivered, awaiting closure approval/sign-off |  | EU Phase 4A | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | Gemini | 2016-07-25 | Beverley Viney | Rachel Addison | 0 |  | Project Delivery |  | 2017-09-22 | 2017-09-22 | 2017-10-01 | Gemini | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4149 | 2. Change sanction/approved and in project delivery |  | NG Gateway Migration | CP | LIVE | D1 - Change in delivery | 40.54% |  |  | Gemini | 2016-11-28 | Beverley Viney | Rachel Addison | 0 |  | Project Delivery |  | 2018-06-30 | No Date | 2018-03-31 | Other | Other | 100+days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 19: Network Operator and User Relationship Management | One | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-07-19 | No Date | No Date | No Date
4368 | 3. Change delivered, awaiting closure approval/sign-off |  | EU Gas Capacity Conversion Interim Optimal Solution | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | Gemini | 2017-09-15 | Darren Lond/Beverley Viney | Rachel Addison | 0 |  | Project Delivery |  | 2018-02-18 | 2018-02-18 | 2018-01-01 | Gemini | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | No DSC Service Area | No Number of impacted DSC Service Areas | No Change Improvement Scale | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-10-10 | No Date | 2017-11-08 | No Date
4376 | 2. Change sanction/approved and in project delivery |  | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | CP | LIVE | D1 - Change in delivery | 28.83% |  |  | Gemini | 2017-09-22 | Chris Gumbley/Darren Lond | Nicola Patmore | 0 |  | Project Delivery |  | 2018-11-15 | No Date | 2019-01-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-10-12 | No Date | 2017-12-13 | No Date
4550 | 1. Start-Up (Progressing through change governance) |  | Gemini Re-platform | CP | LIVE | B4 - EQR In progress | 19.22% |  |  | Gemini | 2017-12-04 | Phil Hobbins | Hannah Reddy | 0 |  | Project Delivery |  | No Date | No Date | 2020-01-01 | Gemini | No Process | 60-100 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2017-12-13 | No Date | No Date | No Date
4632 | 1. Start-Up (Progressing through change governance) |  | Analysis for Gemini Enhancements | CP | LIVE | B5 - EQR awaiting ChMC approval | 34.53% |  |  | Gemini | 2018-03-19 | Celine Reddin/Beverley Viney | Hannah Reddy | 0 |  | Project Delivery |  | No Date | No Date | 2018-09-20 | Gemini | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | One | High | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 2018-04-11 | No Date | No Date | No Date
4216 | 2. Change sanction/approved and in project delivery |  | API Platform Implementation | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | Data Office | 2017-02-03 | Gareth Hepworth | Mark Pollard | 0 |  | Project Delivery |  | 2018-06-30 | No Date | 2017-12-10 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Medium | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4470 | 3. Change delivered, awaiting closure approval/sign-off |  | MI & KPI Dashboard for Business Operations | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 15.02% |  |  | Data Office | 2017-03-31 | Michele Downes | Jo Duncan | 0 | UKLP IADBI312v2 | Project Delivery |  | 2018-02-23 | 2018-02-23 | 2018-11-01 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | Service Area 23: Internal | None (Xoserve internal initiative) | Low | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date
4440 | 2. Change sanction/approved and in project delivery |  | Npower MPRN Information report | CR (ASR) | LIVE | D1 - Change in delivery | 31.83% |  |  | Data Office | 2016-08-04 | Emma Partlett | Jo Duncan | 0 | UKLP IADBI246 | Project Delivery |  | 2018-04-27 | No Date | 2018-04-27 | BW | Other | 31-100days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | One | Medium | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Date | No Date | No Date | No Date