## Slide 1: Ofgem Switching Programme: Central Switching Service consequential change update
9th May 2018

## Slide 2: Ofgem Switching Programme – Journey so far
As CDSP, Xoserve have been supporting the Ofgem Switching Programme (OSP) since it’s inception in October 2015
In March 2017 Xoserve responded to an Ofgem RFI estimating the cost of Consequential change as CDSP
In February 2018 an Ofgem Outline Business Case and E2E Design Baseline (that is logical and solution agnostic) marked the move from the OSP’s Blueprint to Enactment phase
Following the completion of the OSP’s E2E Design Baseline, Xoserve undertook initial analysis to understand impacts and variances to the assumptions made in March 2017
This presentation shares those high-level findings and describes next steps to further increase accuracy of requirements, solution, plan and cost impacts as the OSP progresses
MOD630R has been underway to consider additional, elective consequential changes, but with limited cross-industry input; there is a risk that this opportunity is not being maximised and your DSC support of this review group is requested (see appendix 2)

## Slide 3
UK Link
Disable switching functionality for sites in scope of CSS
Retention of switching functionality for sites out of scope of CSS
Include new data items & interfaces
Modification of existing interface files to shippers
Gemini
Modification of processes from D-2 to ~D-22 hrs and their impacts
Engagement with stakeholders on impacts to their processes and subsequent impact to Gemini
DES & BW
Real time replication of data into BW
Inclusion of new data items (REL, Switch Status)
Inclusion of new interfaces, screens & access controls
Definition of solution options to meet NFRs
MIS
Real time replication to MIS database from DES/UK Link
Inclusion of new data items (REL, Switch Status)
Inclusion of new APIs
CMS
Impacts expected due to changes to Dead to live processing
Data
Cleansing
Shipper-Supplier relationship
Address Data
Supplier ID association
Build of new data items
MAP ID, REL, Switch Status
Migration to CSS Provider
Impacts to Transformation & Validation to be assessed when solution known
NFRs
Infrastructure /architectural changes not expected
Realignment of batch processing timelines
Current requirements have perceived gaps
Operation
Business Change – Process changes, new exceptions
Transitional arrangements – Process Definition
Service Management – scope impacts
Networks
IX install required should electricity suppliers chose IX
IX installs required for CSS Provider
Complexity Levels:
High
Medium
Low
Processes
Maintain Gas Industry Stakeholders
Maintain Supply Point Meter Register
Predict, Allocate & Balance Daily Energy
Settle Meter Point Consumption
Invoice & Collect Charges
Level 1 Impact Assessment: Complexity of CSS Consequential
Industry Interaction
Responding to Consequential impacts for bidders
Meeting DCC MI / assurance / interaction needs

## Slide 4: Plan Analysis
 | Q1 18 | Q2 18 | Q3 18 | Q4 18 | Q1 19 | Q2 19 | Q3 19 | Q4 19 | Q1 20 | Q2 20 | Q3 20 | Q4 20 | Q1 21 | Q2 21
Ofgem Timeline |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CSS Consequential (CSSC) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Pre-Qual.
Tender Process
Contract
Contract
Award – Feb 19
Build & Test
Potential Go Live Range
Level 2 IA
Level 3 IA
Customer & Stakeholder Engagement
Solution Agnostic – Delivery (Design, Build & Test)
‘No regrets’ delivery plan
& costs understood
Solution Specific Design and Delivery
Risk: Agnostic Design doesn’t enable early start
Mitigation: Understand and commence ‘no regrets’ work
Data Cleanse
Risk: CSSC greater in scale than CSS, Xoserve might be on Critical Path
Mitigation: Commence CSSC Delivery ahead of Contract Award
Indicative Ofgem Timelines
Risk: Ambitious timelines and potentially not fully considering industry-wide plans
Mitigation: Continued engagement with Ofgem/DCC to promote realistic planning
Agnostic
Design
Baselined
Solution Specific
Design Baselined
Identify ‘Regrets / No Regrets’ Work
Pre-Delivery
Checkpoint
Pre-Level 3
Check Point
Level 1
Impact
Analysis
Key:
Indicative Timelines
Draft Timelines
Planned Timelines
CP2
CP1
Risk: Bidder behaviour results in increasing costs to CSSC
Mitigation: To be discussed
L1 IA
Industry Programme ‘Delays’?
Industry Programme ‘Delays’?
CP1
CP1: Return to DSC to provide cost update and discuss BP impacts. Potential funding decision required.
CP2
CP2: Level 3 analysis update and definition of ‘no regrets’ CSS Consequential delivery programme, and associated funding decisions

## Slide 5: Appendix 1 – Definition of Complexity
Red RAG (High Complexity) | Amber RAG rating (Medium Complexity) | Green RAG rating (Low Complexity)
External Interfaces exist (dependency on the CSS technology selected) Impacts to existing UK Link processes and batch processing timelines Changes are not wholly in Xoserve control and require extensive customer engagement Changes involved are complex especially where processes and code requires unpicking Perceived gaps in Non-Functional Requirements Requirements are changeable or there are known gaps | Changes involved are of medium complexity, impacting fewer objects and downstream processes Changes are within Xoserve control, requiring minimal customer engagement Relatively stable requirements | Changes are considered as simple Changes are within Xoserve control requiring no customer engagement required Requirements are stable and well defined requirements (no regret work)

## Slide 6: Modification Review Group 0630R update for DSC Change Management Committee
May 2018
Appendix 2

## Slide 7: Overview
Review group formed to:
Promote awareness of Ofgem Switching Programme (OSP) and its implications to UNC and iUNC parties
Allow UNC and iUNC parties to discuss implications and categorise
  Core
  Consequential
  Sustaining / elective

## Slide 8: Scope
Area | Description | Example
OSP Core | CSS cannot be built without these Xoserve Developments | Migration of data to CSS
OSP Consequential | CSS dictates essential changes to UK Link | Shipper appointment to a supply point is from CSS
OSP Elective | Changes the industry may choose to make | The way GT charges are provided for a CoS
Primary 630R scope:
Develop requirements and outline solution ideas for sustaining / elective scope

## Slide 9: Modification review group 630R
0630R is expected to conclude in July 2018
Low Shipper attendance is cause for concern, requirements may be missed or be raised too late for inclusion in the programme of works
For any sustaining / elective changes a UNC modification and / or DSC Change Proposal will be required
Mod 0630R business requirements document https://www.gasgovernance.co.uk/sites/default/files/ggf/book/2018-02/Business%20Requirements%20Document%20-%20OSP%20v0%203%20clean.pdf
Note: for the End to End design documents please refer to those published by Ofgem and the DCC