## Slide 1: XRN4361 – UK Link Release 2 - Delivery
05th June 2018 |  | Overall Project RAG Status |  |  | A
 |  | Plan/Time | Risks and Issues | Cost | Resources
RAG Status |  | A | A | G | G
Status Explanation |  |  |  |  | 
Objective | Full project delivery of UK Link Future Release 2 Scope |  |  |  | 
Plan/Time | Acceptance & Performance Testing Both User Acceptance and Performance testing phases have been successfully completed XRN4449 Customer Testing Testing phase completed on the 01st June. Awaiting confirmation from a 3 Customers for approval of testing plans Regression Testing Testing commenced as per plan on 21st May and plan is currently tracking slightly behind but no impact to planned end date 5 out of 13 CRs have been completed R2 Customer Training Customer training material has been uploaded to Xoserve.com and can be accessed via this link Cutover/Implementation Planning Implementation strategy/approach in approval process Go No Go criteria and customer communication strategy to be presented to Customers Imp contacts W/C 11th June Implementation Dress Rehearsal, lower lever cutover & implementation plans drafted and walkthroughs to review and approve in progress |  |  |  | 
Risks & Issues | Risk that RT is not completed to plan which could therefore have a downstream impact to the iDR planned start date |  |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases, etc) and all requirements are able to be met |  |  |  | 

## Slide 2: UK Link Release 2 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build | Acceptance Test | Performance Test | Regression Test | Imp. |  | PIS
Baseline Plan | 07/06/17 | 25/07/17 | 09/08/17 | Aug 17 | Aug 17 | 20/11/17 | 29/01/18 | 18/05/18 | 18/05/18 | 22/06/18 | 29/06/18 |  | 30/07/18
Current Plan | 07/06/17 | 11/10/17 | 10/01/18 | 13/12/17 | 16/01/18 | 29/01/18 (12/01/18) | 16/02/18 | 18/05/18 | 18/05/18 23/05/18 | 22/06/18 | 29/06/18 |  | 08/08/18
Secondary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build | Acceptance Test | Performance Test | Regression Test | Imp. |  | PIS
Baseline Plan | 07/06/17 | 25/07/17 | 07/02/18 | NA | NA | 09/02/18 | 09/03/18 | 18/05/18 | 18/05/18 | 22/06/18 | 29/06/18 |  | 30/07/18
Current Plan | 07/06/17 | 27/11/17 | 07/02/18 | NA | NA | 16/02/18 09/03/18 | 09/03/18 30/03/18 06/04/18 | 18/05/18 | 18/05/18 23/05/18 | 22/06/18 | 29/06/18 |  | 08/08/18
RAG Key – Milestones are end dates:
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed