## Slide 1: DSC Change Committee Summary – 13th June
12 new change proposals raised and approved
  5 - sent for Review
    XRN4690 – Actual read following Estimated Transfer Read Calculating AQ 1
    XRN4691 to XRN4694 CSEPS IGT & GT File Formats (4 CP’s amendments to various GT/IGT file flows)
  2 approved to be passed to DSG for solution options
    XRN4686 Smart Metering Reporting
    XRN4687 PSR updates for Large Domestic Sites
  XRN4667 – changes to service lines for information to be passed to CoMC to approve (AOB item)
  XRN4635 – Provision of a Consumer Enquiry Service Web Portal (Mnumber) – approved
  XRN4525 – Read Validation, increasing the outer tolerance value for specific AQ bands for Class 3 & 4 Meter Points – approved to progress to delivery
  XRN4665 – Creation of new EUC’s – approved to progress to delivery (implementation date to be agreed)
  XRN4695 – Investigating Causes and Contributors to Levels and Volatility of Unidentified Gas – Approved
EQR approval
  XRN4695 – Investigating Causes and Contributors to Levels and Volatility of Unidentified – EQR Approved
CCR approvals
  XRN4568 – DSC Service description table cosmetic changes to Service Line

## Slide 2: DSC Change Committee Summary – 13th June
Release Updates:
  Release 2
    On track for delivery
  Release 3
    Currently tracking to plan but current overall RAG status is AMBER
      Track 1 (13 Changes) – Detailed Design Complete. Build commenced, on track to complete as per plan
      Track 2 (XRN4454 – Cadent/NGT Separation) – Reporting and File Format confirmation for both Cadent and NG finalised 4/6/18. Extensions were given to allow for full review. Potential risk that the agreement carries some level of assumed requirements. A full assessment of the requirements and design, build components being completed but build plan is now impacted by extended delay.
  Release June 19
    Initial changes for inclusion and high level timeline
CSS high level update (now a standard agenda item in ChMC)

## Slide 3: DSC Change Committee Summary – 9th May
AOB items
Change Assurance presentation
  https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-06/8.2%20Change%20Assurance%20update.pptx
MOD621 Update
  https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-06/8.3%20Modification%200621%20GB%20Charging%20Project%20update.pptx
RAASP
  https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-06/8.5%20RAASP%20Update.pptx