## Indicative PRIDe Project Plan
All dates are indicative
| Start | Finish | 2018 | [6 empty] | 2019 | [11 empty] | 2020
Indicative PRIDe Project Plan | Tue 12/06/18 | Mon 03/02/20 | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Steering and Control
Present Project plan | Tue 12/06/18 | Tue 12/06/18
PAC to agree PRIDe Project Plan | Tue 12/06/18 | Tue 12/06/18
PAC to agree how industry will be kept up to date on implementation progress | Tue 12/06/18 | Tue 12/06/18
Engagement, Education and Evolution
Define "Engagement, Education and Evolution" approach | Tue 10/07/18 | Wed 11/07/18
PAC workshop to assess how to improve industry performance through "Engagement, Education and Evolution" | Tue 10/07/18 | Tue 10/07/18
PAC to agree on approach to take forward | Tue 10/07/18 | Tue 10/07/18
PAC workshop to draft wording for potential modifications | Tue 10/07/18 | Tue 10/07/18
PAC to agree on modification sponsor | Tue 10/07/18 | Tue 10/07/18
UNC Modification process | Mon 13/08/18 | Mon 01/04/19
Implementation date | Mon 01/04/19 | Mon 01/04/19
Prevent
PAC to define "Prevent" approach and purpose | Tue 11/09/18 | Tue 11/09/18
PAC workshop to assess where there are opportunities to improve performance through prevention | Tue 11/09/18 | Tue 11/09/18
PAC to agree on "Prevent" approach to take | Tue 11/09/18 | Tue 11/09/18
PAC workshop to draft wording for potential modifications | Tue 11/09/18 | Wed 12/09/18
PAC to agree on modification sponsor | Tue 11/09/18 | Wed 12/09/18
Modification raised | Tue 11/09/18 | Tue 11/09/18
UNC Modification process | Mon 17/09/18 | Wed 01/05/19
Implementation date | Wed 01/05/19 | Wed 01/05/19
Commence Prevent mechanism on a prioritisation basis | Wed 01/05/19 | Wed 01/05/19
Detect
PAC to define "Detect" approach and purpose | Tue 07/05/19 | Tue 07/05/19
PAC workshop to assess where there are opportunities to improve performance through detection | Tue 07/05/19 | Tue 07/05/19
PAC to agree on "Detect" approach to take | Tue 07/05/19 | Tue 07/05/19
PAC workshop to draft wording for potential modifications | Tue 07/05/19 | Wed 08/05/19
PAC to agree on modification sponsor | Tue 07/05/19 | Wed 08/05/19
Modification raised | Tue 07/05/19 | Tue 07/05/19
UNC Modification process | Thu 20/06/19 | Mon 03/02/20
Implementation date | Mon 03/02/20 | Mon 03/02/20
Commence Detect mechanism on a prioritisation basis | Mon 03/02/20 | Mon 03/02/20
Incentive
PAC to define "Incentive" approach and purpose | Tue 11/09/18 | Wed 12/09/18
PAC workshop to assess where there are opportunities to improve performance through incentives | Tue 11/09/18 | Tue 11/09/18
PAC to agree on appeals process | Tue 11/09/18 | Wed 12/09/18
PAC to agree on "Incentive" approach to take | Tue 11/09/18 | Tue 11/09/18
PAC workshop to draft wording for potential modifications | Tue 11/09/18 | Wed 12/09/18
PAC to agree on modification sponsor | Tue 11/09/18 | Wed 12/09/18
Modification raised | Tue 11/09/18 | Tue 11/09/18
UNC Modification process | Mon 17/09/18 | Wed 01/05/19
Implementation date | Wed 01/05/19 | Wed 01/05/19
Commence Incentive mechanism on a prioritisation basis | Wed 01/05/19 | Wed 01/05/19
Remedy
PAC to define "Remedy" approach and purpose | Tue 07/05/19 | Tue 07/05/19
PAC workshop to assess where there are opportunities to improve performance through remedy | Tue 07/05/19 | Tue 07/05/19
PAC to agree on appeals process | Tue 07/05/19 | Tue 07/05/19
PAC to agree on "Remedy" approach to take | Tue 07/05/19 | Tue 07/05/19
PAC workshop to draft wording for potential modifications | Tue 07/05/19 | Tue 07/05/19
UNC Modification process | Thu 20/06/19 | Mon 03/02/20
Implementation date | Mon 03/02/20 | Mon 03/02/20
Commence Remedy mechanism on a prioritisation basis | Mon 03/02/20 | Mon 03/02/20