## Slide 1: XRN 4695 Supporting Document High Level Plan
ChMC 11th July 2018

## Slide 2: Planning Assumptions
Regular Update meetings will be scheduled 1 week prior to Change Management Committee (ChMC)
Ad hoc updates will be provided as appropriate
External data science provider is appointed by end of July 2018
Change Managers support obtained for full proposed spend
Xoserve will not continue to progress the plan, or areas of the plan, if it is found that there is no material benefit to be gained
Project scope excludes development of any new UNC Modifications or Change Proposals
Budget and spend updates will be provided to ChMC & Contract Management Committee (CoMC)
Industry input will be available to support analysis & resolution of issues where required

## Slide 3: Risks and Mitigations
Risk | Mitigation
Individual activities may not have a significant impact on understanding and mitigating UIG | Ongoing analysis of the impact of individual issues on UIG is part of the programme, and will be used to prioritise activities. The 3rd party advanced analytics is split into two phases which will enable us to stop if phase one is not successful in identifying benefit.
Rolling off resource early will be subject to contract T&Cs, reducing cost savings | We are looking at the resource mix to provide a more flexible cost model. We will not however compromise on quality of expertise to achieve this.
Limited availability of SME resources if high priority operational issues arise | Backfill and knowledge transitions to be put in place to help reduce SME dependency
Recruitment of new roles/backfill may be slower than estimated | Recruitment activities already underway with key roles prioritised
All timelines assume BER approval in July | Recruitment and 3rd party mobilisation activities can continue at risk
Significant additional work may be identified in order to drive to target UIG levels and volatility | Any additional opportunities will be brought to ChMC for discussion, prioritised against other ongoing work, and taken through the Mod process if required.

## Slide 4: UIG Taskforce High level work streams
 | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  | 
W/C | 02/07 | 09/07 | 16/07 | 23/07 | 30/07 | 06/08 | 13/08 | 20/08 | 27/08 | 03/09 | 10/09 | 17/09 | 24/09 | 01/10 | 08/10 | 15/10 | 22/10 | 29/10 | 05/11 | 12/11 | 19/11 | 26/11 | 03/12 | 10/12 | 17/12 | 24/12 | 31/12 | 07/01 | 14/01 | 21.01 | 28/01 | 04/02 | 11/02 | 18/02 | 25/02
Industry Updates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Advanced Analytics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Issue Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
UIG Process and Rule Changes (Governance) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Team Mobilisation
BER Signoff
Issue Impact Quantification
XRN4665 / UNC Modification 0644
Dec Mod 658 Target
Progress issues as per Impact and Analysis Output
Issue Analysis
UNC Modification 0652 Workgroup
UNC Modification 0654 Workgroup
Notification of any of new / high value issues to industry via appropriate operational / contractual forum
Change Management Committee
Advanced Analytics Stages
Data Preparation and Mobilisation
Sprint 1
Sprint 2
Sprint 3
Analytics
Recommendations

## Slide 5: UIG – Advanced Analytics
Xoserve will be working with Analytic Consultants creating a small joint team of focused data analysis and algorithm development experts. Initial approaches focused on factor analysis and clustering approaches.
Sprint 2: Algorithm Development
Algorithm development to predict UIG volatility.
Identification of missing data sets.
30 Jul
13 Aug
27 Aug
3 Sep
10 Sep
17 Sep
24 Sep
1 Oct
8 Oct
16 Jul
Mobilisation
Recruitment of back fill resources to enabling the leverage of Xoserve SMEs, project resources and Data Scientists.
Creating data transfer mechanisms and implementation of technology to support analytics process.
Engagement workshops between Xoserve and Analytic Consultants to agree direction of analysis
Sprint 1
Sprint 2
Internal AA Steering Group
15th Aug: Mobilisation Progress Update.
29th Aug: Analytics Direction Overview.
19th Sep: Sprint 1 Overview / Outputs
3rd Oct: Sprint 2 Overview / Outputs
17th Oct: Final Analytics Recommendations
*Dates subject to change based on funding approval and mobilisation timescales currently estimated at 6 weeks
Sprint 1: Variable Impacts
Identification of factors that impact UIG and their relationship to each other i.e. gas usage, weather, system price, day of week etc.
Identification of socioeconomic, demographic or other data items that show a strong relationship with UID levels
Sprint 3: Algorithm Performance
Test algorithm performance against historical data sets
Determine prediction capabilities.
Sprint 3
15 Oct

## Slide 6: Issue Analysis Stream High level Activity Plan
July | August | September | October | November | December | January | February
DM energy analysis & investigations
Continue to work on DM energy issues, liaison with relevant parties to resolve data issues
Support industry to conclude all DM read & asset issues
Identify options for improving Class 2 read performance
Theft of Gas
Support AUGE analysis & initiatives
Investigate reporting processes
Benchmark reported theft against other industries / data sources
AQ
Review & investigate all known issues & quantify UIG impacts
Assess carried forward AQs & investigate root causes / estimate impacts
UIG Sharing
Assure correct operation of existing NDM allocation & UIG sharing processes
WAR Bands & EUCs
Build on work undertaken by PAC
Attempt to quantify impact of more appropriate WAR Bands on UIG
Monitor take up of WAR Bands & provide RCA
Provide regular reporting
Unregistered / Shipperless
Review previous assessments
Estimate impacts on UIG
Investigate patterns & trends
Interface Files / Batch Processes
Review processes timings
Consider impacts on UIG
LDZ Measurement Errors
Review processes with Networks, including inter LDZ Meters
Assess impacts of incorrect measurements
Estimates
Assess accuracy of DM & NDM estimates & make recommendations for improvement if appropriate
NDM Nomination Accuracy
Review movement of UIG Nominations against Allocations & identify causes of volatility
Make recommendations for process / data improvements
UNC Obligations
Building on work of PAC
Benchmark Shipper performance against key areas which can influence UIG
Development of Customer Dashboards for use in operational meetings
CSEP – LDZ Mapping
- Investigate any incorrect mapping & associated energy volume
Note – prioritisation and sequencing will be subject to change based on increased understanding of the impact of activities and any insight gained from the Advanced Analytics work stream
Known issues – not yet quantified
Possible issues – not yet quantified
Process review

## Slide 7: UIG Process & Rule Changes Stream
Currently 3 UNC Modifications are in flight within the UIG workgroup that Xoserve are supporting:
  Mod 0644 / XRN4665 (additional EUCs) will be voted upon at ChMC in July to proceed to delivery.
  Mod 0652 (submission of reads for winter consumption calculations) is due back to panel on the 16th August. Report development is required.
  Mod 0654 (mandatory provision of NDM sample data by Shippers) is due back to panel on the 16th August. Report development is required.
Further Modifications / changes will be added to the POAP once raised / identified – out of scope of current BER

## Slide 8: Cost Breakdown by work stream
The intent is to share SME expertise, communication and project management resources across the work streams, with costs allocated proportionally to the three streams of work.
Based on current allocations, the following is the approximate breakdown of costs by work stream:
  Advanced Analytics: £750k
  Issue Analysis: £270k
  UIG Process and Rule Changes: £80k