## Slide 1: XRN4361 – UK Link Release 2 - Delivery
03rd July 2018 |  | Overall Project RAG Status |  |  | G
 |  | Plan/Time | Risks and Issues | Cost | Resources
RAG Status |  | G | G | G | G
Status Explanation |  |  |  |  | 
Objective | Full project delivery of UK Link Future Release 2 Scope |  |  |  | 
Plan/Time | Regression Testing Successfully completed for all 13 CRs in scope Cutover/Implementation Planning Implementation Dress Rehearsal was successfully completed on 21st June Go No Go (GONG) approved internally 7 by Customers on 28th June for R2 to proceed into implementation Implementation successfully completed (30th June and 01st July) Post Implementation Support PIS commenced on 01st July 18 and plans/resources to monitor processes impacted by R2 changes deployed is in place A number of tickets have been raised that are being worked through to analyse any issues and to fix if required XRN4249 – Address Management – Part B – Data Migrations Following R2 implementation, confirmation of data load plan with checkpoints/comms plan to be reviewed and agreed with DSG on 16th July |  |  |  | 
Risks & Issues | There is a risk that PIS exit is not achieved by the planned milestone date |  |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases, etc) and all requirements are able to be met |  |  |  | 

## Slide 2: UK Link Release 2 - Plan
Primary Scope | Scoping |  |  | Initiation |  | Delivery |  |  |  |  |  | Realisation | 
Stage | Scope Prioritisation | Scope Defined | Funding | Initiation | Analysis and HLD | Detailed Design | Build | Acceptance Test | Performance Test | Regression Test | Imp. |  | PIS
Baseline Plan | 07/06/17 | 25/07/17 | 09/08/17 | Aug 17 | Aug 17 | 20/11/17 | 29/01/18 | 18/05/18 | 18/05/18 | 22/06/18 | 29/06/18 |  | 30/07/18
Current Plan | 07/06/17 | 11/10/17 | 10/01/18 | 13/12/17 | 16/01/18 | 29/01/18 (12/01/18) | 16/02/18 | 18/05/18 | 18/05/18 23/05/18 | 22/06/18 | 29/06/18 |  | 08/08/18
RAG Key – Milestones are end dates:
Milestone date forecast to be missed
Milestone date forecast to be at risk
Milestone date forecast to be met
Milestone completed
Planning/Milestone date to be confirmed