## Slide 1: DSC Change Committee Summary – 11th July
3 new change proposals raised and approved
  XRN4679 – Requiring a Meter Reading following a change of local distribution zone or exit zone – Approved
  XRN4676 – Reconciliation issues with reads recorded between D-1 to D-5 – approved (Xoserve raised change)
  XRN4670 – Management of a replacement read, where the read provided is identical to that already held in the UK Link for the same read date (Xoserve raised change)
Solution/Delivery option approval
  XRN4690 – Actual Read following estimated transfer read calculating AQ of 1
    Solution approved to roll over AQ when a negative volume is recorded as a transitional arrangement
    Also requested solution option for re-estimation of the transfer reading to be fully assessed as enduring solution
  XRN4665 – Creation of new End user Categories
    Approved solution option 2 – New EUC’s with same UIG share factor
    Approved change to be delivered for start of new gas year in 2019
BER approval
  XRN4695 – Investigating Causes and Contributors to Levels and Volatility of Unidentified – BER Approved

## Slide 2: DSC Change Committee Summary – 11th July
Release Updates:
  Release 2
    Delivery completed successfully now in Post Implementation Support period.
  Release 3
    No longer on plan therefore overall RAG status is RED
      Proposed that the delivery is split into 2 tracks with the 13 changes progressing under track 1. These changes are tracking to plan and would be considered GREEN
      Cadant Billing change will be delivered on a separate track and will not be delivered for release 3 implementation date. Proposed to deliver on either 1st Feb 2019 or 1st March 2019 (aligned to next major release)
  Extraordinary Change Committee will be held 23rd July to approve the preferred delivery date for Cadent billing change.

## Slide 3: DSC Change Committee Summary – 11th July
Release Updates Continued:
  Release June 19
    Tabled changes for consideration for June 2019 release
    Scope required to be approved in August 2019 DSC Change Committee meeting
Future release needs:
    Some options were presented on future releases expected a release is required in September 2019 to deliver the MOD0621 UK Link consequential change.
    Options presented to:
      Have an additional release in September 2019
      Combine June 2019 with September and release in September 2019
      Bring forward November 2019 release and combine with September 2019 and deliver in September 2019
CSS high level update

## Slide 4: DSC Change Committee Summary – 11th July
AOB items
  2018-2019 UNC user Representatives process
    https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-07/11.1%20User%20Representatives.pptx
  IX update
    https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-07/11.2%20IX%20Update.pptx
  DSC Governance process (approved)
    https://www.gasgovernance.co.uk/sites/default/files/ggf/2018-07/11.4%20ChMC%20Governance%20%20group%20recommendations.pptx