## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed platform | Customer change lead | Comments
N/A | N/A | N/A | All DNs | Smart DCC Demand Data | TBC | Reporting | NA | UK Link and SAP BW | New data items to be created between SAP ISU and SAP BW. Brand new reports required. | TBC | Data | Paul Orsler | Reporting requirement in the future following the roll-out of smart in order to use smart information rather than demand data. No change since last meeting.
Mod 0621 A-L (no I, G as withdrawn) | Final modification report | UNC - NTSCMF | Various | Amendments to Gas Transmission Charging Regime | Modification - May 2019 System - October 2019 | Rule and System Change | No | UK Link & Gemini | Currently undertaking impact analysis | June 2019 Release | Transmission and Shared Services | Steve Pownall | Proposal to amend the Gas Transmission Charging regime in order to better meet the relevant charging objectives and customer/stakeholder provided objectives for Gas Transmission Transportation charges to deliver compliance with relevant EU codes. Anticipated impacts on Gemini and UK Link invoicing systems. Currently 10 alternates to Modification 0621 have been raised and will follow the same route as 0621. The Final Modification Report is drafted. There are various consultation responses and no clear preference.
Mod 0619 / A / B | Awaiting Authority Decision | UNC - DWG | Gazprom Energy / SGN / Centrica | Application of proportionate ratchet to daily read sites (0619 & 0619B) Protection from ratchet charges for daily read customer with an AQ of 73,200kWh and below (0619A) | 2018-10-01 | Rule and System Change | Yes | UK Link | Impacts to invoicing. B has additional reporting | June 2019 Release | R&N | Rachel Hinsley | Change to UK Link to implement a new solution. Modification proposes to remove ratchet charges on Class 1 and 2 Supply Points. An amended ROM response has been provided. Issued for Consultation which closed out on 01 March 2018. Panel recommended that Mod 0619 should not be implemented. Awaiting an Ofgem decision.
Mod 0642 (Urgent) / 0642A (Urgent) | Awaiting Authority Decision | UIG Workgroup | Corona Energy / EON | (Urgent) - Changes to settlement regime to address Unidentified Gas issues | April 2018 / Oct 2018 | System Change | No | UK Link and Gemini | Significant impacts to both systems. Impacts to allocation and invoicing. Estimated delivery time - 46 weeks for 0642, 35 weeks for 0642A | June 2019 Release | R&N | Linda Whitcroft | This Modification implements the proposal set out by the DNV GL on 31 October 2017 to utilise a top-up down allocation and nomination approach for NDM allocation, with resulting volatility reconciled to unread meters. Ofgem confirmed urgent status for this Modification. Panel did not recommend implementation. Final Workgroup Report has been submitted to Ofgem for a decision. Ofgem gave a minded to position and issued a paper for consultation with the industry. Closed 5th July.
Mod 0642A | With Workgroup | UNC | EON Energy | (Urgent) - Changes to settlement regime to address Unidentified Gas issues |  | System Change | [6 empty] | This Modification seeks to introduce a fixed unidentified gas (UIG) value per category across all Shippers and also to introduce a Balancing Quantity to act as an equal/opposite leveller. This is an alternate to 0624. Ofgem agreed the Modification should follow the same timescales as 0642 (Urgent).
Mod 0643 (Urgent) | Awaiting Authority Decision | UIG Workgroup | Orsted | (Urgent) - Changes to settlement regime to address Unidentified Gas issues including retrospective correction | Retrospective Jun-2017 | System Change | No | UK Link and Gemini | Significant impacts to both systems. Impacts to allocation and invoicing. Estimated delivery time - 50 weeks | June 2019 Release | R&N | Linda Whitcroft | This purpose of this modification mirrors 0642 however looks to backdate the proposal to 01 June 2017. Panel did not recommend implementation. Final Workgroup Report has been submitted to Ofgem for a decision. Ofgem gave a minded to position and issued a paper for consultation with the industry. Closed 5th July.
Mod 0630R | With Workgroup | UNC | Cadent Gas | Review of the consequential changes required in UNC as a result of the Ofgem Switching Programme | Any Modifications as a result of 0630R will be impact assessed and system implications considered. Should a Modification be raised, there are potential impacts to both UK Link and Gemini. | [5 empty] | CSS | Rachel Hinsley | The Change of Supplier required information was discussed. The lists of data items included and excluded from the switch were mentioned with particular focus on the billable attributes excluded from the file flows. A number of options were proposed, the preferred option was a 'Shell record' - UNC flows outside of CSS containing the relevant details. Where not provided, the default values will be used. Next meeting cancelled. BRD to be updated and concluded and report to be completed.
Mod 0632S | Issued for Consultation | UNC - DWG | Corona Energy | Shipper asset details reconciliation |  | Reporting | NA | No system impact | NA | NA |  |  | Modification seeks to place obligation in the UNC for Shippers to record whether a Smart Meter or AMR device exists at their site and for Xoserve to report within 3 months of implementation the number of Smart Meters and AMR Devices installed on sites by each EUC band. Issued for Consultation with a close out of 08 March 2018.
Mod 0636 / A-D | Awaiting Authority Decision | UNC - Transmission | Various | Updating the parameters for the NTS Optional Commodity Charge | 2018-10-01 | System Change | Y | No system impact for 0636 / A / B System impacts for 0636 C & D | For C & D UK Link and Gemini | TBC | Transmission and Shared Services | Steve Pownall | Amending the existing parameters used in the derivation of the Optional Commodity Charge tariff. Ofgem have requested additional evidence from the industry. Deadline 13th July via Huddle.
Mod 0639R | Closed Proposed removal from bubbling under | UNC | Gazprom Energy | Review of AUGE Framework and Arrangements | Any Modifications as a result of 0639R will be impact assessed and system implications considered. Should a Modification be raised, there are unlikely to be system impacts. | [5 empty] | NA | Fiona Cottam | The AUGE framework and arrangements have been in place for some time and cover pre and post Nexus. The purpose of the review will be to determine if any changes to its arrangements are appropriate. The Workgroup has concluded and closed. Propose to remove from bubbling under.
Regulatory Reference | Status | Governance | Proposer / Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0644 | With Workgroup | UNC - DESC | EON Energy | Improvements to nomination and reconciliation through the introduction of new EUC bands and improvements for the ALP and DAF | 2018-10-01 | System Change | TBC | UK Link and SAP BW (potentially Gemini) | Currently undertaking impact analysis assessing whether there are changes to both UK Link and Gemini. New data items to be taken into consideration for reporting purposes | June 2019 Release | R&N | Simon Harris | This Modification seeks to split the End User Categories (EUC) EUC01B and EUC02B into three and grouping by prepayment, market sector code of industrial and commercial and finally all remaining meter point reference numbers. It also seeks to amend the Daily Adjustment Factors (DAF) where they reach defined tolerances. These amendments would provide a more accurate profile to that which is in place today and would work towards improved nominations which in turn would reduce reconciliation and UIG. Progressing through XRN4665.
Mod 0647 | With Workgroup | UNC - DWG | WWU | Opening Class 1 reads to Competition | 2019-10-01 | Rule Change | TBC | Potential impacts to UK Link and Gemini depending on agreed changes. | Impacts to file flows and validations for Shippers to be able to send in reads for Class 1. Dependent on the options, the allocation timings in Gemini may be impacted. | June 2019 Release | R&N | Rachel Hinsley | Proposes to Open Class 1 reads to competition by introducing common arrangements for Class 1 and 2 by removing the DNO obligation to provide a Daily Read service to Shippers for non-telemetered Class 1 Supply Meter Points. Continue at Workgroup and due to conclude in October 2018. Request from Workgroup that implementation is outside of a winter release however the modification is unlikely to be concluded in time for this to be within the June 2019 scope.
Mod 0649S | With Workgroup | UNC - DWG | Gazprom Energy | Update to UNC to formalise the Data Enquiry Service Permissions Matrix | 2018-05-01 | Rule Change | NA | No system impact. Permissions Modification only | NA | NA | NA | Rachel Hinsley | This modification seeks to formalise the Data Enquiry Service (DES) Permissions Matrix within the Uniform Network Code (UNC) and set out the process for amending the data access permissions in the future. There are no system impacts, it simply formalises the matrix. Progressing and expanding to include API permissions.
Mod 0651 | With Workgroup | UNC - DWG | Cadent | Replacement of the Retrospective Data Update provisions | From Summer 2019 to end 2020 | Rule & System change | NA | System impacts expected - details TBC | Currently undertaking impact analysis to understand the system(s) impact | June 2019 Release | R&N | Paul Orsler | This UNC Modification is seeking to amend those changes to the UNC identified within UNC Modification 0434 Project Nexus – Retrospective Adjustment specifically relating to Retrospective Data Updates, to incorporate the requirements of Option 4 as identified within the Request 0624R Review of arrangements for Retrospective Adjustment of Meter Information, Meter Point/Supply Point and Address Data Workgroup
Mod 0652 | With Workgroup | UNC | Npower | Obligation to submit reads and data for winter consumption calculation (meters in EUC bands 3 – 8) | 2018-09-01 | Rule change | NA | SAP BW impacted | Currently undertaking impact analysis to understand the system(s) impact | NA | NA | Rachel Hinsley | This modification aims to create an obligation, and associated monitoring reports, for Shippers to submit reads and correct data to ensure the appropriate winter consumption calculation takes place, for accurate NDM WAR band profiling. Modification to be developed alongside Modification 0644. Likely to introduce reporting impacts.
Mod 0653 | With Workgroup | UNC - Transmission | Centrica | Updating the parameters for the NTS Optional Commodity Charge – Introducing the NTS Optional Capacity Charge | 2019-10-01 | Rule & System change | TBC | Likely System impacts | TBC | June 2019 Release | Transmission and Shared Services | Steve Pownall | To replace NTS Optional Commodity Charges with NTS Optional Capacity Charges that will provide an enduring solution at all system entry and exit points, being mindful of changes ensuing from the European Tariff Network Code. Last Workgroup meeting was deferred due to insufficient time to discuss the proposal. Next Workgroup will be included as part of Transmission on 03 May 2018
Mod 0654 | Issued to Workgroup | UNC | EON Energy | Mandating the provision of NDM sample data | 2018-09-01 | Rule change | NA | No System impacts | NA | NA | NA | Fiona Cottam | This modification is seeking to introduce an obligation into the UNC for the provision of regular NDM sample data to the Central Data Services Provider (CDSP). Panel agreed for Mod 0654 to be issued to Workgroup and a report presented no later than 17 July 2018 Panel.
Mod 0655S | With Workgroup | UNC - DWG | Gazprom Energy | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | 2018-08-01 | Rule change | NA | Minimal System impacts | Insertion of a read by the CDSP, flows of the reads to impacted parties | TBC | R&N | Dave Addison | This Modification would require the CDSP to provide a Meter Reading in the event that the Local Distribution Zone or Exit Zone was amended for a Supply Meter Point. Change Proposal to be raised with the CDSP to propose this as a DSC Service Line. Update to be provided at next DWG. CP to be discussed at ChMC and subsequently the mod will be withdrawn.
Mod 0657S | With Workgroup | UNC - DWG | Npower | Adding AQ reporting to the PARR Schedule reporting suite | 2018-11-01 | Reporting | NA | No System impacts | Report already developed - no system impacts | NA | Data | Rachel Hinsley | This Modification adds AQ reporting to the Performance Assurance suite of reports (PARR Schedules) that were initially introduced through Modification 0520A. Proposer believes there are limited impacts on Central Systems as reports are being developed under XRN4525. This Modification removes anonymization.
Regulatory Reference | Status | Governance | Proposer / Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0658 (Urgent) | Awaiting Authority Decision | UNC | Total | CDSP to identify and develop improvements to LDZ settlement processes | 2018-07-01 | TBC | NA | No System impacts | TBC - Outcomes may result in further modifications and system impacts | NA | New UIG task force | Fiona Cottam | This modification proposes to authorise the CDSP to assign resources and incur costs related to a task force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties. Progressing through the DSC with XRN4658.
Mod 0659S | With Workgroup | UNC | EON | Improvements to the Composite Weather Variable | 2019-10-01 | Rule & System change | NA | System impacts | Potential impacts to UK Link and Gemini | NA | TBC | Rachel Hinsley | This Modification seeks to amend the Composite Weather Variable (CWV) to include additional parameters to complement wind speeds and temperature, leading to improvements in the Weather Correction Factor (WCF).
Mod 0660S | With Workgroup | UNC | Centrica | Amendment to PARR permissions to allow PAC to update with UNCC approval | 2018-10-01 | Rule change | NA | No System impacts | NA | NA | TBC | Rachel Hinsley | To allow the Performance Assurance Committee (PAC) to request updates to the Performance Assurance Reports Register (PARR) without recourse to the full UNC modification process, but instead be able to submit requests for new and amended reports to the UNCC for approval.
Mod 0661R | Request for workgroup | UNC | Winchester | Reconciliation and Imbalance Cash Out Prices | Any Modifications as a result of 0661R will be impact assessed and system implications considered. Should a Modification be raised, there are unlikely to be system impacts. | [5 empty] | TBC | Rachel Hinsley | This Requests aims to seek a method of incentivising Shippers to purchase the correct amount of gas for NDM sites, in advance of the gas day and support de-risking Shipper imbalance costs.
Mod 0662 | With Workgroup | UNC | NTS | Revenue Recovery at Combined ASEPs | 2019-10-01 | Rule & System change | NA | System impacts | Potential impacts to UK Link and Gemini | NA | TBC | Steve Pownall | The purpose of this modification is to allow entry capacity booked for the entry of gas into the NTS from storage sites within combined Aggregated System Entry Points (ASEPs), to be treated the same as a “Storage Site” as designated in National Grid’s Licence with respect to the application of any revenue recovery charge based on capacity bookings.