## Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 2206.68 | 2379.2291 | 1874.3342 | 508.504 | 645.7547 | 720.0755 | 0 | G | G | 199.5843 | 135.899 | 63.9525 | 0 | 246.3189
| Internal |  |  | 396.886 | 119.055 | 111.777 | 166.054 | 0 | NA | NA | 63.2479 | 10.2 | 4.8 | 0 | 33.5291
| Total |  |  | 2271.2202 | 627.559 | 757.5317 | 886.1295 | 0 | NA | NA | 262.8322 | 146.099 | 68.7525 | 0 | 279.848
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | 0 | -3.2 | 0 | 140 | -143.2 | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## Detail
Values in £0,000s | [5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's) | [8 empty] | Comparison Formulae |  | 6 | 8 | 9 | 11 | 12 | 13 | 14 | 25
Budget Pot Reference | Project Ref No | Project Title | Senior Project Manager | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments | SORT FIELD 1 | SORT FIELD 2 | Matcher | Project Line | High Level Process Stage | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Value of Work Done (Current Year) | Change in Value of Work Remaininng (Current Year) | Change in Value of Work Remaining (Future Financial Years) | CCN Status | Any Value Change? | This Year Spend Change? | Master Change Flag | (Negative means old value is lower) | Cell Colour Code
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Delivery | External [O] | 1449.1201 | 944.8257 | 504.2944 | 468.029 | 399.703 | 77.0937 | 0 | 47% | 3% | 34% | 16% | 0% | 187.8604 | 11.9911 | 135.899 | 63.9525 | 0 |  |  | D | 83 | 4361External [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | SAME | 0 | -3.2 | 0 | 140 | -143.2 | 0 | SAME | YES | -3.2 | TRUE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Delivery | Internal [O] | 368.9906 | 151.555 |  | 119.055 | 30 | 2.5 | 0 | 47% | 3% | 34% | 16% | 0% | 14.1 | 0.9 | 10.2 | 4.8 | 0 |  |  | D | 84 | 4361Internal [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | SAME | 0 | 0 | 0 | 10 | -10 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Delivery | Total [O] | 1818.1107 | 1096.3807 |  | 587.084 | 429.703 | 79.5937 | 0 | 47% | 3% | 34% | 16% | 0% | 201.9604 | 12.8911 | 146.099 | 68.7525 | 0 |  |  | D | 85 | 4361Total [O] | 4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Total [O] | SAME | 0 | -3.2 | 0 | 150 | -153.2 | 0 | SAME | YES | -3.2 | TRUE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | External [O] | 903.259 | 903.2585 | 0.0005 | 40.475 | 246.0517 | 616.7318 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 58.4585 | 187.5932 | 0 | 0 | 0 |  |  | D | 126 | 4572External [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - External [O] | SAME | 0 | 0 | 0 | 102.8 | -102.8 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Internal [O] | 0 | 245.331 |  | 0 | 81.777 | 163.554 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 19.4291 | 62.3479 | 0 | 0 | 0 |  |  | D | 127 | 4572Internal [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Internal [O] | SAME | 0 | 0 | 0 | 27.3 | -27.3 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 327.8288 | 780.2858 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 77.8876 | 249.9411 | 0 | 0 | 0 |  |  | D | 128 | 4572Total [O] | 4572 UKL Nov '18 Release [R3] (DSC CB) - Total [O] | SAME | 0 | 0 | 0 | 130 | -130 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | External | 1.5 | 1.4 | 0.1 | 0 | 0 | 1.4 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 261 | 4542External | 4542 Changes to Shipper Portfolio Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 262 | 4542Internal | 4542 Changes to Shipper Portfolio Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Total | 1.5 | 1.4 |  | 0 | 0 | 1.4 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 263 | 4542Total | 4542 Changes to Shipper Portfolio Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | External | 8.75 | 8.75 | 0 | 0 | 0 | 8.75 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 264 | 4525External | 4525 Transparency of AQ Process - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 265 | 4525Internal | 4525 Transparency of AQ Process - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Total | 8.75 | 8.75 |  | 0 | 0 | 8.75 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 266 | 4525Total | 4525 Transparency of AQ Process - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Delivery | External | 9.5 | 9 | 0.5 | 0 | 0 | 9 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 267 | 4328External | 4328 iGT Elected Shipper Sites Report - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 268 | 4328Internal | 4328 iGT Elected Shipper Sites Report - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Delivery | Total | 9.5 | 9 |  | 0 | 0 | 9 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 269 | 4328Total | 4328 iGT Elected Shipper Sites Report - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Delivery | External | 7.1 | 7.1 | 0 | 0 | 0 | 7.1 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 270 | 4354External | 4354 Nested CSEP Report for DNs - External | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 271 | 4354Internal | 4354 Nested CSEP Report for DNs - Internal | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Delivery | Total | 7.1 | 7.1 |  | 0 | 0 | 7.1 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0 |  |  | D | 272 | 4354Total | 4354 Nested CSEP Report for DNs - Total | SAME | 0 | 0 | 0 | 0 | 0 | 0 | SAME | NO | 0 | FALSE |  | 0
Note on AM2: Max Pemberton: Checks whether the value for this years spend has actually changed, or just moved from forecast to actual