## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
4525 | NA | AQ Transparency Reporting – reports to ensure transparency of the AQ across the Market | TBC | 2018-05-11 | 25/05/2018 | 01/06/2018 | x |  |  |  |  | 2018-06-13 | Reports being assured and productionised ready for delivery. 1 report is unavailable and will require a minor release to be produced
4328 | NA | IGT Elected Sites Reporting- Reports to capture where the Electing Shipper is not the last confirmed shipper | TBC | 2018-05-11 | 25/05/2018 | 01/06/2018 | x |  |  |  |  | 2018-06-13 | Expected to be delivered by 10th August
NA | 0632 | Shipper asset details reconciliation | TBC | 2018-05-11 | 25/05/2018 | 01/06/2018 | x |  |  |  |  | 2018-07-10 | Report produced; being assured ready to issue to the industry.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | GB Charging Part A | 2008.1 | 2018-07-13 | 2018-07-27 | NA |  |  | X |  |  | NA | 2018-08-08 | 2018-11-18 | No representations received. Issued for 'information only'.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | NA | NA | No approval required in August. Feedback was received - proposed to be discussed at DSG on Monday 6th August and further changes to be proposed based on DSG outcomes
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 23rd July
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4685 | NA | Confirmation of the scope of delivery and planned deployment date of Minor Release Delivery ‘Drop 1’ | 1972.6 | 2018-06-15 | 2018-06-29 | 2018-07-03 | X | [5 empty] | 2018-07-11 | TBC | 3 representation comments received, 2 in support, 1 requesting deferral of new rejection code implementation until a major release. Change Managers to decide whether to implement on 14th July or in a major release. All other changes have no external impact.
NA | NA | Ability to Accept Extended Reading Indexes of up to 12 Characters | 1972.7 | 2018-06-15 | 2018-06-29 | 2018-07-03 | X |  |  |  | X |  | 2018-07-11 | 2019-03-01 | 2 representation comments, both seeking further clarity, both in support of the change.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4453 | NA | Confirmation of File Format Changes and clarification on Version Control | 1946.8 | 2018-05-11 | 2018-05-25 | 2018-06-04 | X |  |  |  |  | 1961 | NA | R3 | 2 x representation comments received. Both comments sought alternative options. DSG need to discuss and propose a solution

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
NA | UK Link & CMS Disaster Recovery test 2018 | 2018-08-10 | TBC | 2018-08-12 | TBC | To test and confirm disaster recovery processes and procedures for the UK Link application. 2 outages will be required over the weekend, times to be confirmed. | 09/05/2018 New dates notified 13/06/2018
NA | Gemini and UK Link Portal | 2018-09-09 | 03:00:00 UK BST | 2018-08-26 | 07:00 UK BST (contingency 08:00) | Activity is to upgrade the perimeter Checkpoint firewalls that provides security to Xoserve applications: Contact Management System (CMS), Gemini, PRISMA, Extended Product 1 (XP1), UK Link Network, Data Communications Company (DCC), Enhanced File Transfer (EFT) and UK Link Portal. | 2018-08-08
N/A Request Number - Impacted System is CMS |  | Fail Over: 15/09/2018 | Midnight | 2018-09-16 07:00 | 07:00 UK BST (contingency 07:00 23/09/2018) | Xoserve will be conducting a scheduled Disaster Recovery (DR) exercise for the CMS Application which will be carried out during the CMS Maintenance window, with activities following the below schedule: | 2018-08-08
|  | Failback: 16/09/2018 | Midnight | 2018-09-17 | 07:00 UK BST (contingency 07:00 24/09/2018) | Xoserve will be conducting a scheduled Disaster Recovery (DR) exercise for the CMS Application which will be carried out during the CMS Maintenance window, with activities following the below schedule: | 2018-08-08