## Issue Register - Open
Issue ID. | Date Raised | Customer Sector Affected | Defect / CR ID. | Issue Title | Issue Description and Materiality | Industry / Customer Impact (financial & process) | Xoserve Priority | Resolution Action Plan | Latest Update | Resolution Status | Date of Status Change
I001 | 2017-06-01 | Shippers | Mod 0658 / XRN4695 | Levels & volatility of Unidentified Gas (UIG) | Levels & volatilty with UIG between D-5 of the gas day to GFD+5 and beyond D+5 close-out in extended reconciliation periods which create the need for Shippers to account for UIG until eventually reconciled. | The ongoing level, volatility and unpredictability of UIG is causing considerable commercial difficulty to Shippers across both domestic and non-domestic sectors | High | 1. Submit BER to ChMC for approval - Complete 2. Subject to approval, mobilise team - UIG Task Force - Complete 3. Produce plan - Complete 4. Issue Customer dashboards 5. Comms plan | UIG Issue Register published on xoserve.com & updated weekly. Update & progress report to be presented at September ChMC | On Track
I002 | 2017-07-18 | Shippers |  | Amendment Invoice supporting information (AML & ASP files) | A number of functional defects and integration issues are causing presentation and charge calculation issues within the AMS invoice. | Presentation issues where data is missing or incorrect within the ASP / AML supporting data files which a workaround is in place but is causing customers issues when trying to match the data. The charge calculation issues are excluded from the invoice until a fix is deployed. | High | 1. Resolve the defects - ongoing 2. Correct data contained in the file - ongoing 3. Correct presentation of the invoice - ongoing 4. Reduce the time taken to issue supporting information to customers - ongoing 5. Carry out Design and RCA. - ongoing | Part 1 of the Root Cause Analysis (Known as UBID) has been tested and the fix was deployed over the weekend (25th August). We believe that this fix will significantly reduce the amount of mismatches within the ASP and AML supporting information files. Customers will see a reduction in the amount of mismatches within the September Amendment Invoice which is issued in October. Part 2 of RCA Root Cause Analysis work has been completed and we have mobilised a team of business and technical experts whose sole purpose is to develop, test and deliver fixes to the known defects that are impacting the Amendment invoice supporting information. The task force will deploy fixes as soon as they have completed all assurance testing, which means that we may implement these fixes ahead of current release schedule. These defects will continue to be discussed at the bi-weekly Delivery Sub Group meeting (DSG) and the weekly defect summary report will continue to be published. | At Risk
I003 | 2018-03-20 | Shippers | 945 | Incorrect functionality of a Meter Read validation routine affecting circa 3,000 meter reads | An issue was identified in March following a number of exceptions raised from UK Link. A validation routine in UK Link was creating exceptions in certain scenarios when processing the meter read. It was found that the validation job was incorrect. On the 9th March 2018 the validation was stopped. Analysis has identified that 3,652 MPRNs have been affected. | Reads accepted and displayed correctly on UKLink & Data Enquiry however AQ & Reconciliation calculated on the amended read or read date. | Medium | 1. Apply fix to all MPRNs. A data fix was deployed weekend of 5th/6th May. Complete 2. Correct energy of those MPRNs affected for the May Amendment invoice issued in June. Complete 3. Carry out analysis on affects on the MPRNs by 15th June. Complete 4. Notify Shippers of the MPRNs (completed on 11th May), impacts & what has been done to correct by w/c 10th September | 1. Re-profiled data following meeting with Operational team. Based on this we have identified all affected MPRN's that require a new read to be loaded 2. Reports to be validated and issued to customers w/c 10/09/2018 | On Track
I007 | 2018-04-01 | Shippers | XRN4671 | Energy for Class 2 sites incorrect in Gemini where a read replacement is received or a consumption adjustment within GFD+5. | Energy mismatch in Gemini where a read is replaced with a read or a consumption adjustment for Class 2 sites as the energy calculated is not being sent to Gemini correctly. | Impacts to invoicing: Energy Balancing, UIG, Commodity invoice, Impacts UIG - inaccurate values until adjustments are carried out. | High | 1. Carry out RCA. Complete 2. Raise defect. Complete CR raised 24/05/2018 4671. 3. Daily monitoring & adjustment process in place. 4. Deploy fix | New planned implementation date is 16th September | At Risk
I009 | 2018-02-12 | Shippers |  | Missing Read files where the meter exchange takes place on same date as transfer date | Transfer read files are not issued to the Shipper where there has been a meter exchange on the same day as a shipper transfer | Opening read & closing read not issued to the outgoing & incoming Shipper | Medium | Agreement at DSG a workaround until the defect is fixed | Workaround is still in place and the fix for this defect is planned to take place in October | On Track
I011 | 2018-06-05 | Shippers | XRN4578 / XRN4740 | AQs calculated incorrectly following a meter exchange where AMR is installed on a Class 4 meter point | For Class 4 meter points where an asset update received and AMR is installed, the site visit read relating to the Meter Exchange is calculating the volume back to the previous AMR installation, which is correct however, this volume is being included within the AQ calculations and therefore using a duplicated volume for this period of time and resulting in an inflated AQ. | Inflated AQs used for gas allocation, this will have an impact on UIG. | Medium | 1. Raise Defect. Complete CR raised: XRN 4578, XO3637 2. Analysis & profiling. Complete 3. Notify Shippers of MPRNs affected & the correct values that should have been issued by 30th July. Complete 4. Raise CR for fix. Complete 6. Agree options for correcting AQ at DSG. Complete 5. Apply fix | Change Request raised (XRN4740) & approved for fix to be deployed. Awaiting deployement date. | On Track
I012 | 2018-03-01 | DN's |  | The number of Must Reads has increased significantly | - DNs raised the issue that the value on the invoices that we produce on their behalf to the Shippers has reduced since Nexus. At the same time, the invoices from the MRAs for procuring reads on their behalf has not reduced. - Analysis identified that the technical elements of the process are working correctly. However, there are reasons for the reduced value of the invoice (not all reasons affect all DNs) | Must Read revenue for DNs | Medium | 1. Analysis 2. Reporting to DNs 3. Focus on team to reduce queries outstanding & clear Must Reads 4. Discussions with MRA | 1. Updates provided directly to each DN on their position and the full position of Must Reads is provided 2. Attend DN Constituent meeting to provide overall updates. 3. Regular comms to DNs on progress updates & latest Must Read stats 4. Propose to close at Sept CoMC | On Track
I013 | 2018-06-21 | All | See separate tab | Data issues affecting AQ calculations | External queries have been raised regarding the AQ values calculated in May. This has resulted in the identification of potentially 14 data issues which may have affected the May and June AQ calculation. The analysis has identified that the issues appear to be related to specific scenarios associated with the energy used in the AQ calculation | Incorrect allocations which will only correct when a read is loaded and energy is reconciled however it will take upto 12 months for the AQ to correct. This will also affect UIG as the allocations for NDM meter points are based on the AQ. | High | 1. Profiling to identify no. of meter points affected and the impacts on the AQ - ongoing, focus on RCA & fix 2. Map each issue to the scenarios identified that have caused issues in the AQ calculation - complete 3. Identify any defects resulting in held Reconciliations that have also affected AQ - Complete 4. Resolution options - ongoing 5. Correction of consumption | Discussed at DSG on 20th August. Shippers requested ball-park figure for affects to AQ & UIG - provided on 23rd August. Defect planning & prioritisation in progress. | At Risk
I023 | 2018-09-07 | Shippers |  | Estimated Transfer of Ownership Read Failure | Estimated Read not issued in MBR file following Transfer of Ownership . The two days affected were 15/06/2018 and 30/06/2018 and applied to 78 MPRN's (12 Shippers) | Shippers have not received notification of Estimated Transfer Read | Low | 1. Notify the Shippers of all affected MPRN's 2. IS Ops to ensure that the estimated read is sent via the MBR file to all affected Shippers by close of play Friday 14th September | 1. Reports issued to Shippers on 10/09/2018 2. IS Ops manually working through the affected MPRN's to ensure that the MBR file is generated to provide the estimated transfer read to the Shipper | On Track
Insert new rows above this line |  |  | Insert new rows above this line

## Issue Register - Closed
Issue ID. | Date Raised | Customer Sector Affected | Defect / CR ID. | Issue Title | Issue Description and Materiality | Industry / Customer Impact (financial & process) | Xoserve Priority | Resolution Action Plan | Latest Update | Resolution Status | Date of Status Change
I004 | 2017-12-11 | DN's |  | Network Reports - providing aggregate AQ, SOQ & CSEP portfolio information (BOPRI & SCH606) | The BOPRI & SCH606 reports are issued to DNs monthly (BOPRI on 28th & SCH606 on the 1st). There have been issues with both reports including the December report which DNs use to set their transportation rates for the 12 months commencing 1st April. BOPRI shows all 'rolling' AQs, SCH606 all CSEP SOQs. Updated reports issued on the 11th January however, due to the difference in the reports Networks were not confident with the reports issued in January. | Reports are used by DNs for setting the transportation rates the the 12 months from April. Any errors in the reports will mean an under or over recovery which will need to be adjusted. | 3. High | 1. Validate the report issued in January. Complete 2. Ensure the monthly reports issued are correct. Complete 3. Ensure the IA carried out for datafixes includes BW impacts. |  | Complete | 2018-06-05
I008 | 2018-05-15 | Shippers | 969 | Incorrect AQ/SOQ values issued in transfer of ownership files | At D-2 the TRF (transfer of ownership file) is issued to the Shipper and provides the values that will be effective on the transfer effective date, including AQ and SOQ values. Due to a code change for a defect deployed on September 27th 2017, incorrect Rolling SOQ data has been sent for all Class 3 and 4 sites transferring ownership, equating to 1.75 million Meter Points with incorrect SMP rolling SOQ values. The rolling SOQ being issued is the value as at EUC effective date (either 1st October or 1st of the month if a rolling AQ change has taken place).The transportation rates sent in the same file are correct. | Incorrect AQ & SOQ values issued to incoming Shipper. Transportation charges provided on the files are correct. | High | 1. Defect raised (969). Carry out RCA. Complete 2. Deploy fix. Complete 3. Notify Shippers of MPRNs affected & the correct values that should have been issued by 20th July. | Reports issued to Shippers on 23rd July 2018 showing the MPRNs affected, incorrect SOQ sent in the file & the SOQ that should have been sent in the file. | Complete | 2018-07-23
I014 | 2018-06-28 | Shippers | 1022 | Read issued in the Transfer of Ownership files (TRF) | At transfer of ownership the TRF file is issued on D-2 of the Confirmation effective date confirming the effective date of the Confirmation. The MRI file is also issued which contains asset information. The ‘Last Actual Read’ recorded on UKLink is submitted in both the TRF file (S15) and the MRI file however the read in the MRI is not the correct read. Defect 1022 raised. This has been since 01/06/2017. | Shippers use the read submitted in the transfer of ownership files to validate the next read received. | Medium | 1. Understand issue & resolve Complete 2. Apply fix 3. Advise Shippers when code deployed | Communication sent to Shippers on 28/08/2018 advising that the issue is fixed | Complete
I017 | 2018-07-12 | Shippers | N/A | DPS file sequencing | DPS files issued to Shippers have not followed the sequence of the last release (e.g. .PN002332.DPS’ to .PN002354.DPS’ ) | Loading of files | Medium | 1. Understand issue & resolve 2. Advise Shippers | Files re-issued on 12/7/18 | Complete | 2018-07-12
I019 | 2018-07-20 | Shippers | N/A | DM Reports | DM reports issued to Shippers were incorrect for 30/06/2018 to 06/07/2018 | TBC | Medium | 1. Identify reason for incorrect values being issued 2. Re-run reports & re-issue |  | Complete
I020 | 2018-07-25 | Shippers | 999 | Incorrect FYAQ values issued in transfer of ownership files (TRF). | At D-2 the TRF (transfer of ownership file) is issued to the Shipper and provides the values that will be effective on the transfer effective date, including FYAQ and FYSOQ values. Incorrect FYSOQ data has been sent for all Class 3 and 4 sites transferring ownership, | Incorrect FYAQ & FYSOQ values issued to incoming Shipper. Transportation charges provided on the files are correct. | Medium | 1. RCA & profiling to identify no. of meter points - complete 2. Deploy fix. Complete. Complete 3. Notify Shippers of MPRNs affected & the correct values that should have been issued by 20th August. | 23/08/2018 - issue now closed and data provided to customers | Complete | 2018-08-23
I021 | 2018-07-27 | Shippers | N/A | UIG Rec Invoice includes kWh for SSP pre go live | The kWh presented to you in the supporting information is not as expected as we have included the kWh associated to SSP reconciliation pre go-live (which has no financial value). However this does not impact the invoice value as the smear is based on the monetary value (GRE) and we do not re-value the reconciliation using SAP and kWh. | TBC | Low | New, TBC |  | Complete | 2018-07-27
I022 | 2018-07-27 | Shippers | N/A | Delay is publishing the Performance Assurance Report Register (PARR) reporting | The publication of the Performance Assurance Report Register (PARR) reporting for August 2018 will be delayed and will not be published on Monday 30 July 2018 as expected. | Unable to view reports | Low | The CDSP and PAFA are working on resolving these issues as efficiently as possible |  | Complete | 2018-07-27
Insert new rows above this line |  |  | Insert new rows above this line

## P1 P2 Incidents
Ticket Ref | Date Raised | Issue Title | Issue Description | Cause | Resolution Action Plan | Raised By | Status | Closed Date
843169 (Problem ID 1636) | 2018-05-03 | Issues with the Allocation run in Gemini affecting UIG | Issue encountered with the first run of Energy Allocation for Gas Day 2nd & 6th May 2018. NDM Allocation failed to calculate for this gas day, for all LDZs, This was corrected within the day. | The cause of this issue is due to a code fault | 1. RCA 2. Daily monitoring until the cause is known 3. Datafix to be deployed end of June for issues relating to May allocation run (Problem ID 1636) 4. Review validations for data contained within files | Xoserve | Closed | 2018-05-03
848559 | 2018-05-17 | Gas Nominations batch job failure affecting UIG | Unidentified Gas nominations batch job failure within Gemini at approximately 11:00 on 17th May. Issue repeated on 21st May. All shippers with active Unidentified Gas meters in Gemini would have had a blank value within the Gemini demand screen for the next gas day nominations. Between 11:00 and 14:20 no forecasting figures shown | This is a known issue where a fault with the Gemini consequential code changes (as part of UK Link Replacement Implementation) resulted in figures remaining uncalculated in certain scenarios. | 1. RCA 2. Daily monitoring until the cause is known 3. Datafix to be deployed end of June | Xoserve | Closed | 2018-05-17
843903 | 2018-06-04 | Workflow did not complete in SAP potentially resulting in incorrect data held in UKLink & Gemini | Workflow did not complete for 4,000 meter points resulting in potential incorrect data being held in UKLink & SAP affecting gas nominations, allocations, DEs & invoicing. May also impact read estimation & read processing. | Fix deployed at the weekend affected the process. | 1. Identify cause 2. Re-start workflow & monitor until completion 3. If updates not completed by deadline date for each update, notify relevant customers & impacts as at 05/06/18: - 97 MPRNs which were due yesterday , have been completed yesterday - All affected workflows identified re-instantiated successfully - 3956 MPRNs - No Contract Change process flows pending for effective date prior to 04.06.2018. Out of 187 Class Change to be effective today i.e. 05.06.2018 , 82 are already completed, remaining are in progress . | Xoserve | Closed | 2018-06-05
| 2018-06-05 | Incorrect file loaded into Gemini affecting Allocations in Gemini & UIG | Issued experienced on 5th & 6th June due to incorrect file loaded for 5th June, delay with processing the file caused issues with allocation run on the 6th June. This was corrected within the day. Delayed publication of the UIG data for the 5th of June has meant that customers would have seen their UIG screens showing a blank value until the UIG job (as part of the Allocation Suite) had completed. | This was due to a system issue by Networks Aggregator systems experiencing a technical issue when transferring the file between systems. | 1. RCA 2. File re-loaded & Process re-ran 3. Correct UIG data was published around 12:30pm | Xoserve | Closed | 2018-06-06
856558 (Problem ID 1708) | 2018-06-08 | Incorrect demand forecast received affecting Gas Nominations & UIG | Separate issue affecting UIG for Gas Nominations on 8th June due to incorrect demand forecast received. All shippers with active Unidentified Gas meters in Gemini would have had a blank value within the Gemini demand screen for the next gas day nominations. Between 11:00 and 14:20 no forecasting figures shown | June issue caused by file an incorrect demand forecast had been sent to Gemini from National Grid’s Aggregator service, due to a Distribution Networks submitting incorrect values to NG. | 1. RCA 2. Daily monitoring until the cause is known 3. Continued daily monitoring until a manual validation or system validation can be implemented | Xoserve | Closed | 2018-06-10
856162 (Problem ID 1713) | 2018-06-15 | Issues with the Allocation run in Gemini affecting UIG | Issue identified on the 15th June. The UIG values are very high for LDZs NW, NO, WM for Gas Day 13/06/2018 | This is due to low Daily Metered (DM) values being used as part of the UIG calculation within the allocation suite job. | 1. RCA 2. New values received via the CON file will instigate a re-calculation using the correct Daily Meter value. UIG values will be monitored on a daily basis until Sunday Morning (17th June 2018) to ensure recalculation occurs. 3. If the UIG values do not re-calculate by the above date/time (due to no new amendments received via the CON file) then a data fix will be applied. 4. Further checks will be made early Monday morning (18th June) at 09:00 post the allocation suite run on Sunday evening at 19:00. | Xoserve | Closed | 2018-06-18
865213 | 2018-07-02 | Line Pack not published | A Control Room User raised a ticket as Line Pack had not been published for 00:00 hour bar. | Gemini Application Support began investigating and found that Gemini had received two Line Pack files at 23:00; this meant that the 23:00 hour bar loaded successfully with the first file but the second file got stuck in processing. The batch job was triggered and the 00:00 hour bar Line Pack file was published successfully. | P2 Incident Management process. | NG Control Room | Closed | 2018-07-02
| 2018-07-04 | Data Enquiry Service is at D-2 | There has been a delay in completing the daily data load for the Data Enquiry Service (DES). As a result the system is displaying data for 2nd July 2018 but data for 3rd July 2018 is not visible. The data for 3rd July 2018 is currently being loaded which means users may be experiencing slow performance on some of the screens |  | 1. RCA 2. Run batch process to update data 3. Advise customers | Xoserve | Closed | 2018-07-05
| 2018-07-12 | Technical issue with Data Search telephone service | technical issue with our Data Search telephone service, 0121 713 4901 and Contact Management Helpline, 0121 713 4903 |  | P2 Incident Management process Available 13/07/18 at 8.00 am | Xoserve | Closed | 2018-07-13
873558 | 2018-07-16 | UIG not visible in Gemini | Shippers and GNCC are unable to view the UIG Nominations balance for 15th and 16th Gas day & UIG allocations for 14th | A column in one of the table has size 8 digits which is causing the UIG job failures. Database have restructured the table column size from 8 to 10 in the production environment | P2 Incident Management process. The P2 for this issue will be closed, however as part of each Major Incident a Problem Record will be created that will be used to identify the Root Cause and provide any forward service improvement actions | Xoserve | Closed | 2018-07-16
874837 | 2018-07-20 | UIG mismatch in Gemini | Mismatch due to the UIG allocation job took time to complete for the gas day (11th ,12th,13th,14th,15th) which delayed the process. | Job overrun due to defect 873558 | This will be included in the RCA raised for the P2 | Xoserve | Closed | 2018-07-20
884278 | 2018-07-29 | Gemini-Demand Attribution not published for 10th hour bar | P2 raised at 10:30. Shippers unable to place gas nominations. | Scheduling team have identified that the demand attribution jobs were on hold | Batch jobs have manually released the jobs. Jobs are now completed and demand attribution is published. Service resumed at 11:31. Problem record raised for further investifgation: 1797. | Xoserve | Closed | 2018-07-29
886370 | 2018-08-05 | IX - Unable to connect to multiple shipper sites | AML file delivery to 3 shippers impacted. | Vodafone IX team have updated that the connectivity issue is due to huge file transfer (400MB files); | Rebooted the IX servers for the affected sites to restore the connectivity. | Xoserve | Closed | 2018-08-05
888227 | 2018-08-09 | UIG Allocations | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 8th). This has affected the following: The UIG allocation values for Gas Days 3rd to 6th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 7th August were not calculated and appear as zero for all LDZs for all Shippers | This was due to the allocation suite overrunning on 8th August hitting the maintenance window. | Calculations to have been completed and visible to Shippers via Gemini from this afternoon (Thursday 9th). A service improvement proposal is currently being reviewed by NG regarding our recommended tactical archiving solution to alleviate the operational issues associated with the overrunning allocation suite. We are expected approval from their change board next week so we can start the work Fix was successful on Friday 8th September. Performance has been monitored over the last 3 days, and average run time for UIG allocations is around 2 hours instead of 6-8 hours | Xoserve | Closed | 2018-08-09
888227 | 2018-08-10 | UIG Allocations | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 9th). This has affected the following: The UIG allocation values for Gas Days 4th to 7th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 8th August were not calculated and appear as zero for all LDZs for all Shippers This is linked to 888227 | This was due to the allocation suite overrunning on 9th August hitting the maintenance window. | Calculations to be completed (by 12:45) and be visible to Shippers via Gemini from this afternoon (Friday 10th). A service improvement proposal is currently being reviewed by NG regarding our recommended tactical archiving solution to alleviate the operational issues associated with the overrunning allocation suite. Approval expected from change board next week so work can begin early September. Fix was successful on Friday 8th September. Performance has been monitored over the last 3 days, and average run time for UIG allocations is around 2 hours instead of 6-8 hours | Xoserve | Closed | 2018-08-10
888227 | 2018-08-13 | UIG Allocations | The Unidentified Gas (UIG) batch job failed to complete in Gemini yesterday evening (August 12th). This has affected the following: The UIG allocation values for Gas Days 4th to 7th August were not updated and are out of date for all LDZs. The UIG allocation values for Gas Day 11th August were not calculated and appear as zero for all LDZs for all Shippers This is linked to 888227 | This was due to the allocation suite overrunning on 11th August hitting the maintenance window. | Currently discussing remedial action with National Grid to minimise further instances occurring, this is currently going through governance & planning stages for delivery of the service improvement. Highly likely that the issues will continue to delay the UIG batch jobs until the fix is implemented. Change proposal raised and approved. This will be implemented during Gemini maintenance window on Friday morning (with the caveat that the issue does not occur Thursday evening). So the first actual run in Production will be Friday evening. Fix was successful on Friday 8th September. Performance has been monitored over the last 3 days, and average run time for UIG allocations is around 2 hours instead of 6-8 hours | Xoserve | Closed | 2018-09-11
893054 | 2018-08-24 | Amendment Invoice | The UGR charge in the Amendment Invoice is incorrect. The total national Unidentified Gas reconciliation value is correct, but the allocation to individual Shippers is incorrect. | Error in the brought forward Shipper throughput values for market shares of UIG reconciliation allocation from the previous month | The correct allocation of Unidentified Gas reconciliation will be calculated and an adjustment invoice will be issued week commencing 10th September 2018 | Xoserve | Open
896574 | 2018-09-05 | IX file transfer service unavailable | Inbound and outbound file flow for Shippers (4) impacted |  | Service Provider has configured and installed new kit for all affected shippers and the file flow has restarted. | Xoserve | Closed | 10/09/2018
Insert new rows above this line

## AQ Issues
Defect No. | Description | Volume | Customer Impact | Expected Fix Date | Tracked by AMS/AML Focus Team? | Update as of 11th September | Status | Date Affected Meter Points Issued
1067 | Where an estimated transfer read is replaced (via the Shipper Agreed read process) the consumption and energy calculated from the replaced read is incorrect. | 67474 | The incorrect energy will be used in the AQ process for calculating a revised AQ. | Not allocated as yet | No, this does not have an impact on the energy used for Reconciliation process. | 1366 new MPRNs have been identified to be affected by this defect. These are being profiled and will be shared once the data is available. | Open | The MPRNs known as at 30/07/2018 issued on 03/08/18
1043 | The AQ calculation process should only consider consumption history on or after the backstop date. Functionality prior to fix on 12th July 2018 was not considering any reads where the read date is equal to the backstop date. Therefore a revised monthly AQ will not be calculated. This scenario will apply in the following cases: 1. New meter points confirmed on or after 1st June 2017 where the confirmation effective date is the backstop date for AQ calculation process. 2. Following an AQ Correction, the effective date of the corrected AQ is the backstop date. | 9922 | Potential impacts: The consumption period is reduced for the purposes of the monthly AQ process. | Deployed on 12/07/2018 | No as this does not affect the creation of a reconciliation or the charges. | The fix was deployed on 12th July 2018. The issue prevented AQs being calculated. Now the functionality is working correctly any meter reads loaded after 12th July will, subject to validations, calculate an AQ. | Closed | 2018-07-11
985 | Where an RGMA asset update is submitted and accepted between D & D+5 of the effective date of the transfer, the energy is calculated incorrectly. Volume & energy for asset read is being calculated, should be recorded as zero as the volume & energy is calculated from transfer read. | 11,855 as at 7th August | The incorrect energy will be used in the AQ process for calculating a revised AQ | Deployed in R2.02 on 27/07/2018 | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team | Following fix being deployed, all of the MPRNs affected by this defect was provided on w/c 20/08/18 and the period of the incorrect consumption; start and end of the incorrect consumption & energy calculation. | Open | The MPRNs known as at 04/07/2018 issued on 06/07/18
933 | Where an estimated transfer read is generated and loaded with a TTZ (Through the Zeros) count of one, on receipt of the next actual read the energy calculated is incorrect. Estimate loaded with TTZ of 1, when Shipper replaces the read the TTZ count is used to calculate the energy. A negative consumption should have been created. | 166 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Deployed in R1.21 on 04/05/2018 | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team | The MPRNs affected by this defect was provided w/c 30/08/18 and the period of the incorrect consumption; start and end of the incorrect consumption & energy calculation. | Open | The MPRNs known as at 04/07/2018 issued on 06/07/18
1040 | Where a read is received for a Class 4 Prime & Sub site the read is not triggering an AQ calculation | 5 (TBC) | No AQ for Class 4 P&S sites. | Planned to be deployed as part of R2.05 | No as this does not affect the creation of a reconciliation or the charges. | This defect is preventing AQs being calculated. Once the fix is deployed affected Shippers will be contacted for resolution options. | Open | Will be provided once the fix is deployed
1052 | The energy calculation is incorrect where there is an estimated read used for reconciliation, the TTZ of -1 is being used in the calculation. | 947 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team | The MPRNs affected by this defect were provided on 08/08/18 and the period of the incorrect consumption; start and end of the incorrect consumption & energy calculation. | Open | MPRNs provided 08/08/18
937 | Where a consumption adjustment is received for a DM meter point (Class 1 and 2 only) during the period of an asset update, the consumption adjustment is rejected. Only affects Class 1 and 2 meter points. | TBC. Linked to defect 974. | For the AQ process the original consumption will be used, not the revised consumption. | Deployed on 08/08/18 | No. Reconciliation is not created. | Date TBC of the MPRNs affected by this defect | Open | 2018-07-11
1045 | Following read replacement prior to a shipper transfer the reconciliation is missing any read between the replaced read and the shipper transfer read. The replaced read should reconcile back to the next subsequent read, instead it is reconciling to the shipper transfer read. | 1260 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team | The code changes have been completed, testing scenarios being developed. The MPRNs affected by this defect were provided on 08/08/18 and the period of the incorrect consumption; start and end of the incorrect consumption & energy calculation. | Open | MPRNs provided 08/08/18
863 | Incorrect volume and energy calculated where a read is replaced via the SAP screens | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team | Date TBC of the MPRNs affected by this defect | Open | TBC
XRN4740 | For Class 4 meter points where an asset update is received and AMR is installed, the site visit read relating to the Meter Exchange is calculating the volume back to the previous AMR installation, which is correct however, this volume is being double counted in the AQ calculations and therefore using a duplicated volume for this period of time and resulting in an inflated AQ. | Approx 7000 | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | No as this does not affect the creation of a reconciliation or the charges. | New CR raised to fix issue | Open | TBC
1122 | AQ calculation greater than expected, appears to have included energy recorded against an inactive reading | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | No as this does not affect the creation of a reconciliation or the charges. | Defect 1103 has been closed as a Duplicate defect of 1122 | Open | TBC
New
1125 | It has been identified for Class 4 Sites with AMR fitted where a site visit read has been loaded and a subsequent cyclic read has already been received and processed. Then the system should recognise the site visit and should recalculate the volume/energy between the site visit read and the cyclic read. | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team |  | Open | TBC
XRN4742 | When a shipper carried out a reconfirmation the new UKLink system required a reading for the Final read (FINT) and the Opening read (OPNT). It was an agreed approach at the time of migration to load a consumption of zero for OPNT and FINT reads and leave all the consumption against the latest read. This was carried out for 175k NDM Supply Meter Points. This approach was taken as it was deemed too difficult to apportion in the Energy, however will/has caused incorrect AQ and possibly FYAQ calculations since Nexus Go Live | Approx 175k | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | No as this does not affect the creation of a reconciliation or the charges. | Date TBC of the MPRNs affected by this defect | Open | TBC
947 | Where an incoming Shipper is supplying the Opening Read D-5 and D-1 of the actual shipper transfer date, the outgoing shipper is also submitting a cyclic read within this transfer window which is causing the volume/energy to be calculated incorrectly. This is affecting the AQ values calculated. | TBC | The incorrect energy will be used in the AQ process for calculating a revised AQ | Not allocated as yet | Yes. This defect is being monitored and tracked by the Amendment Invoice Focus team | Profiling is ongoing and the MPRNs affected by this defect will be issued W/c 10/09. | Open | TBC