## Slide 1: Change Management Committee – June 2019 Update
September 12th 2018

## Slide 2: June 19 Headlines
All 12 changes allocated to June 2019 are still progressing through the Capture phase:
  7 changes are currently undergoing ‘High-Level Solution Option Impact Assessments’ (HLSOIAs).
  2 changes (XRNs 4676 & 4044) have completed HLSOIAs….
  A further 3 changes (XRNs 4642, 4645 & 4679) are now proposed for November 2019 as the requirements are not mature enough to be included for a June 2019 release.
As the preferred solution option for each change needs to be agreed prior to being formally assigned to a June 19 release, there is a tight timeframe to ensure that all changes are in a position to be agreed in October 10th ChMC.
An extraordinary ChMC may also be required, following October’s ChMC, to approve the EQR for the progression of Design. Further analysis is underway by Xoserve to understand whether this is required or not, an update will be provided ASAP.

## Slide 3: Change Index
June 19 | XRN | Change Title | Current Capture Status | Complexity | Impacted Parties | HLSOIA Due | Target Issue Date for Solution Packs | Target DSG Session to Confirm Preferred Option | Target Close-Out Date for Solution Packs | Target ChMC Session to Confirm Preferred Option & inclusion in June ‘19 release
 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | Undertaking HLSOIA | Low | Xoserve | 10/09/18 | 14/09/18 | 17/09/18 | 28/09/18 | 10/10/18
 | 4690 | Actual read following estimated transfer read calculating AQ of 1 | Undertaking HLSOIA | Medium | Shippers | 12/09/18 | 14/09/18 | 17/09/18 | 28/09/18 | 10/10/18
 | 4687 | PSR updates for large domestic sites | Undertaking HLSOIA | Low | Shippers | 14/09/18 | 14/09/18 | 17/09/18 | 17/09/18 | 10/10/18
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | Undertaking HLSOIA | Medium | DN | 19/09/18 | 21/09/18 | - | 05/10/18 | 10/10/18
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | Undertaking HLSOIA | Medium | DN | 19/09/18 | 21/09/18 | - | 05/10/18 | 10/10/18
 | 4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | Undertaking HLSOIA | High | DN | 19/09/18 | 21/09/18 | - | 05/10/18 | 10/10/18
 | 4694 | CSEPs: IGT and GT File Formats (Create new data validations ) | Undertaking HLSOIA | High | DN | 19/09/18 | 21/09/18 | - | 05/10/18 | 10/10/18
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | Completed HLSOIA | Medium | Xoserve | Completed | 23/09/18 | 07/09/18 | 20/08/18 | 12/09/18
 | 4044 | Extension of ‘Must Read’ process to include Annual Read sites | Completed HLSOIA | Low | Cadent Gas | Completed | N/A | 17/09/18 | N/A | 10/10/18
 | 4642 | Address Maintenance Solution | Capture Workshops in Progress | Medium | Xoserve | Current Status: This is suggested to move to November 2019 as the requirements are not mature enough to progress to HLSOIA at present. |  |  |  | 
 | 4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows) | Capture Workshops in Progress | High | Shipper/DN | Current Status: This is suggested to move to November 2019 as the requirements are not mature enough to progress to HLSOIA at present. |  |  |  | 
 | 4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | Capture Workshops in Progress | Medium | Xoserve | Current Status: This is suggested to move to November 2019 as the requirements are still being ratified with customers. |  |  |  | 
* Italics indicate that the funding has not been formally agreed at ChMC
**Extraordinary DSG meeting required