## Intro Page
Xoserve Change Delivery Plan on a Page |  | Legend
|  | XXX | Completed Task
| The attached plans give a view of the all change currently being managed by Xoserve via mutiple delivery platforms, UK link, Gemini, and Data. |  | Forcast Activity
| Tab 1 - provides all UK Link impacting change, release 2 & 3 are currently in delivery, releases June-19 and Nov-19 have not yet had the scope for inclusion in the release agreed, therefore any change detailed in these releases are placeholders only. Also sets out potential delivery timelines for CSS (Central Switching Services) and UIG (unidentified Gas). At present RAASP is considered for inclusion in November 2019 release |  | Baseline Activity
| Tab 2 - lists all current live change that feeds into the plans in this publication |  | Potential Actibity
| Tab 3 - Provides a 'look ahead' 2 year view of change for UK Link | RAG | Activity at risk
|  | RAG | Activity with potential risk
|  | RAG | Activity on Track
|  | RAG | Activity under replan/Review

## UK Link_2yr_view
Change Allocation | Count of XRNs
Solution Manager Update (Feb'18) | 1
Release Nov 19 | 4
Release Jun 19 | 11
Release Feb 19 | 0
Release Sep 19 | 0
R3.0 (Nov'18) | 15
R2.0 (Jun'18) | 17
R1.0 (Nexus) | 1
R&N New Environment (Apr'18) | 1
R&N Minor Release/Impact Assessment (Mar'18) | 1
Out for industry sponsorship/approval to reject | 2
Internal req Gathering (Capture) | 13
Minor Enhancement Delivered Change | 15
CSS | 2
Candidate for Minor Release Drop 2 | 3
Candidate for Minor Release Drop 1 | 5
AQ Bands Increase | 1
Closedown | 0
Grand Total | 92
Please filter in column C within the 'R&N_Live_Changes' tab to view specific XRNs

## Sheet4
Row Labels | Count of XRN Ref
(blank)
2019-11-01 | 4 | X
2019-06-01 | 11 | X
Solman | 1 | X
R3.0 (Nov'18) | 15 | X
R2.0 (Jun'18) | 17 | X
R1.0 (Nexus) | 1 | X
R&N New Environment (Apr'18) | 1 | X
R&N Minor Release/Impact Assessment (Mar'18) | 1 | X
Out for industry sponsorship/approval to reject | 2 | X
MR Drop 2 | 3 | X
MR Drop 1 | 5 | X
Minor Enhancement Delivered Change | 15 | X
Internal Requirements Gathering (Capture) | 13 | X
CSS | 2 | X
AQ Bands Increase | 1 | X
Grand Total | 92

## Gemini & Data Stream POAP (hidden)
Gemini
Data Platform

## Gemini & Data Stream_Live_Chang (hidden)
XRN Ref | High-Level Status | R&N Release Allocation | Change Title | Change Type | Delivery Status | Change Lifecycle Status | Xoserve Proposed Indicative Prioritisation Score | July'17 Change Demand Backlog ChMC Priority | July'17 Change Demand Backlog SDG Priority | Xoserve Platform Owner | Origination Date | Change Originator | Xoserve Project Manager | R&N Release Number | Previous UK Link CR Ref | Delivery Team | ClearQuest Ticket (Minor Enhancement Delivery) | Current Delivery Implementation Forecast Date | Actual Delivery Implementation Date | Customer Requested Implementation Date | Primary Application Impacted | Business Process Impact | Flash IA: Perceived Delivery Effort | Workaround Available? | Workaround Accountability | Workaround Frequency | No. of Xoserve FTEs required to service the workaround | Workaround Complexity? | Workaround Lifespan | Change Driver | Change Beneficiary | Shipper Impact | Network Impact | iGT Impact | Primary Impacted DSC Service Area | Number of DSC Service Areas impacted | Change Improvement Scale (Size of proposed change) | Customer System Changes Required? | Customer Testing Likely Required? | Customer Training Required? | Safety of Supply at risk? | Financial Loss Incurred to Customer? | Customer Switching at risk? | ChMC CP Approval date | ChMC EQR Approval date | ChMC BER Approval date | ChMC CCR Approval date
4739 | 1. Start-Up (Progressing through change governance) |  | Standard Testing Toolset | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 9.61% |  |  | T & SS | 2018-08-15 | Jon Follows | Jon Follows |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE | Low | FALSE | FALSE | No Date | No Date
4741 | 1. Start-Up (Progressing through change governance) |  | National Grid Transmission and Deloittes Audit Reporting Suite (AS20180410) | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 11.41% |  |  | Data Office | 2018-08-14 | Fiona Mills | Jo Duncan |  |  | Xoserve Resource | XOS3700 | No Date | No Date | 372092 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | No Date | No Date
4743 | 1. Start-Up (Progressing through change governance) |  | MAM Reconciliation Report (TP20180406 - SPAA – Supplier Performance Schedule 22) | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 35.44% |  |  | Data Office | 2018-08-20 | Emma Partlett | Jo Duncan |  |  | Xoserve Resource | XO3701 | No Date | No Date | 2018-11-02 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Groups | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | Five to Twenty | TRUE | High | FALSE | FALSE | No Date | No Date
4744 | 2. Change sanction/approved and in project delivery |  | Tansform US - IX Server Replacement | CR (Internal) | LIVE | D1 - Change in delivery | 9.61% |  |  | T & SS | 2018-08-20 | Annie Griffith | Michael Dickson |  |  | Xoserve Resource |  | No Date | No Date | No Date | IX | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | No Date | No Date
4745 | 1. Start-Up (Progressing through change governance) |  | Data modelling CLC process | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 19.22% |  |  | Data Office | 2018-08-20 | Mike Orsler/Tahera Choudhury | Alex Sharp |  |  | Xoserve Resource |  | 2018-12-31 | No Date | 2018-09-30 | IX | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4749 | 1. Start-Up (Progressing through change governance) |  | Analysis for the provision of data services to Third Parties | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 14.41% |  |  | Data Office | 2018-08-29 | Mark Pollard | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-01-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4750 | 1. Start-Up (Progressing through change governance) |  | Analysis for a Dual Fuel Enquiry Service | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 16.22% |  |  | Data Office | 2018-08-29 | Mark Pollard | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-11-30 | BW | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4751 | 1. Start-Up (Progressing through change governance) |  | UIG Shipper Dashboards & Internal Dashboards | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.62% |  |  | Data Office | 2018-08-29 | Michele Downes | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-15 | BW | Other | No Delivery Effort | TRUE | Xoserve | Monthly | One | Medium | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | TRUE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4752 | 1. Start-Up (Progressing through change governance) |  | Meter Read Performance | CP | LIVE | A2 - CP proposed for ChMC | 25.83% |  |  | Data Office | 2018-08-31 | Rachel Hinsley | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-30 | BW | Reads | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4754 | 1. Start-Up (Progressing through change governance) |  | Monthly GT / IGT Supply Point Count to be supplied to SPAA Code Administrator | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.62% |  |  | Data Office | 2018-09-03 | Paul Orsler | Paul Orsler |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-10-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4756 | 1. Start-Up (Progressing through change governance) |  | Reporting Balanced Scorecard via BIRST | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.62% |  |  | Data Office | 2018-09-03 | Sabah Hussain | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-28 | Birst | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4734 | 2. Change sanction/approved and in project delivery |  | Capture Process Model (internal process) | CR (Internal) | LIVE | D1 - Change in delivery | 16.22% |  |  | Data Office | 2018-08-08 | Emma Smith | Susan Helders |  |  | Xoserve Resource |  | 2018-10-31 | No Date | 2018-10-31 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4730 | 1. Start-Up (Progressing through change governance) |  | SPAA – Supplier Performance Report (TP20180395) | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 20.42% |  |  | Data Office | 2018-08-07 | Michael Orsler/Emma Partlett | Jo Duncan |  |  | Xoserve Resource | XO3702 | No Date | No Date | 2018-11-01 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4731 | 2. Change sanction/approved and in project delivery |  | Capture Process Model | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-08-07 | Steve Nunnington | Susan Helders |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-07 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4646 | 2. Change sanction/approved and in project delivery |  | Amendment to plot to postal report | CR (Internal) | LIVE | D1 - Change in delivery | 30.63% |  |  | Data Office | 2018-04-10 | Tahera Choudhury | Jo Duncan | 50 |  | Minor Enhancements Team | XO3678 | 2018-11-26 | No Date | 2018-05-04 | BW | SPA | 0-30 days | FALSE | [5 empty] | MOD/Ofgem | One Market Group | FALSE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4623 | 2. Change sanction/approved and in project delivery |  | XEC Customer Dashboard Development | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-02-05 | James Verdon | Jo Duncan | 0 |  | Xoserve Resource |  | 2018-11-30 | No Date | 2018-05-11 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4702 | 1. Start-Up (Progressing through change governance) |  | Opportunity 1: Switching Performance dashboard (s) to enable supplier incentivisation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 24.02% |  |  | Data Office | 2018-06-18 | Rebecca Roden | Jo Duncan |  |  | Xoserve Resource |  | No Date | No Date | 2019-05-31 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4703 | 1. Start-Up (Progressing through change governance) |  | Opportunity 2: Duel fuel enquiry service to deliver improved consumption estimations | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 33.63% |  |  | Data Office | 2018-06-18 | Rebecca Roden | Mark Pollard |  |  | Xoserve Resource |  | No Date | No Date | 2018-05-31 | Other | AQ | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | TRUE | TRUE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4706 | 1. Start-Up (Progressing through change governance) |  | (ASR) National Grid Gas – Test Support & Consultancy on Connectivity between Xoserve & Gemini | CR (ASR) | LIVE | A9 - Internal change progressing through capture | 20.42% |  |  | T & SS | 2018-06-25 | Greg Causon | Nicola Patmore |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-30 | Gemini | Other | 100+ days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | TRUE | TRUE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4169 | 2. Change sanction/approved and in project delivery |  | To update functionality in Gemini to ensure that all Cash Call Notices and TemplaRequest for Project Management resource to manage the analysis and resolution of the issues with the Amendment invoicees reflect UNC Section X and Energy Balancing Credit Rul | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-01-09 | Loraine O’Shaughnessy | Donna Johnson | 50 |  | Minor Enhancements Team | XO3452 | 2018-11-02 | No Date | 2018-09-13 | Gemini | Other | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4672 | 3. Change delivered, awaiting closure approval/sign-off |  | Extension of PCW API Service to Suppliers | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 25.23% |  |  | Data Office | 2018-05-14 | Mark Pollard | Mark Pollard |  |  | Xoserve Resource |  | 2018-06-29 | 2018-06-29 | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4673 | 3. Change delivered, awaiting closure approval/sign-off |  | Identification of Short Haul in Non-standard Sites Reports | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 29.43% |  |  | Data Office | 2018-05-14 | Thomas Rooney | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-24 | 2018-08-24 | 2018-06-30 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | Two to Five | Low | 2019-02-28 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4729 | 2. Change sanction/approved and in project delivery |  | Addition of data items to VOL Enhanced Report | CR (ASR) | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2018-08-03 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-24 | No Date | 2018-09-01 | No Application | No Process | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE | Low | FALSE | FALSE | No Date | No Date
4639 | 2. Change sanction/approved and in project delivery |  | Customer KVI Reporting | CR (Internal) | LIVE | D1 - Change in delivery | 37.84% |  |  | Data Office | 2018-03-27 | Michele Downes | Jo Duncan |  |  | Xoserve Resource |  | 2018-10-31 | No Date | 2018-05-01 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-04-27 | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 19: Network Operator and User Relationship Management | FALSE | FALSE | All | FALSE | High | FALSE | FALSE | No Date | No Date
4714 | 2. Change sanction/approved and in project delivery |  | Birst Reporting for Strategy House Embedding | CR (Internal) | LIVE | D1 - Change in delivery | 33.63% |  |  | Data Office | 2018-07-16 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-08-17 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4619 | 2. Change sanction/approved and in project delivery |  | SAP BW MPRL Delta Table Creation | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-02-26 | Steve Concannon | Fay Morris | 50 |  | Minor Enhancements Team | XO3665 | 2018-11-09 | No Date | 2018-08-30 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4718 | 1. Start-Up (Progressing through change governance) |  | BW Universe Changes Deployment | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 27.63% |  |  | Data Office | 2018-07-20 | Jo Duncan | Jo Duncan |  |  | Minor Enhancements Team | XO3693 | No Date | No Date | 2018-08-31 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | Two to Five | High | 2018-12-31 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4724 | 1. Start-Up (Progressing through change governance) |  | Removal of Asset Status codes DM and FA from file format documentation (impact assessment required) | CR (Internal) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 25.23% |  |  | Data Office | 2018-07-31 | Ellie Rogers | Rebecca Roden |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-10 | ISU | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4683 | 2. Change sanction/approved and in project delivery |  | Class 3 & 4 Energy Comparison Report | CR (Internal) | LIVE | D1 - Change in delivery | 36.64% |  |  | Data Office | 2018-05-25 | Jo Tedd | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-07-01 | Gemini | Invoicing | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | Two to Five | TRUE | Medium | FALSE | FALSE | No Date | No Date
4684 | 1. Start-Up (Progressing through change governance) |  | SAP BW Accelerator: Table Migration | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 16.82% |  |  | Data Office | 2018-05-29 | Fay morris | Fay Morris |  |  | Third Party SI / Service Provider |  | 2019-02-01 | No Date | 2019-02-01 | BW | Other | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4666 | 2. Change sanction/approved and in project delivery |  | Changes to Gemini system to provide Business User access to Class 1 & 2 Energy values, to view & update & include additional data items in existing system generated reports | CR (Internal) | LIVE | D1 - Change in delivery | 40.84% |  |  | T & SS | 2018-05-04 | Jo Tedd | Hannah Reddy |  |  | Third Party SI / Service Provider | XO3676 | No Date | No Date | 2018-05-31 | Gemini | Invoicing | 60-100 days | TRUE | Xoserve | Daily | One | Medium | 2018-12-28 | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | Two to Five | TRUE |  | FALSE | FALSE | No Date | No Date
4542 | 2. Change sanction/approved and in project delivery |  | Changes to the Shipper Portfolio Summary Report (new fields and removal of fields no longer applicable) | CP | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2017-11-24 | Emma Smith | Jo Duncan |  |  | Xoserve Resource | XO3605 | 2018-09-29 | No Date | 2018-11-01 | BW | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2019-01-30 | ChMC endorsed Change Proposal | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-04-11 | 2018-01-10
4525 | 3. Change delivered, awaiting closure approval/sign-off |  | Transparency of the Rolling AQ Process | CP | LIVE | F1 - CCR/Closedown document in progress | 28.83% |  |  | Data Office | 2017-10-31 | Shane Preston/Rachel Hinsley | Jo Duncan |  |  | Xoserve Resource | XOS3584 | 2018-07-31 | 2018-07-31 | 2018-05-25 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2018-04-11 | 2018-02-07
2831.5a | 3. Change delivered, awaiting closure approval/sign-off |  | Smart Metering UNC MOD 430 DCC Testing and Trialling Pre Nexus | CP | LIVE | F1 - CCR/Closedown document in progress | 28.23% |  |  | T & SS | 2015-12-22 | Jo Feguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2017-03-31 | 2017-03-31 | 2017-03-31 | Other | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 17: UK Link Services | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4686 | 1. Start-Up (Progressing through change governance) |  | Smart Metering Report | CP | LIVE | A5a - Solution Development | 28.83% |  |  | Data Office | 2018-06-04 | Liam Percy (CNG) | Emma smith |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | BW | RGMA | 0-30 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4712 | 1. Start-Up (Progressing through change governance) |  | HR and Finance Birst Reporting | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | Data Office | 2018-07-09 | Paul O’Toole | Jo Duncan |  |  | Third Party SI / Service Provider |  | 2018-09-28 | No Date | 2018-08-17 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4594 | 2. Change sanction/approved and in project delivery |  | Customer Inclusion for BIRST Exceptions | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2018-01-23 | Jo Duncan/Thomas Elce | Jo Duncan |  |  | Xoserve Resource |  | 2018-12-30 | No Date | 2018-03-23 | Birst | Other | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-03-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4580 | 2. Change sanction/approved and in project delivery |  | Shipper Performance Birst Dashboard (by Data Cleansing Topic) | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-01-16 | James Verdon | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-29 | No Date | 2018-08-10 | Other | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4726 | 1. Start-Up (Progressing through change governance) |  | Mod 0431 process enhancements | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 34.83% |  |  | Data Office | 2018-08-01 | Tahera Choudhury | Charlie Haley |  |  | Xoserve Resource |  | No Date | No Date | 2018-11-01 | BW | SPA | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-11-01 | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE |  | TRUE | High | FALSE | FALSE | No Date | No Date
4328 | 3. Change delivered, awaiting closure approval/sign-off |  | Report of iGT Meter Points where the confirming shipper is not the elected shipper | CP | LIVE | F1 - CCR/Closedown document in progress | 31.23% |  |  | Data Office | 2017-07-05 | Emma Smith | Jo Duncan | 50 |  | Minor Enhancements Team | XOS3615 | 2018-08-10 | 2018-08-10 | 2018-08-10 | BW | SPA | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE |  | FALSE | Medium | FALSE | FALSE | 2018-03-07 | 2017-07-13
4426 | 2. Change sanction/approved and in project delivery |  | Impact Assessment on changes to Market Intelligence report and Change of Supplier reporting suite ahead of Ofgem RFI | CR (Internal) | LIVE | D1 - Change in delivery | 42.04% | TBP | High | Data Office | 2016-04-28 | Paul Orsler | Jo Duncan |  | UKLP IADBI192 | Xoserve Resource |  | 2018-09-29 | No Date | 2018-07-30 | BW | Other | 31-100days | FALSE | [5 empty] | CMA Order | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4611 | 1. Start-Up (Progressing through change governance) |  | Replacement/Upgrade of Demand Estimation Systems and Processes | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 25.83% |  |  | Data Office | 2018-02-20 | Fiona Cottam | Fay Morris |  |  | Third Party SI / Service Provider |  | 2019-02-28 | No Date | 2019-03-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4655 | 1. Start-Up (Progressing through change governance) |  | Electronic CRM system to Capture Customer Contact Details and Email Conversations | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | T & SS | 2018-04-24 | Adam Jones | Dene Williams |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4610 | 1. Start-Up (Progressing through change governance) |  | ASR Request - Reporting to SPAA Secretariat in Support of SPAA Schedule 25 – Management of Prepayment Activities | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 26.43% |  |  | Data Office | 2018-02-20 | Greg Causon | Jo Duncan |  |  | Minor Enhancements Team | XO3679 | No Date | No Date | 2018-06-30 | BW | SPA | 60-100 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | Multiple Market Participants | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
3676 | 3. Change delivered, awaiting closure approval/sign-off |  | Amendment to the AQ &SOQ File and Field Length | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 19.22% | 0% | 0% | T & SS | 2015-03-24 | Jo Tedd/ Dan Donovan | Donna Johnson | 50 | UKLP IADBI080 | Minor Enhancements Team | XO3598 | 2018-05-08 | 2018-05-08 | 2018-10-01 | Gemini | SPA | 0-30days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4493 | 3. Change delivered, awaiting closure approval/sign-off |  | BIRST Connect integration | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | Data Office | 2017-06-26 | Steve Concannon | Emma Rose | 50 | UKLP IADBI353 | Third Party SI / Service Provider |  | 2018-01-26 | 2018-01-26 | 2017-11-30 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4596 | 2. Change sanction/approved and in project delivery |  | Setup of File Transfer mechanism from BO to IX | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-01-23 | Steve Concannon | Fay Morris | 50 |  | Minor Enhancements Team | XO3647 | 2018-09-22 | No Date | 2018-04-30 | IX | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4689 | 2. Change sanction/approved and in project delivery |  | Aggregate Energy AQ Report | CR (Internal) | LIVE | D1 - Change in delivery | 23.42% |  |  | Data Office | 2018-06-04 | Lee Jackson | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-29 | No Date | 2018-07-01 | BW | AQ | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4473 | 1. Start-Up (Progressing through change governance) |  | Sybase NLS Solution Design Gap | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% | TBP | Low | Data Office | 2017-04-11 | Lee Chambers | Jo Duncan |  | UKLP IADBI317 | Third Party SI / Service Provider |  | No Date | No Date | 2018-06-01 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4354 | 3. Change delivered, awaiting closure approval/sign-off |  | Request for New DNO Report Nested CSEPs Hierarchy Report | CP | LIVE | F2 - CCR awaiting ChMC approval | 27.03% |  |  | Data Office | 2017-09-01 | Cadent Gas /Emma Smith | Jo Duncan | 50 |  | Minor Enhancements Team | XOS3577 | 2018-05-15 | 2018-05-15 | 2018-02-23 | BW | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | 2018-03-07 | 2017-10-10
4634 | 1. Start-Up (Progressing through change governance) |  | Data Catalogue | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 14.41% |  |  | Data Office | 2018-03-21 | Rachel Hinsley | Dave Addison |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2019-02-01 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
4567 | 2. Change sanction/approved and in project delivery |  | Amendment to plot to postal report | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-01-02 | Tahera Choudhury | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-29 | No Date | 2018-02-28 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4571 | 2. Change sanction/approved and in project delivery |  | MAM and MAP asset data analysis and reporting | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2018-01-03 | Andy Miller | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-29 | No Date | 2018-03-23 | BW | Reads | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4570 | 2. Change sanction/approved and in project delivery |  | BW Reports - RA/ RANTS Reporting Logic | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | Data Office | 2017-01-03 | Michael Maguire | Jo Duncan | 50 |  | Minor Enhancements Team | XO3639 | 2018-10-08 | No Date | 2018-01-31 | BW | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4590 | 2. Change sanction/approved and in project delivery |  | SLSP - Incorrect Seasonal Large Supply Point charging | CR (Internal) | LIVE | D1 - Change in delivery | 40.84% |  |  | Data Office | 2018-01-12 | Carole Elwell | Donna Johnson | 50 |  | Minor Enhancements Team | XO3644 | 2018-11-30 | No Date | 2018-08-31 | ISU | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2018-03-31 | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | Two to Five | TRUE | Medium | FALSE | FALSE | No Date | No Date
4592 | 2. Change sanction/approved and in project delivery |  | BIRST work item inclusion & multiple daily updates | CR (Internal) | LIVE | D1 - Change in delivery | 26.43% |  |  | Data Office | 2018-01-23 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-06-29 | Birst | SPA | 0-30 days | TRUE | Xoserve | Daily | One | Medium | 2018-03-30 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4636 | 2. Change sanction/approved and in project delivery |  | ASR – AS20180277 ENGIE Enhanced Portfolio shipper pack (VOL) | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-30 | No Date | 2018-05-25 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4638 | 2. Change sanction/approved and in project delivery |  | ASR – NGS Asset AS20180274 | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-03-26 | Greg Causon | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-06-29 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 18: Provision of User Reports and Information | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4653 | 1. Start-Up (Progressing through change governance) |  | National Grid Transmission iConversion Project | CR (ASR) | LIVE | B2 - Awaiting ME/Data Office/MR HLE quote | 25.23% |  |  | T & SS | 2018-04-24 | Greg Causon | Emma Rose |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-09-01 | Gemini | Other | 30-60 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | TRUE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
3667a | 1. Start-Up (Progressing through change governance) |  | Provision of Prospective Formula Year AQ/SOQ and Historic RAQ to Proposing Users | CP | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 37.24% |  |  | Data Office | 2018-04-04 | James Rigby | Charlie Haley |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-12-01 | ISU | SPA | 60-100 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 5: Metered Volume and Metered Quantity | TRUE | FALSE | One | TRUE | Medium | FALSE | FALSE | No Date | 2018-04-11
4675 | 1. Start-Up (Progressing through change governance) |  | Digital signage Links for Birst Connectivity | CR (Internal) | LIVE | B1 - Start Up In Progress (Awaiting PAT/RACI) | 22.22% |  |  | Data Office | 2018-05-17 | Jo Duncan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-30 | No Date | 2018-06-30 | Birst | Other | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4757 | 1. Start-Up (Progressing through change governance) |  | UIG Issues: Read Performance and WAR Band Reports for Ofgem | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 21.02% |  |  | Data Office | 2018-09-05 | Fiona Cottam | Jo Duncan |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | BW | No Process | 0-30 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | TRUE | High | FALSE | FALSE | No Date | No Date
3457 | 3. Change delivered, awaiting closure approval/sign-off |  | Solution to meet the obligations of UNC MOD 425V & UNC MOD455 | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-08-28 | Joanna Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2015-07-09 | 2015-07-09 | 2000-02-02 | ISU | SPA | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 1: Manage Supply Point Registration | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | 2015-01-19 | 2014-09-03
4110 | 3. Change delivered, awaiting closure approval/sign-off |  | Creation of a Service to Release Domestic Consumer Data to W’s & TPI’s | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | T & SS | 2016-10-12 | Jo Ferguson | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2017-07-31 | 2017-07-31 | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | Five to Twenty | FALSE | Medium | FALSE | FALSE | No Date | No Date
3390 | 3. Change delivered, awaiting closure approval/sign-off |  | Billing History by all NTS capacity / commodity related charges (2003 - 2013) | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-05-16 | Sean McGoldrick | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2014-10-08 | 2014-10-08 | 2000-02-02 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 8: Credit Risk Management (including Cash Collection) and Management of Neutrality Accounting Processes | FALSE | FALSE | Two to Five | FALSE | Medium | FALSE | FALSE | No Date | No Date
3428 | 3. Change delivered, awaiting closure approval/sign-off |  | Correction of CWV data on the National Grid Operational website as a result of incorrect weather flows for NE LDZ | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-06-18 | Joanna Ferguson | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2014-06-23 | 2014-06-23 | 2000-02-02 | ISU | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 15: Demand Estimation | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4009 | 3. Change delivered, awaiting closure approval/sign-off |  | Billing History by all NTS capacity / commodity related charges (applicable dates in 2014 to Nexus implementation) | CP | LIVE | F2 - CCR awaiting ChMC approval | 21.02% |  |  | T & SS | 2016-04-12 | Beverley Viney | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2017-07-19 | 2017-07-19 | 2016-06-30 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4043 | 3. Change delivered, awaiting closure approval/sign-off |  | DN Sales Outbound Services | CP | LIVE | F1 - CCR/Closedown document in progress | 27.03% |  |  | T & SS | 2016-05-26 | Chris Warner | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-07-31 | 2018-06-29 | 2016-10-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 19: Network Operator and User Relationship Management | FALSE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4149 | 2. Change sanction/approved and in project delivery |  | NG Gateway Migration | CP | LIVE | D1 - Change in delivery | 27.03% |  |  | T & SS | 2016-11-28 | Beverley Viney | Rachel Addison |  |  | Third Party SI / Service Provider |  | 2018-10-15 | No Date | 2018-03-31 | Other | Other | 100+days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 19: Network Operator and User Relationship Management | FALSE | FALSE | One | FALSE | High | FALSE | FALSE | No Date | 2017-07-19
4376 | 2. Change sanction/approved and in project delivery |  | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | CP | LIVE | D1 - Change in delivery | 19.22% |  |  | T & SS | 2017-09-22 | Chris Gumbley/Darren Lond | Nicola Patmore |  |  | Third Party SI / Service Provider |  | 2018-11-18 | No Date | 2019-01-01 | ISU | Invoicing | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | One Market Participant | FALSE | TRUE | FALSE | FALSE | FALSE | FALSE | Service Area 7: NTS Capacity / LDZ Capacity / Commodity / Reconciliation / Ad-Hoc Adjustment and Energy Balancing Invoices | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2017-10-12
4550 | 1. Start-Up (Progressing through change governance) |  | Gemini Re-platform | CP | LIVE | C1 - Delivery Business Case/BER in progress | 9.009% |  |  | T & SS | 2017-12-04 | Phil Hobbins | Hannah Reddy |  |  | Third Party SI / Service Provider |  | 2020-01-01 | No Date | 2020-01-01 | Gemini | No Process | 60-100 days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | 2017-12-13
4632 | 2. Change sanction/approved and in project delivery |  | Analysis for Gemini Enhancements | CP | LIVE | D1 - Change in delivery | 25.23% |  |  | T & SS | 2018-03-19 | Celine Reddin/Beverley Viney | Hannah Reddy |  |  | Third Party SI / Service Provider |  | 2018-10-31 | No Date | 2018-09-20 | Gemini | Other | 30-60 days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 20: UK Link Gemini System Services | FALSE | FALSE | One | FALSE | High | FALSE | FALSE | 2018-05-09 | 2018-04-11
3151.1 | 3. Change delivered, awaiting closure approval/sign-off |  | Business to Xoserve to Business File Transfer Capability | CP | LIVE | F1 - CCR/Closedown document in progress | 21.02% |  |  | T & SS | 2014-01-16 | Lee Chambers | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-09-29 | 2014-09-29 | 2014-04-01 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
3143 | 2. Change sanction/approved and in project delivery |  | COR3143 - Decommission XFTM & Server Farm & re-direct NG files Phase 1 | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | Data Office | 2013-08-06 | Khawar Ahmed | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-08-31 | No Date | 2015-10-27 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
3447 | 2. Change sanction/approved and in project delivery |  | COR3447 - XP1 Decommissioning | CP | LIVE | D1 - Change in delivery | 21.02% |  |  | Data Office | 2014-07-08 | Chris Fears | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-08-31 | No Date | 2000-02-02 | Other | Other | 31-100days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4216 | 3. Change delivered, awaiting closure approval/sign-off |  | API Platform Implementation | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | Data Office | 2017-02-03 | Gareth Hepworth | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-06-20 | 2018-06-20 | 2017-12-10 | BW | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4349 | 2. Change sanction/approved and in project delivery |  | Control-M/EM, Server and agent upgrade for Gemini and CMS | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-08-18 | Annie Griffith | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-12-29 | No Date | 2018-07-31 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4324 | 2. Change sanction/approved and in project delivery |  | Checkpoint Hardware Upgrade | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-06-29 | Chris Fears | Emily Pickard |  |  | Third Party SI / Service Provider |  | 2018-08-26 | No Date | 2017-12-01 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4325 | 2. Change sanction/approved and in project delivery |  | Cisco Security Upgrade | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-06-29 | Chris Fears | Emily Pickard |  |  | Third Party SI / Service Provider |  | 2018-08-26 | No Date | 2018-02-02 | Other | Other | 31-100days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4562 | 2. Change sanction/approved and in project delivery |  | Testing Lifecyle Improvements | CR (Internal) | LIVE | D1 - Change in delivery | 22.22% |  |  | T & SS | 2017-12-18 | Andy Simpson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2018-12-31 | No Date | 2018-03-31 | Other | No Process | No Delivery Effort | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4440 | 2. Change sanction/approved and in project delivery |  | Npower MPRN Information report | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2016-08-04 | Emma Partlett | Jo Duncan |  | UKLP IADBI246 | Xoserve Resource |  | 2018-09-28 | No Date | 2018-04-27 | BW | Other | 31-100days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
2831.2 | 3. Change delivered, awaiting closure approval/sign-off |  | DSP Gateway Mechanism Analysis & Design | CP | LIVE | F1 - CCR/Closedown document in progress | 25.23% |  |  | T & SS | 2012-11-21 | Joanna Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-04-16 | 2014-04-16 | No Date | Other | Other | 31-100days | FALSE | [5 empty] | ChMC endorsed Change Proposal | All UK Gas Market Participants | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
3151 | 3. Change delivered, awaiting closure approval/sign-off |  | Communications Link Solution for Provision of Smart Meter Data from iGT's to Xoserve | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 22.22% |  |  | T & SS | 2013-08-15 | Lee Chambers | Jon Follows |  |  | Third Party SI / Service Provider |  | 2014-09-01 | 2014-09-01 | 2014-04-30 | ISU | Other | 100+days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
2831.4 | 3. Change delivered, awaiting closure approval/sign-off |  | Smart Metering UNC MOD 430: DCC User Gateway Network | CP | LIVE | F1 - CCR/Closedown document in progress | 9.009% |  |  | T & SS | 2014-03-13 | Jo Ferguson | Jon Follows |  |  | Third Party SI / Service Provider |  | 2016-09-22 | 2017-09-22 | No Date | ISU | Other | 100+days | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date
4635 | 2. Change sanction/approved and in project delivery |  | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service (Number) | CP (Non System Impacting) | LIVE | D1 - Change in delivery | 13.21% |  |  | T & SS | 2018-03-21 | Charlie Hayley | Charlie Haley |  |  | Xoserve Resource |  | 2018-09-01 | No Date | No Date | Other | Portal | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | 2018-06-13
4647 | 2. Change sanction/approved and in project delivery |  | IS Operations - Service Management Performance Birst Dashboards | CR (Internal) | LIVE | D1 - Change in delivery | 24.62% |  |  | Data Office | 2018-04-13 | Luke Moise | Jo Duncan |  |  | Xoserve Resource |  | 2018-08-31 | No Date | 2018-05-15 | Birst | Other | 0-30 days | TRUE | Xoserve | Daily | One | Low | 2018-05-15 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4650 | 1. Start-Up (Progressing through change governance) |  | M-Number DVD Automation | CR (Internal) | LIVE | A5 - CP in capture with DSG | 33.63% |  |  | Data Office | 2018-04-17 | Mark Pollard | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-09-28 | No Date | 2018-05-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | All UK Gas Market Participants | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | TRUE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4656 | 2. Change sanction/approved and in project delivery |  | Customer Instant Feedback Mechanism for KVI Reporting | CR (Internal) | LIVE | D1 - Change in delivery | 27.03% |  |  | T & SS | 2018-04-24 | Adam Jones | Dene Williams |  |  | Third Party SI / Service Provider |  | 2018-09-01 | No Date | 2018-06-01 | Other | Other | 30-60 days | TRUE | Xoserve | Daily | Two to Five | Low | 2018-12-28 | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4697 | 2. Change sanction/approved and in project delivery |  | Amendment Invoice - High Financial Values report from BIRST | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | Data Office | 2018-06-06 | Dan Donovan | Jo Duncan |  |  | Xoserve Resource |  | 2018-09-28 | No Date | 2018-07-31 | Birst | Invoicing | 0-30 days | TRUE | Xoserve | Monthly | One | Medium | 2019-02-26 | Xoserve Internal CR (business improvement initiative) | One Market Group | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4700 | 1. Start-Up (Progressing through change governance) |  | Provision of data to Suppliers via API | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | Data Office | 2018-06-18 | Mark Pollard | Simon Harris |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-28 | BW | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Group | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | TRUE | FALSE | None (Xoserve internal initiative) | FALSE | High | FALSE | FALSE | No Date | No Date
4710 | 2. Change sanction/approved and in project delivery |  | ASR – POW to be added to Eon Reports | CR (ASR) | LIVE | D1 - Change in delivery | 25.23% |  |  | Data Office | 2018-07-02 | Greg Causon | Charlie Haley |  |  | Xoserve Resource |  | 2018-08-24 | 2018-08-24 | 2018-08-07 | BW | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | One | FALSE | Medium | FALSE | FALSE | No Date | No Date
4747 | 1. Start-Up (Progressing through change governance) |  | Npower Smart Meter Upgrade Notification Report (AS20180412) | CR (ASR) | LIVE | A9 - Internal change progressing through capture | 31.23% |  |  | Data Office | 2018-08-24 | Greg Causon | Charlie Haley |  |  | Xoserve Resource |  | No Date | No Date | 2018-11-01 | Other | Other | 0-30 days | FALSE | [5 empty] | Additional or 3rd Party Service Request | One Market Participant | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 24: Additional Service Request or Third Party Request | FALSE | FALSE | One | TRUE | Medium | FALSE | FALSE | No Date | No Date
4748 | 1. Start-Up (Progressing through change governance) |  | Birst Dashboard Development for Process Federation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 22.22% |  |  | Data Office | 2018-08-28 | Susan Helders | Jo Duncan |  |  | Xoserve Resource |  | No Date | No Date | 2018-09-15 | Birst | Other | 0-30 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4552 | 1. Start-Up (Progressing through change governance) |  | ‘Front end’ development of new Company Intranet | CR (Internal) | LIVE | C1 - Delivery Business Case/BER in progress | 22.22% |  |  | T & SS | 2017-12-05 | Sarah Bridge | Emma Rose |  |  | Third Party SI / Service Provider |  | 2018-11-30 | No Date | 2017-06-30 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Xoserve Only | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Low | FALSE | FALSE | No Date | No Date
4625 | 3. Change delivered, awaiting closure approval/sign-off |  | Retrospective - Change of Supply API Prototype Development for British Gas | CR (Internal) | LIVE | F1 - CCR/Closedown document in progress | 15.62% |  |  | Data Office | 2018-02-05 | Iain Snookes | Mark Pollard |  |  | Third Party SI / Service Provider |  | 2018-08-30 | 2018-08-30 | 2018-12-31 | Other | Other | 60-100 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | One Market Participant | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 23: Internal | TRUE | FALSE | One | FALSE | Low | FALSE | FALSE | No Date | No Date
4633 | 2. Change sanction/approved and in project delivery |  | New website for Xoserve | CR (Internal) | LIVE | D1 - Change in delivery | 19.82% |  |  | T & SS | 2018-03-19 | Sarah Bridge | Andrew Poolton |  |  | Third Party SI / Service Provider |  | 2019-01-31 | No Date | 2018-12-31 | Other | Other | 100+ days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 23: Internal | FALSE | FALSE | None (Xoserve internal initiative) | FALSE | Medium | FALSE | FALSE | No Date | No Date
4695 | 2. Change sanction/approved and in project delivery |  | Investigating causes and contributors to levels and volatility of Unidentified Gas | CP (Non System Impacting) | LIVE | D1 - Change in delivery | 43.24% |  |  | Data Office | 2018-06-05 | Rachel Hinsley | Charlie Haley |  |  | Third Party SI / Service Provider |  | No Date | No Date | 2018-07-31 | Other | Other | 100+ days | FALSE | [5 empty] | ChMC endorsed Change Proposal | Multiple Market Groups | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | Service Area 3: Record/submit Data in Compliance with UNC | FALSE | FALSE | One | TRUE | High | FALSE | FALSE | 2018-06-13 | 2018-06-13
4626.1 | 2. Change sanction/approved and in project delivery |  | Provision of an alternative Consumer Enquiry Service (MNumber) PHASE ONE Web Portal Implementation | CR (Internal) | LIVE | D1 - Change in delivery | 27.63% |  |  | Data Office | 2018-03-09 | Dave Acker | Charlie Haley |  |  | Third Party SI / Service Provider |  | 2018-09-01 | No Date | 2018-08-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4626.2 | 1. Start-Up (Progressing through change governance) |  | Provision of an alternative Consumer Enquiry Service (Mnumber) - PHASE TWO Non-Web Portal Implementation | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 27.63% |  |  | T & SS | 2018-03-09 | Dave Ackers | Dene Williams |  |  | Third Party SI / Service Provider |  | 2019-07-31 | No Date | 2018-08-01 | Other | Other | 30-60 days | FALSE | [5 empty] | Xoserve Internal CR (business improvement initiative) | Multiple Market Groups | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | Service Area 16: Provision of Supply Point Information Services and Other Services Required to be Provided Under Condition of the GT Licence | FALSE | FALSE | Two to Five | FALSE | High | FALSE | FALSE | No Date | No Date
4626.3 | 1. Start-Up (Progressing through change governance) |  | Provision of an alternative Consumer Enquiry Service (MNumber) PHASE THREE Web Portal xEnhancements | CR (Internal) | LIVE | A9 - Internal change progressing through capture | 9.009% |  |  | Data Office | 2018-08-13 | Dave Ackers | Charlie Haley |  |  | Third Party SI / Service Provider |  | No Date | No Date | No Date | No Application | No Process | No Delivery Effort | FALSE | [5 empty] | No Change Driver | No Change Beneficiary | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | No Change Improvement Scale | FALSE | FALSE |  | FALSE |  | FALSE | FALSE | No Date | No Date