## Slide 1: Amendment Invoice Task Force Progress Report
10th October 2018

## Slide 2: Background
Amendment Invoice Issues – What’s the issue?
  A number of functional defects and integration issues are causing presentation issues and charge calculation issues within the AMS invoice, resulting in presentation issues where data is missing or incorrect within the supporting data and incorrect charge calculations which are excluded from the invoice until a fix is deployed.
  Delays in issuing the amendment invoice supporting information files and additional correction files required to enable customers to validate the charges issued
What is Xoserve doing about the issues?
  A taskforce consisting of business process and technical experts are working together to fix the issues
  Resources have been increased for both the technical team and the business. The team will focus on defect resolution, resolving exclusions and releasing reconciliation charges
  Defect and exclusion resolution plans have been produced and will be tracked, these will be published
  From October an update on progress will be provided to Contract Management Committee (CoMC) and Change Management Committee (ChMC) monthly

## Slide 3: Task Force Focus Areas (Workstreams)
There are 4 Primary Focus areas (Streams of work)
  Business as Usual (BAU)
    Maintaining the quality of the invoice, and improving the workaround process for issuing supporting AML and ASP files.
  Technical Design Review and Root Cause Analysis (RCA)
    Detailed technical review to identify any process improvements, and understand the root cause of functional defect
  Defect Resolution
    Managing the resolution of defects associated with the Amendment invoice and supporting files, including data correction and release of reconciliation charges (exclusions).
  Customer Engagement and support
    Provide regular updates to Customers
    Engage with Customers to understand the impact that the issue is having on each organisation and work together to find ways to provide additional support.

## Slide 4: Amendment Task Force: dashboard
Overall RAG status:*
R
*R = programme objectives at risk and no agreed plan to resolve; A = programme objectives at risk, with agreed plan in place to resolve; G = on track.
Executive Summary | RAG | 
The Amendment Invoice Taskforce is currently at Amber status due to the number of defects outstanding and the volume of exclusions. Issues also experienced with the July and August invoices. The resources of the team have increased, both technical and business, to resolve the defects and release the reconciliation charges currently excluded from the invoice. The scope of the taskforce includes 32 defects as at 1st September 2018 and all exclusions associated with the defects. Aim of the team is to resolve the defects by end of November 2018 and release reconciliation charges in the November invoice issued in December. Any defects identified after 1st September will continue to be prioritised and resolved as BAU. A full time Customer Liaison Manager has been assigned to ensure customers are actively updated with progress and involved with solution options. Reporting will be provided monthly at DSC committee meetings and published on Xoserbve.com. | RCA | A
 | Defects & Exclusion | G
 | BAU | A
Progress since last month - key milestones | Workstream | Date | Status
Phase 1 Exclusions Plan – Initial Analysis & Profiling completed | Defect & Exclusions | 1409/18 | Completed
Phase 2 Exclusions Plan – Pattern Analysis & Fix Planning completed | Defects & Exclusions | 28/09/18 | Completed
Plan Completed for Defect Resolution | Defects & Exclusions | 14/09/18 | Completed
Exclusion Analysis (Procedure Update) | RCA | 28/09/18 | Delayed 3 weeks
Deploy fixes for 6 defects | Defect & Exclusions | 30/09/18 | Completed
Priorities for next month – key milestones | Workstream | Date | Status
Exception Analysis (Procedure Update) | RCA | 05/10/19 19/10/18 | In progress
AML Scheduling Plan | RCA | 05/10/18 | In progress
POC for single AML/ASP file Plan | RCA | 05/10/18 | In progress
Automation of Offline ASP Mismatch files | RCA | 12/10/18 | In progress
UBID Phase 2 Deployment | RCA | 05/10/18 | In progress
Exclusion Analysis (Procedure Update) | RCA | 28/09/18 19/10/18 | In progress
Deploy fixes for 9 defects | Defect & Exclusions | 31/10/18 | In progress
Release charges for Excluded MPRNs (defects deployed) | Defect & Exclusions | 31/10/18 | In progress

## Slide 5: Amendment Invoice – Resolution Plan
Sep
Oct
Nov
Dec
Jan
Feb
2018
2019
Defects
Eliminate Backlog (32 @ 1/9)
BAU @ M+1
Exclusions
Eliminate Backlog to 31/10
BAU @ M+1
Offline Automation
ASP Correction file
Design & RCA
UBID P1
P2
Benefits Delivery
Mismatch reduction will be measured & reported, visible for Sept Invoice Cycle
Accelerated Offline file production + backlog reduction
1
1
2
2
3
3
Mismatch & Exclusion reduction, will be measured & reported
4
4
All new defects fixed by end of following month (M+1)
Solution Work Packages
5
5
Number of system, scheduling and procedure changes – delivering final set of mismatch fixes

## Slide 6
  Task Force Workstream Updates

## Slide 7: BAU Stream Update
Area | Action | Progress
ASP Mismatch | Reduce the delay issuing mismatch files Remove manual error within the files | Backlog of files is reducing slowly. Due to an increase in class 3 activity, the size of the ASP file has increased for some customers. This has created additional work to process the data and resulted in delays issuing the mismatch files From October (September billing period), the ASP correction files will be issued prior to invoice payment due date (with the exception of some customers who receive larger files, these customers will be contacted directly)
July Amendment Invoice contained incorrect Unidentified Gas Reconciliation charge | Identify reason for the error Implement process improvement | Error was due to a manual error; screen allows a User to select an option to re-calculate the charge. This is a requirement but should only be used in exceptional circumstances The screen has been updated to include a warning message if the option is selected
Delay in issuing August AML and Correction files | Carry out lessons learnt Implement and document any process improvements identified Monitor | Issue with the delay caused by a manual process not carried out before the files were produced All manual processes are being documented to ensure they are not missed in the future Plan to automate

## Slide 8: RCA Stream Actions
Activity | Target Completion Date | Benefits | Target Status
Package 3A: Additional Analysis: Tools and Class 3 | 02/11/2018 | Additional analysis required before benefits are understood. Areas were identified during RCA work as potential reasons for mismatches | On target
Package 3B: Additional Analysis: DM Rec Interface | 08/02/2019 |  | On target
Package 3C: Additional Analysis: AML Extraction Process | 11/01/2019 |  | On target
Package 4A: Exception Analysis: Procedure Update | 05/10/2018 19/10/2018 | Process improvements to ensure speedier closure of exceptions to release charges on the invoice and reduce mismatches | At Risk
Package 4B: Exclusion Analysis: Procedure Update | 28/09/2018 19/10/2018 |  | At Risk
Package 5A: Service Improvement CRs: Automation and Reporting | 28/12/2018 | Automated reporting internally to enable validation & invoice analysis prior to issue | On target
Package 5B: Service Improvement CRs: Automation and Reporting | 18/01/2019 |  | On target
Package 6: Code Review | 22/02/2019 | Identify any further improvements areas to reduce mismatches | On target
Package 7: AML Scheduling Plan | 05/10/2018 | Delivery of file before payment due date | On target
Package 8: PoC for single AML/ASP file | 05/10/2018 | Merge of files | On target
SAP Automation of Offline ASP Mismatch files | 12/10/2018 | Earlier delivery of files | On target
UBID Phase 1 | 25/08/2018 | Reduction in mismatches | Complete
UBID Phase 2 | 05/10/2018 |  | On target

## Slide 9: Defect and Exclusions Resolution Plan
Defect Resolution Plan as at 30th September 2018
Exclusion Resolution Plan as at 30th September 2018
  Please note this is a draft document.
These documents will be updated, tracked and published weekly on Xoserve.com

## Slide 10: Customer Engagement - Proposals
Monthly progress updates provided to Contract Management Committee (CoMC) and Change Management Committee (ChMC)
Updated plans published on Xoserve.com
DSG will be used to discuss and agree any solution options
Customer Liaison Manager will continue to be the first port of call for customers