## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Description Change to the C41 for Clarification | 2102.1 - RJ - ES | 2018-10-12 | 2018-10-26 | 2018-10-29 | X |  |  |  |  | 2123 - RJ - PO | 2018-11-07 | Release 3 - 2nd November 2018 | We received one representation which approved this change in principle. This is an administative change, and Xoserve will ask ChMC to approve this change to be implemented as part of Release 3.

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 23rd July
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | ANT File Format Change Pack | 2074.1 - RJ - RH | 2018-09-14 | 2018-09-28 | 2018-10-02 | X |  |  |  |  | 2090 - RJ - ES | 2018-10-10 | 2018-11-02 | 1 representation comment received in support

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
EFT Application Upgrade | EFT | November (Expected Late November) | 03:00:00 GMT | November (Expected Late November) | 07:00:00 GMT | Version application upgrade of the Enhanced File Transfer (EFT). All inbound and outbound files during this window will not be processed until EFT has been released at 07:00 UK GMT. | 2018-11-07
COR4349: Control M Agent Upgrade for Production Environments | Gemini | 2018-11-11 | 05:00:00 GMT | 2018-11-11 | 07:00:00 GMT | There will be an extended Gemini service outage following the Gemini maintenance window.The normal BAU maintenance window remains from 03:00 to 05:00. | 2018-11-07