## Slide 1: Change Management Committee – June 2019 Update
10th October 2018

## Slide 2: June 19 Headlines
All 9 changes allocated to June 2019 have now completed HLSOIAs and Solution Option Pack Assessment
The next steps are to seek approval for the June 19 scope at ChMC on October 10th
An extraordinary ChMC is required on October 17th to seek approval of the EQR for the progression of the Detailed Design
Timeline of Next Steps Outlined Below:
1
10th Oct
17th Oct
9th Nov
Change Packs Issued to Customers
ChMC – Scope Approval
ChMC – EQR Approval
2
3
4
Date TBC
First Customer Awareness Day for June 19

## Slide 3: Change Index
June 19 | XRN | Change Title | Complexity | Impacted Parties | Target Close-Out Date for Solution Packs | Target ChMC Session to Confirm Preferred Option | Current Position
 | 4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date | Medium | Xoserve | Closed | 10/10/18 | Proposed for June 19, Xoserve exploring whether the change could be delivered earlier as part of a MR, or whether the change could be postponed until Nov 19 to allow for greater resource availability to focus on XRN4665 EUC.
 | 4690 | Actual read following estimated transfer read calculating AQ of 1 | Medium | Shippers | Closed | 10/10/18 | Proposed for an earlier Minor Release delivery, in DSG, on October 2nd. Seeking decision at Oct 18 ChMC .
 | 4687 | PSR updates for large domestic sites | Medium | Shippers | Closed | 10/10/18 | Proposed for June 19 – seeking decision at Oct 18 ChMC
 | 4691 | CSEPs: IGT and GT File Formats (CGI Files) | High | DN | 05/10/18 | 10/10/18 | Proposed for June 19 – seeking decision at Oct 18 ChMC
 | 4692 | CSEPs: IGT and GT File Formats (CIN Files) | High | DN | 05/10/18 | 10/10/18 | Proposed for June 19 – seeking decision at Oct 18 ChMC
 | 4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN. | High | DN | 05/10/18 | 10/10/18 | Proposed for June 19 – seeking decision at Oct 18 ChMC
 | 4694 | CSEPs: IGT and GT File Formats (Create new data validations ) | High | DN | 05/10/18 | 10/10/18 | Proposed for June 19 – seeking decision at Oct 18 ChMC
 | 4676 | Reconciliation issues with reads recorded between D-1 to D-5. | Low | Xoserve | ?? | 10/10/18 | Proposed for June 19, Xoserve exploring whether the change could be delivered earlier as part of a MR, or whether the change could be postponed until Nov 19 to allow for greater resource availability to focus on XRN 4665 EUC.
 | 4044 | Extension of ‘Must Read’ process to include Annual Read sites | Low | Cadent Gas | ?? | 10/10/18 | Proposed for June 19 – seeking decision at Oct 18 ChMC

## Slide 4: Evolution of June’19 Scope
XRN | Change Title
4642 | Address Maintenance Solution
4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date
4687 | PSR updates for large domestic sites
4690 | Actual read following estimated transfer read calculating AQ of 1
4691 | CSEPs: IGT and GT File Formats (CGI Files)
4692 | CSEPs: IGT and GT File Formats (CIN Files)
4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN.
4694 | CSEPs: IGT and GT File Formats (Create new data validations )
4676 | Reconciliation issues with reads recorded between D-1 to D-5.
4679 | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone
4044 | Extension of ‘Must Read’ process to include Annual Read sites
4645 | The rejection of incrementing reads submitted for an Isolated Supply Meter Point (RGMA flows)
12 Changes Initially Earmarked for June 19
August 2018 ChMC
XRN | Change Title
4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date
4690 | Actual read following estimated transfer read calculating AQ of 1
4687 | PSR updates for large domestic sites
4691 | CSEPs: IGT and GT File Formats (CGI Files)
4692 | CSEPs: IGT and GT File Formats (CIN Files)
4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN.
4694 | CSEPs: IGT and GT File Formats (Create new data validations )
4676 | Reconciliation issues with reads recorded between D-1 to D-5.
4044 | Extension of ‘Must Read’ process to include Annual Read sites
September 2018 ChMC
Scope Reduced to 9 Changes in Sept, due to:
4642: Proposed to move to November 19 as the requirements were not mature enough to progress the HLSOIA
4645: Proposed to move to November 19 as the requirements were not mature enough to progress the HLSOIA.
4679: Proposed to move to November as the requirements were still being ratified by customers.
XRN | Change Title
4670 | Reject a replacement read, where the read provided is identical to that already held in UK Link for the same read date
4676 | Reconciliation issues with reads recorded between D-1 to D-5.
4687 | PSR updates for large domestic sites
4691 | CSEPs: IGT and GT File Formats (CGI Files)
4692 | CSEPs: IGT and GT File Formats (CIN Files)
4693 | CSEPs: IGT and GT File Formats Files Affected: CIC, CIR, CAI, CAO, DCI, DCO, CIN, CCN, CUN.
4694 | CSEPs: IGT and GT File Formats (Create new data validations )
4044 | Extension of ‘Must Read’ process to include Annual Read sites
Potential Finalised June 19 Scope – To be Agreed at October 2018 ChMC
Scope Reduced to 8 Changes in Oct, due to:
4690: Potential removal from June 19, in order to be delivered earlier via a Minor Release – Seeking ChMC decision.