## Slide 1: Change Assurance Dashboard
November 2018

## Slide 2: Change Assurance Dashboard
Assurance status | Numbers
Complete | 10
Underway | 1
Scoping | 3
At Risk | 0
Chart: Priority findings by Project
| R2 | R3 | TU N&D | TU ERP | Strategic Hosting | Gemin GBC A
CA4 | 3 | 4 | 2 | 0 | 0 | 1
CA3 | 3 | 4 | 6 | 9 | 7 | 2
CA2 | 0 | 7 | 17 | 18 | 12
CA1 | 0 | 1 | 3 | 4 | 5
Summary Comments
The majority of our work this quarter has been assurance of internal projects and programmes i.e. TransformUs ERP & D&N, Strategic Hosting
Assurance Health check completed got Gemini GB Charging Part A.
Assurance Health check underway for R3, will be reported at the next meeting
Contributed to CSS Bid response
Planned next quarter: MIS delivery framework review, Pre-Go-live Check R3 Cadent Billing, Gemini GB Charging Part B health check, set-up of assurance regime for CSSC and further health checks on internal projects
Chart: Findings Status by Project
| Open | Closed
R2 | 4 | 2
R3 | 0 | 16
TU D&N | 22 | 8
TU ERP | 12 | 19
Strat Host | 16 | 8
GBC A | 0 | 3

## Slide 3: Gemini GB Charging Part A Summary Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | October 2018 | Gemini GB Charging Part A – Health check | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Other | CA1 CA2 CA3 CA4 | Gemini GB Charging Part A is planned to deliver five changes on 18th November 2018, with Part B delivering a greater and more complex scope delivering 6th September 2019. The assessment covered Part A only with Part B being assessed in April 2019 The project is running to plan and has passed all of its planned stage gates successfully with well documented evidence of success. The governance and control framework is well established and maintained, with only minor observations in relation to Assumptions and Dependencies The project is being delivered by an experienced team, the majority of who have successfully delivered previous Gemini releases. This applies equally to the Xoserve, Wipro and NG resources. Good collaboration between all parties has also been a key factor in the progress made to date. The plans are clear, generally well-structured and kept up to date. There is a minor finding in relation to the utilisation of dependencies in the plan Customer feedback has been positive and they are all confident that the project should successfully deliver its outcomes Testing is well planned, and supported by a clear and approved strategy. System Testing, Integration Testing and UAT (to date) have had very low defect rates (below1%) Implementation readiness is on track. In addition the team has continued to build on the improvements to the delivery approach that were started following EU Phase 2; introducing further changes, in collaboration with NG transmission, Wipro and NG IS, which have added value.
2
1

## Slide 4: Change Assurance reporting RAYG definitions
Categorisation of delivery risk is as follows:
Red : indicates issues that could entail significant risk to the success of the Programme. Remedial action fundamental to successful outcome of programme, should be implemented as soon as possible;
Amber : indicates issues that could entail significant risk to the success of the Programme. Remedial action important to programme outcomes, should be implemented as soon as practical;
Yellow : indicates issues within could entail risk to the success of the Programme, but this risk is low Remedial action a good to have for the programme, implementation advised;
Green : indicates very minor to no issues, entailing minimal risk to the success of the Programme. Improvement would reduce risk, but the weakness is unlikely to undermine the success of the programme

## Slide 5: Change Assurance Findings Severity
Category | Description
CA1 | High risk of impacting successful delivery and achieving outcomes – finding needs to be addressed in order for project to succeed
CA2 | Moderate risk of impacting successful delivery and achieving of outcomes – finding needs to be addressed in order to protect time, cost and quality
CA3 | Low risk of impacting successful delivery and outcomes – consider fixing in project and apply to future projects
CA4 | Minor impact to achieving delivery or outcomes – build in as a lessons learnt for efficient and effective delivery for future projects