## Slide 1: UIG Task Force Progress Report
DSC ChMC 7/11/18

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a task force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force Dashboard
  POAP
  Executive Summary of Sprint 3
  Post Sprint 3: Areas Of Investigation (placeholder)
  Shipper dashboards (placeholder)
  Findings template
  Reporting on budget

## Slide 3: Plan on Page
Delivery team milestone
Advanced Analytics
I
DSC ChMC governance
C
Completed activity
 | August |  |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  | 
 | 01/08 | 06/08 | 13/08 | 20/08 | 27/08 | 03/09 | 10/09 | 17/09 | 24/09 | 01/10 | 08/10 | 15/10 | 22/10 | 29/10 | 05/11 | 12/11 | 19/11 | 26/11 | 03/12 | 10/12 | 17/12
Develop Investigation Log
Define functional requirements for initial dashboard
Issue analysis and tracking (Investigation Tracker updated and published weekly)
Identify initial reporting inputs and outputs
Customer Engagement Manager Day 1
I
12/09 DSC ChMC
I
10/10 DSC ChMC
I
08/08 DSC ChMC
Develop Industry Data Tree
Develop Data Dictionary
C
03/09 Kick-off workshop with Vendor
Finalise inputs to data hamper
Develop stakeholder comms & engagement plan
Confirm UIG points of contact & allocate Relationship Mgrs
C
Customer Advocate
Briefing Session
Develop and manage shipper action plans (linked to Investigation Log)
Sprint 1
Sprint 2
Sprint 3
22/10 Action plan template developed
Establish units of measurement & glide path
Mobilisation activity completed
C
C
24/8 Data Package 1 to vendor
03/9 Data Package 2 to vendor
14/9 Data Package 3a to vendor
27/9 Data Package 3b to vendor
Sprint 4
Sprint 5
Sprint 6
05/10 Initial specification complete
C
C
I
07/11 DCS ChMC
I
12/12 DSC ChMC
C
27/08 Sprint 1 Exec Summary
C
C
C
C
12/10 Publish Industry Data Tree
C
C
C
C
Sprints 4-6 to continue at the same pace and follow directly after the initial sprints to maintain momentum and ensure existing team resources are fully utilised. A 14-day stand-down period applies at any time.
10/10 Agree appropriate forum for creation of shipper dashboards
C
C
12/10 Sprint 2 Exec Summary
I
02/10 Extraordinary DSC ChMC
I
TBC Extraordinary DSC ChMC
C
25/10 Sprint 2 Exec Summary

## Slide 4: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Workstream | Date | Status
Proposed dashboard specification complete | Customer | 05/10 | C
Complete Sprint 2 | AA + IA | 08/10 | C
Sprint 3 Kick off Workshop / Deliverable prioritisation | AA + IA | 08/10 | C
Agree appropriate forum for creation of shipper dashboards | Customer | 10/10 | C
Publish Data Tree | AA + IA | 12/10 | C
Publication of Sprint 2 Executive Summary | AA + IA | 12/10 | C
Publication of Sprint 3 Executive Summary | AA + IA | 25/10 | C
Priorities for next month – key milestones | Workstream | Date | Status
Attend UIG working group - dashboard | IA & AA | 31/10 | G
Findings report published | IA & AA | 08/10 | G
Publication of Sprint 4 Executive Summary | IA & AA | 08/10 | G
Publication of Sprint 5 Executive Summary | IA & AA | 22/11 | G
Overall RAG status:*

## Slide 5: Sprint 3 Outcomes And Sprint 4 Areas Of Investigation

## Slide 6: Sprint 3 Outcomes And Sprint 4 Areas Of Investigation

## Slide 7: Sprint 3 Outcomes And Sprint 4 Areas Of Investigation

## Slide 8: Sprint 3 Outcomes And Sprint 4 Areas Of Investigation

## Slide 9: Sprint 4 Further Areas Of Investigation

## Slide 10: Sprint 4 Early View of Findings
  Sprint 4 due to complete Monday 5th November
To be updated post 5th Nov

## Slide 11: Sprint Findings Template

## Slide 12: Shipper Dashboards
  Industry Forum = UIG working group 31/10/18
To be updated post 31/10/18

## Slide 13: Overview Of Taskforce Funding