## Slide 1: Amendment Invoice Task Force Progress Report
ChMC 12th December 2018

## Slide 2: Background
Amendment Invoice Issues – What’s the issue?
  A number of functional defects and integration issues are causing presentation issues and charge calculation issues within the AMS invoice, resulting in presentation issues where data is missing or incorrect within the supporting data and incorrect charge calculations which are excluded from the invoice until a fix is deployed.
  Delays in issuing the amendment invoice supporting information files and additional correction files required to enable customers to validate the charges issued
What is Xoserve doing about the issues?
  A taskforce consisting of business process and technical experts are working together to fix the issues
  Resources have been increased for both the technical team and the business. The team will focus on defect resolution, resolving exclusions and releasing reconciliation charges
  Defect and exclusion resolution plans have been produced and will be tracked, these will be published
  From October an update on progress will be provided to Contract Management Committee (CoMC) and Change Management Committee (ChMC) monthly

## Slide 3: Task Force Focus Areas (Workstreams)
There are 4 Primary Focus areas (Streams of work)
  Business as Usual (BAU)
    Maintaining the quality of the invoice, and improving the workaround process for issuing supporting AML and ASP files.
  Technical Design Review and Root Cause Analysis (RCA)
    Detailed technical review to identify any process improvements, and understand the root cause of functional defect
  Defect Resolution
    Managing the resolution of defects associated with the Amendment invoice and supporting files, including data correction and release of reconciliation charges (exclusions).
  Customer Engagement and support
    Provide regular updates to Customers
    Engage with Customers to understand the impact that the issue is having on each organisation and work together to find ways to provide additional support.

## Slide 4: Amendment Task Force: dashboard
Overall RAG status:*
R
*R = programme objectives at risk and no agreed plan to resolve; A = programme objectives at risk, with agreed plan in place to resolve; G = on track.
Executive Summary | RAG | 
The Amendment Invoice Taskforce is currently at Amber status due to the number of defects outstanding and the volume of exclusions. Issues also experienced with the July and August invoices. The resources of the team have increased, both technical and business, to resolve the defects and release the reconciliation charges currently excluded from the invoice. The scope of the taskforce includes 32 defects as at 1st September 2018 and all exclusions associated with the defects. Aim of the team is to resolve the defects by end of November 2018 and release reconciliation charges in the November invoice issued in December. Any defects identified after 1st September will continue to be prioritised and resolved as BAU. A full time Customer Liaison Manager has been assigned to ensure customers are actively updated with progress and involved with solution options. Reporting will be provided monthly at DSC committee meetings and published on Xoserbve.com. | RCA | R
 | Defects & Exclusion | G
 | BAU | A
Progress since last month - key milestones | Workstream | Date | Status
AML Scheduling Plan Approval | RCA | 20/11/18 | Completed
PoC for single AML File Approval to Proceed | RCA | 20/11/18 | Completed
Release Charges for Excluded MPRNs 35,626K (for defects deployed) | Defect & Exclusions | 30/11/18 | Completed
Deploy fixes for 12 defects | Defects & Exclusions | 30/11/18 | Completed
Exclusion Analysis (Procedure Update) | RCA | 28/09/18 10/11/18 | Completed
Priorities for next month – key milestones | Workstream | Date | Status
Deploy fix for 1 defect | Defects & Exclusions | 31/12/18 | In progress
Exception Analysis (Procedure Update) | RCA | 05/10/19 10/11/18 07/12/18 | In progress
Automation of Offline ASP Mismatch files | RCA | 12/10/18 23/11/18 14/12/18 | In progress
PoC for single ASP File Approval to Proceed | RCA | 31/01/19 | In Progress
Release Charges for Excluded MPRNs 12,186K (for defects deployed) | Defect & Exclusions | 31/12/18 | In progress
Executive Summary | RAG | 
The Amendment Invoice Task Force status will remain at Red. This is due to the UIG reconciliation smear and charge issue. Initially it was thought that July, August & September allocations were incorrect, It has now been confirmed that the UIG reconciliation charges issued on the Amendment Invoice are incorrect going back to October 2017 to the present day. The scope of the taskforce includes 32 defects as at 1st September 2018 and all exclusions associated with the defects. The aim was to resolve the defects by end of November and release reconciliation charges in the November invoice issued in December, however we now have 5 Defects that will be deployed in January 2019 and the reconciliation charges for these defects will be released on the February invoice. Any defects identified after 1st September will continue to be prioritised and resolved as BAU. | RCA | A
 | Defects & Exclusion | A
 | BAU | A

## Slide 5: Amendment Invoice – Resolution Plan
Sep
Oct
Nov
Dec
Jan
Feb
2018
2019
Defects
Eliminate Backlog (32 @ 1/9)
BAU @ M+1
Exclusions
Eliminate Backlog to 31/10
BAU @ M+1
Offline Automation
ASP Correction file
Design & RCA
UBID P1
P2
Benefits Delivery
Mismatch reduction will be measured & reported, visible for October Invoice Cycle
Accelerated Offline file production + backlog reduction
1
1
2
2
3
3
Mismatch & Exclusion reduction, will be measured & reported
4
4
All new defects fixed by end of following month (M+1)
Solution Work Packages
5
5
Number of system, scheduling and procedure changes – delivering final set of mismatch fixes

## Slide 6
  Task Force Workstream Updates

## Slide 7: BAU Stream Update
Area | Action | Progress
ASP Mismatch Files | Reduce the delay issuing mismatch files Remove manual error within the files | The backlog continues to reduce slowly. From October (September billing period), the aim was for the ASP correction files to be issued prior to invoice payment due date, this has not been achievable to date, however Xoserve continue to work on the automated solution. The volume of backlog is reducing each month due to UBID and efficiencies within the billing team. The number of shippers with an ASP file mismatch for October billing period is down to 16 (for September it was 22, August it was 30).
AML correction File (Data Extraction) | Change in the extraction script from SQL to ABAP | This will make the extraction for the AML correction data more efficient and will enable Xoserve to issue the files on time, fully complete and accurate.(previous incomplete files had missing data)

## Slide 8: RCA Stream Actions
Activity | Target Completion Date | Benefits | Target Status
Package 3B: Additional Analysis: DM Rec Interface | 08/02/2019 | Additional analysis required before benefits are understood. Areas were identified during RCA work as potential reasons for mismatches | On target
Package 3C: Additional Analysis: AML Extraction Process | 11/01/2019 |  | On target
Package 4A: Exception Analysis: Procedure Update | 05/10/2018 30/11/2018 07/12/2018 | Process improvements to ensure speedier closure of exceptions to release charges on the invoice and reduce mismatches | On target
Package 4B: Exclusion Analysis: Procedure Update | 28/09/2018 16/11/2018 |  | Complete
Package 5A: Service Improvement CRs: Automation and Reporting | 28/12/2018 | Automated reporting internally to enable validation & invoice analysis prior to issue | On Target
Package 5B: Service Improvement CRs: Automation and Reporting | 18/01/2019 |  | On target
Package 6: Code Review | 22/02/2019 | Identify any further improvements areas to reduce mismatches | On target
Package 7: AML Scheduling Plan (Phase 1) *Previous date given was for production of the plans to deliver the activity (Phase 2) is the actual plan to deliver AML files | 05/10/18 31/12/18* | Delivery of file before payment due date | Complete On target
Package 8: Single AML/ASP merge file *Previous date given was for POC and delivery of the supporting plans to deliver activity (Phase 1) Delivery Of PoC (Proof of Concept) for AML merge files PoC (Proof of Concept) for ASP merge file | 05/10/18 30/11/18 22/02/18 | Merge of files | Complete Complete In Progress
SAP Automation of Offline ASP Mismatch files | 12/10/2018 23/11/2018 14/12/2018 | Earlier delivery of files | On target

## Slide 9: Defect and Exclusions Resolution Plan
Defect Resolution Plan as at 29th November 2018
https://www.xoserve.com/wp-content/uploads/Customer-Defects.pdf
Exclusion Resolution Plan as at 29th November 2018
https://www.xoserve.com/wp-content/uploads/Customer-Exclusions.pdf
These documents will be updated, tracked and published weekly on Xoserve.com

## Slide 10: UBID Implementation Update
Phase 1 was implemented in August and phase 2 implemented early October.
Following the implementation of both phases the greatest benefit is early visibility of mismatches, providing the opportunity for the operational team in Xoserve to exclude and rectify issues before they feed into the ASP/AML files.
This month has seen the affected customers reduce to 16, and a financial value of 110,000 for November. This is significantly lower than the 2.5 million debit for the month of August.
Xoserve will continue to monitor the situation and keep customers informed of progress.

## Slide 11: Customer Engagement
Monthly progress updates provided to Contract Management Committee (CoMC) and Change Management Committee (ChMC)
Updated plans published on Xoserve.com
DSG will be used to discuss and agree any solution options
Customer Liaison Manager will continue to be the first port of call for customers
Is there anything else you would like Xoserve to provide an update on?