## 1-Summary
Xoserve Monthly Reporting | [5 empty] | Nov 2018
| Invoicing Information | [8 empty] | Contract Management Reporting
| Invoice | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | Priority 1 KPI |  |  |  |  | 1
| LDZ Capacity (CAZ) | 300714752.62 | 302200317.27 | 312174512.16 | 302299412.99 | 312562745.62 | 312780813.69 | 302866760.19 | 313359948.83
| Commodity (COM) | 47885458.16 | 29034584.31 | 19449237 | 14591606.04 | 14290600.7 | 15048321.28 | 17528307.3 | 29476349.27 | Priority 2 KPIs |  |  |  |  | 0
| Amendments (AMS) | 435828.94 | 1543453.44 | 2024085.07 | 2213969.29 | 1483244.96 | 830443.17 | -385853.99 | 58182.64
| Meter Assets (MAS & ADP) | 193565.33 | 194233.3 | 200707.08 | 194233.54 | 200707.69 | 200263.88 | 189788.22 | 196114.17 | UK Link Availability (Gemini) |  |  |  |  | 100%
| NTS Entry Capacity (NTE) | 12522228.64 | 1577511.57 | 1599795.55 | 1621553.61 | 1735803.71 | 1735803.71 | 1760935.51 | 8332609.71
| NTS Exit Capacity (NXC) | 16944144.32 | 18111359.22 | 18702620.75 | 18117525.2 | 18720256.49 | 18720256.49 | 18113875.74 | 13807265.85 | UK Link Availability (Non-Gemini) |  |  |  |  | 100%
[10 empty] | Third Party Services Sold |  |  |  |  | 10050
[10 empty] | Additional Services Sold |  |  |  |  | 10952
[10 empty] | Operational Requirements |  |  |  |  | No Failures
Supply Point Information
[10 empty] | Type | April | May | June | July | August | September | October | October
[10 empty] | Class 1 | 449 | 420 | 422 | 427 | 427 | 429 | 433 | 437
[10 empty] | Class 2 | 663 | 686 | 687 | 658 | 655 | 650 | 645 | 636
[10 empty] | Class 3 | 119857 | 121241 | 123483 | 125491 | 78827 | 88860 | 87615 | 95286
[10 empty] | Class 4 | 23975239 | 23988139 | 24005430 | 24038014 | 24101362 | 24110132 | 24128941 | 24146202
Highlights & Other Matters
Smart Meter- % 27.81%

## 2-KPIs
Key Priority Indicators |  |  | June 2018 | [7 empty] | Comments / Actions
Reference | Service Requirement Description | Service Requirement Trigger | Service Requirement Output | Time for delivery of service requirement | How service requirement delivered | Performance standard | UNC Ref | KPI Priority | Mapping to Previous | RAG Status | Comments / Details | What is remedial action?
DS-CS SA1 - 02 | Respond to Supply Point Enquiry | Receipt of Supply Point Enquiry from a User | Send Enquiring User a response or reject enquiry and send Enquiring User details of reason for rejection | Within two (2) Supply Point System Business Days of receipt | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G1.16 | 1 | reporting ref 13 | G
DS-CS SA1 - 04 | Respond to Supply Point Nomination | Receipt of Supply Point Nomination from a Proposing User | Send Proposing User a Supply Point Offer, reject the Supply Point Nomination and send User details of the reasons for rejection or send User and relevant Network Operator a referral notice | Within two (2) Supply Point System Business Days of receipt of the Supply Point Nomination | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.4.1,G2.3.4, G2.3.5, G2.3.6, G2.3.7, G2.3.8, G2.3.9, G5.4.2 G2.1.2(a) | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 05 | Submission of Supply Point Offer following submission of referral notice or request for information to a Network Operator | Receipt of response from a Network Operator | Send User a Supply Point Offer or reject the Supply Point Nomination and send the User details of the reasons for rejection | Within two (2) Business Days of receipt of a response to the referral from the Network Operator or request for information | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.3.4 (b), G2.3.8, G2.3.9 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 06 | Notification of the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity as a result of a Supply Point Ratchet. | Receipt of notification by the CDSP of the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity at any time prior to the submission of a Supply Point Confirmation by the Proposing User | Send Proposing User notice that Supply Point Offer has lapsed | Within two (2) Business Days of the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity | UK Link Communication |  | TPD G2.4.5 (a) | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 07 | Notification of the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity as a result of a Capacity Revision Application | Notification of the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity as a result of a Capacity Revision Application | Inform the Proposing User of the application of paragraph 2.7.3 | Within 5 Supply Point Systems Business Days after the occurrence of the event giving rise to the application of paragraph 2.7.3 | UK Link Communication | Within 5 Supply Point Systems Business Days after the occurrence of the event giving rise to the application of paragraph 2.7.3 | TPD G2.4.6 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 08 | Notification of revision to the Formula Year Annual Quantity or End User Category | A change in the Formula Year Annual Quantity or End User Category in relation to a Proposed Supply Point during the period a Supply Point Offer remains valid | Send Proposing User notice of change to Formula Year Annual Quantity or End User Category | Within two (2) Supply Point Systems Business Days of the change of the Formula Year Annual Quantity or End User Category | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.4.7 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 09 | Respond to Supply Point Confirmations | Receipt of Supply Point Confirmation from a Proposing User where the Proposed Supply Point includes a Shared Supply Meter Point | Send Proposing User notice acknowledging receipt of Supply Point Confirmation or rejecting Supply Point Confirmation and details of reasons for rejection | Within two (2) Supply Point Systems Business Days of receipt of the Supply Point Confirmation | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.5.11, G2.5.5, G2.6.2 and G2.6.3 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 11 | Notification to existing User of receipt of Supply Point Confirmation | Receipt of Supply Point Confirmation from a Proposing User which is not rejected which a Supply Point Withdrawal has not been submitted | Send existing User notice of submission of a Supply Point Confirmation and the Proposed Supply Point Registration Date | Within two (2) Supply Point Systems Business Days of receipt of the Supply Point Confirmation | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.8.1(a) | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 12 | Respond to Proposing User following Supply Point Objection | Receipt of Supply Point Objection from the Registered User | Send notice to Proposing User of objection and where objecting User is required to declare its identity, notify the Proposing User of the identity of the objecting User; and where the objection was raised at the request of the Consumer and the reasons for the objection have been provided | Within two (2) Supply Point Systems Business Days of receipt of Supply Point Objection | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.8.3(b), (c ), (d) and € G2.8.4(b) | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 13 | Respond to Objecting User following receipt of Supply Point Objection | Receipt of Supply Point Objection from the Registered User | Send notice to objecting User of acceptance or rejection of Supply Point Objection | Within two (2) Business Days of receipt of Supply Point Objection | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.8.3(d) | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 14 | Notification of Supply Point Objection not withdrawn | Receipt of Supply Point Objection from an objecting User which is not withdrawn by the Objection Deadline | Send each Existing Registered User notice of lapse of Supply Point Confirmation | By not later than one (1) Supply Point Systems Business Day before the Proposed Supply Point Registration Date | UK Link Communication | 90% of transfer of ownership files to be issued by 08:00 on D-2 Supply Point Systems Business Days before the transfer date and in any event 100% issued within 2 Supply Point Systems Business Days. | TPD G2.8.6 | 1 | reporting ref 14 | G
DS-CS SA1 - 15 | Notification to Proposing User of effectiveness of Supply Point Confirmation | Receipt of Supply Point Confirmation from a Proposing User where the Proposed Supply Point has been withdrawn by the existing User | Send Proposing User notice of Supply Point Confirmation being effective and the information in relation to the Supply Point to be included in the Supply Point Register. Provide the Valid Meter Reading for the latest Read Date, in the case of a Class 1 or 2 Supply Point, for which Exit Close-Out has occurred. | By not later than one (1) Supply Point Systems Business Day before the Proposed Supply Point Registration Date | UK Link Communication | 90% of transfer of ownership files to be issued by 08:00 on D-2 Supply Point Systems Business Days before the transfer date and in any event 100% issued within 2 Supply Point Systems Business Days. | TPD G2.8.8(a) & G2.9.2 | 1 | reporting ref 14 | G
DS-CS SA1 - 16 | Notify the User (which was the Existing Registered User immediately preceding the effective date of the Supply Point Confirmation) of the identity of the Proposing User (that has become the Registered User) and the identity of the supplier | Passing of Objection Deadline | Send Existing Registered User notice of effectiveness of Supply Point Confirmation and details of the identity of the Registered User and supplier | By not later than one (1) Supply Point Systems Business Day before the Proposed Supply Point Registration Date | UK Link Communication | 90% of transfer of ownership files to be issued by 08:00 on D-2 Supply Point Systems Business Days before the transfer date and in any event 100% issued within 2 Supply Point Systems Business Days. | TPD G2.8.8(b) | 1 | reporting ref 14 | G
DS-CS SA1 - 17 | Respond to Supply Point Withdrawal notice | Receipt of Supply Point Withdrawal notice from a Withdrawing User | Send Withdrawing User notice of acceptance or rejection of Supply Point Withdrawal notice and where rejected the reason for rejection of the Supply Point Withdrawal notice. Where required, in a Shared Supply Meter Point, inform each Sharing Registered User of the withdrawal acceptance. | Within two (2) Supply Point Systems Business Days of acceptance of the Withdrawal Notice | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G3.1.2 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 18 | Notification that Withdrawing Supply Meter Point comprised in a Proposed Supply Point for which the Supply Point Confirmation is effective | Receipt of Supply Meter Point Withdrawal notice from a Withdrawing User for which the Supply Point Confirmation is effective | Send Withdrawing User notice that Withdrawing Supply Meter Point comprised in a Supply Point Confirmation which is effective | Within two (2) Supply Point Systems Business Days of acceptance of the Withdrawal Notice | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G3.1.4 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 19 | Notification of Supply Point Withdrawal comprising Shared Supply Meter Points | Receipt of Supply Point Withdrawal notice from a Withdrawing User for a Supply Point which comprises a Shared Supply Meter Point | Send other Sharing Registered User(s) notice of receipt of Supply Point Withdrawal notice | Within two (2) Supply Point Systems Business Days of the receipt of the Supply Point Withdrawal Notice | UK Link Communication |  | TPD G3.1.5 | 1 | reporting ref 17 | G
DS-CS SA1 - 25 | Respond to Shared Supply Meter Point Nomination | Receipt of Shared Supply Meter Point Notification from proposed Sharing Registered Users or Sharing Registered User Agent | Send proposing Sharing Registered Users notice of acceptance or rejection of the Shared Supply Meter Point Nomination and where rejected the reason for rejection. Where accepted send Supply Point Offers to each Sharing Registered user (and, if appointed, to the Sharing Registered User Agent) | Within two (2) Business Days of receipt of response from Network Operator | Conventional Notice | Submit 100% responses to all Users within Day of receipt plus 2 Business Days | TPD G1.7.6, G1.7.2(d)(i) G1.7.11 | 1 | reporting ref 17 | G
DS-CS SA1 - 29 | Respond to request to cancel a Supply Point Confirmation | Receipt of request from Proposing User to cancel Supply Point Confirmation | Send Proposing User notice of acceptance or rejection of request and send Registered User notice of cancellation of Supply Point Confirmation | Within two (2) Supply Point Systems Business Days of receipt of request | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.8.1( c) | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 30 | Respond to request to withdraw a Supply Point Objection | Receipt of request from objecting User to withdraw Supply Point Objection prior to the 7th Supply Point Systems Business Day after the Supply Point Objection was made or, if earlier, the Objection Deadline | Send objecting User notice of acceptance or rejection of request and send notice to Proposing User where Supply Point Objection withdrawn | Within two (2) Supply Point Systems Business Days of receipt of request | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G2.8.5 | 1 | reporting ref 13 and 17 | G
DS-CS SA1 - 53 | Respond to Shared Supply Meter Point Confirmation | Receipt of a Shared Supply Meter Point Confirmation from each Sharing Registered User | Send each proposing Sharing Registered User notice of acceptance or rejection of the Shared Supply Meter Point Confirmation and where rejected the reason for rejection of the Shared Supply Meter Point Confirmation | Within two (2) Supply Point Systems Business Days of receipt of the Shared Supply Meter Point Confirmation | Conventional Notice | Submit 100% of files (excluding transfer of ownership) in accordance with the UK Link Manual to Users within 2 Supply Point Systems Business Days of receipt. | G1.7 | 1 | KPI reporting ref 17 | G
DS-CS SA1 - 54 | Respond to Shared Supply Meter Point withdrawal | Receipt of a Shared Supply Meter Point withdrawal notification from each Sharing Registered User | Send each proposing Sharing Registered User notice of acceptance or rejection of the Shared Supply Meter Point withdrawal and where rejected the reason for rejection of the Shared Supply Meter Point withdrawal | Within two (2) Supply Point Systems Business Days of receipt of the Shared Supply Meter Point Confirmation | Conventional Notice | Submit 100% of files (excluding transfer of ownership) in accordance with the UK Link Manual to Users within 2 Supply Point Systems Business Days of receipt. | G1.7.10 | 1 | KPI reporting ref 17 | G
DS-CS SA2 - 01 | Standards of Service query management | Receipt of a Standard of Service Operational Query from a Shipper User | Record, investigate and resolve Query in accordance with the Standard of Services Query Management Operational Guidelines | In accordance with the requirements of TPD Section S4.7 and the Standard of Services Query Management Operational Guidelines | Contact Management Service (CMS) | a) Resolve 80% of User Standards of Service Queries within 4 Business Days within the calendar month (except where the Query Type is DUP) b) Resolve 80% of User Standards of Service Queries within 4 Business Days within the calendar month (except where the query type is DUP) for 90% of Users c) Resolve 95% of User Standards of Service Queries within 10 Business Days within the calendar month d) Resolve 95% of User Standards of Service Queries within 10 Business Days within the calendar month (except where the query type is DUP) for 95% of Users e) Resolve 98% of User Standards of Service Queries within 20 Business Days within the calendar month d) Resolve 98% of User Standards of Service Queries within 20 Business Days within the calendar month (except where the query type is DUP) for 95% of Users | TPD S4.7 and chapter 5 of the Standard of Services Query Management Operational Guidelines TPD Section G1.9.7, G1.9.8 and G1.1.7 | 2 | reporting ref 8 | G
DS-CS SA2 - 03 | Non Standards of Service query management | Receipt from a Shipper User of a query in respect of a matter not subject to a Standard of Service | Record, investigate and resolve query | As soon as reasonably practicable following receipt of the query | Contact Management Service (CMS) | Resolve 50% of User non standards of Service queries within 10 Business Days within the calendar month for 90% of Users Resolve 90% of User non standards of Service queries within 20 Business Days within the calendar month for 95% of Users Resolve 95% of User non standards of Service queries within 40 Business Days within the calendar month for 100% of Users | TPD G1.9.8 | 4 | reporting ref 40 | G
DS-CS SA2 - 04 | Network Operator Queries | Receipt from Network Operator of a query in respect of data held on the Supply Point Register | Record, investigate and resolve the query | As soon as reasonably practicable following receipt of the query | Contact Management Service (CMS) | a) Resolve 50% of Network Operator queries within 10 Xoserve days within the calendar month for 100% of Network Operators b) Resolve 70% of Network Operator queries within 20 Xoserve days within the calendar month for 100% of Network Operators c) Resolve 90% of Network Operator queries within 40 Xoserve days within the calendar month for 100% of Network Operators d) Resolve 100% of Network Operator queries within 80 Xoserve days within the calendar month for 100% of Network Operators | TPD G1.9.8 | 3 | reporting ref 31 | G
DS-CS SA3 - 01 | The receipt, acknowledgement and processing of all data provided by a User where such data must be recorded in the Supply Point Register | Receipt of data from a User which must be recorded in the Supply Point Register | Update or record data in the Supply Point Register in compliance with the requirements of TPD Section G, TPD Section M, TPD Section Q, Standard Special Condition A31 and in accordance with the UK Link Manual | Within two (2) Supply Point Systems Business Days of requirement to change or record data in the Supply Point Register | UK Link Communication |  | TPD Sections G, M and Q G2.5.10 G3.7.2 | 2 | reporting ref 16 | G
DS-CS SA5 - 15 | For Class 2 Supply Meters, the validation of a Meter Reading, a Check Read or an Updated Meter Reading | The receipt of a Meter Reading, Check Read or Updated Meter Reading from the User to be validated, and where applicable to become a Valid Meter Reading or Check Read accepted by the CDSP | Validated Meter Reading, Check Read or Updated Meter Reading, and submission of the validation outcome to the User | As required in accordance with TPD E, H, G and S | Electronic update to CDSP systems |  | M5.1.6 M5.3.5(b)(ii) M5.12 (except 5.12.9) M5.14.1 M5.16 M5.13.13 M5.13.14 | 2 | reporting ref 16 | G
DS-CS SA5 - 16 | For Class 3 and 4 Supply Meters, the validation of a Meter Reading, a Check Read or an Updated Meter Reading | The receipt of a Meter Reading, Check Read or Updated Meter Reading from the User to be validated, and where applicable to become a Valid Meter Reading or Check Read accepted by the CDSP | Validated Meter Reading, Check Read or Updated Meter Reading, and submission of the validation outcome to the User | As required in accordance with TPD E, H, G and S | Electronic update to CDSP systems |  | M5.1.6 M5.3.5(b)(ii) M5.12 (except 5.12.9) M5.14.1 M5.16 M5.13.13 M5.13.14 | 2 | reporting ref 16 | G
DS-CS SA5 - 21 | Generation of an estimated Meter Reading for a Class 2 Supply Meter | Failure by the User to submit an Opening Meter Reading | Estimated Opening Meter Reading determined and provided to the relevant User | The 6th Day after the Supply Point Registration date | UK Link communication |  | M5.13.7(a) 5.13.8(a) | 2 | reporting ref 15 | G
DS-CS SA5 - 22 | Generation of an estimated Meter Reading for a Class 3 Supply Meter | Failure by the User to submit an Opening Meter Reading | Estimated Opening Meter Reading determined and provided to the relevant User | The 6th Day after the Supply Point Registration date or the 15th day after the Supply Point Registration date depending on the outgoing Supply Point Class | UK Link communication |  | M5.13.7(c) 5.13.9(a) | 2 | reporting ref 15 | G
DS-CS SA5 - 23 | Generation of an estimated Meter Reading for a Class 4 Supply Meter | Failure by the User to submit an Opening Meter Reading | Estimated Opening Meter Reading determined and provided to the relevant User | The 6th Day after the Supply Point Registration date or the 15th day after the Supply Point Registration date depending on the outgoing Supply Point Class | UK Link communication |  | M5.13.7(c), 5.13.9, 5.13.11(b) | 2 | reporting ref 15 | G
DS-CS SA6 - 11 | Respond to a LDZ DM Supply Point Capacity Revision Application to reduce or increase the Registered DM Supply Point Capacity. | Receipt of a LDZ DM Supply Point Capacity Revision Application from a User or receipt of an application from a Proposing User | Send User notice approving or rejecting Capacity Revision Application and where application approved send User notice of revised Supply Point Capacity or send User and the Transporter a referral notice | Where a capacity reduction is required, within five (5) Supply Point System Business Days of receipt of application from the User; or where a feasibility assessment is required, no later than the 18th Supply Point Systems Business Day following receipt of application from the User | UK Link Communication | Submit 100% of files (excluding transfer of ownership) | TPD G5.1.7, G5.1.8, G5.1.10, G5.2.4 | 2 | reporting ref 13 | G
DS-CS SA6 - 17 | Determination of the Annual Quantity for each Supply Meter Point and notification to the Registered User | The receipt of a Qualifying Meter Reading, | Notification to the Registered User of the calculated AQ, and that the Annual Quantity has crossed the threshold requirement | Not later than 5 Business Days before the end of the AQ Calculation Month. | UK Link Communication |  | TPD G1.6.6 | 2 | does not translate to existing reporting | G
DS-CS SA6 - 18 | Rejection of a request for a change in the Annual Quantity | Receipt of a request for a change in the Annual Quantity | Send notification to the User detailing the reasons for the rejection | Within 2 Business Days of receipt of a request | UK Link Communication |  | TPD G1.6.23, G1.6.25 and G1.6.26 | 2 | does not translate to existing reporting | G
DS-CS SA6 - 19 | Acceptance of a request for a change in the Annual Quantity | Receipt of a request for a change in the Annual Quantity | Send notification to the User confirming acceptance of request. Amend the Annual Quantity. Notify the User five (5) Supply Point Systems Business Days prior to the date the change in Annual Quantity is given effect. | Submit the acceptance notification within 2 Business Days of receipt of a request. Amend the Annual Quantity with effect from the first Day of the first month which begins at least 15 Supply Point Systems Business Days after the date on which the User gave notice | UK Link Communication |  | TPD G1.6.23,G1.6.25 and G1.6.27 | 2 | does not translate to existing reporting | G
DS-CS SA6 - 20 | Respond to User request to revise Annual Quantity for Supply Point comprising a New Supply Meter Point | Receipt of notification from a User, before the Supply Point Registration Date, with the User estimate of the correct Annual Quantity | Amend the Annual Quantity to that provided by the User | As soon as reasonably practicable | UK Link Communication | 1. Corrections were applied in time and the customer would have received the NRL file normally for these MPRNs. | TPD G1.6.29 | 2 | does not translate to existing reporting | G
DS-CS SA12 - 01 | Record the number for a New Supply Meter Point on the Supply Point Register | Receipt of notice that connection works have or will be undertaken to establish a New Supply Meter Point | Record the new Supply Point Meter Reference Number and send notice to relevant contractor (utility infrastructure provider) of new Supply Point Meter Reference Number | As soon as reasonably practicable following receipt of the notice from the relevant contractor | Contact Management Service (CMS) or Conventional Notice | 2. Corrections were submitted for an MPRN which were not applied in time, and these would appear to have been missed from the NRL file (287 MPRN) [shown under ‘MISSED’ in table below] | TPD G7.3.1 | 3 | reporting ref 34 | G
DS-CS SA17 - 01 | Business Day and Supply Point Systems Business Day calendar services | In time for delivery of the service by 30 September each year | Send all UK Link System Users a list of all Business Days and Supply Point Systems Business Days determined in accordance with the code in the following calendar year | By 30 September in each calendar year | Conventional Notice or email | 3. Corrections were submitted for an MPRN for which our system had already calculated a revised AQ (due for example to receiving a read). In these cases the customer would have seen the MPRN in the NRL file but it would have shown the Xoserve calculated AQ rather than their corrected value (84 MPRN). [shown under ‘INCORRECT’ in table below] | TPD G1.10.3 | 3 | reporting ref 35 | G
DS-NCS SA18-06 | Shared Supply meter Point Daily Allocations | Receipt of read data and daily Calorific Values | Send the Sharing Registered User Agent allocated volume for the previous day for Shared Supply Meter Points which are not telemetered | By 16.30 on the day following the Gas Day | Conventional Notice |  |  | 2 | New | G
DS-NCS SA18-07 | Notification of no meter inspection for 2 years | Where the CDSP determines that Standard Special Condition A10 paragraph 6 of GT Licence applies | Send relevant User date by which meter inspection must be carried out | By not later than four (4) months prior to the date by which the meter inspection must be carried out | UK Link Communication | Notify 100% of supply meter points which require a meter inspection to the User |  | 4 | reporting ref 45 | G
ASGT-CS SA2-01 | Standards of Service query management | Receipt of a Standard of Service Financial Query from a Shipper User | Record, investigate and resolve Query in accordance with the Standard of Services Query Management Operational Guidelines | In accordance with the requirements of TPD Section S4.7 and the Standard of Services Query Management Operational Guidelines | Contact Management Service (CMS) | Valid Invoice Queries for calculation errors do not exceed 2% of issued charges, by volume for submitted Invoice Documents in the relevant Billing Period | TPD S4.7 and chapter 5 of the Standard of Services Query Management Operational Guidelines TPD Section G1.9.8 and G1.18 | 2 | reporting ref 8 and 9 | G
ASGT-CS SA2-02 | GRE Invoice Query service | Receipt from a User of a valid GRE query | Record, investigate and resolve query and in accordance with GRE Invoice Query Incentive Scheme Methodology and submit, if appropriate, an Adjustment Invoice | In accordance with the Invoice Query Incentive Scheme Methodology | Contact Management Service (CMS) and UK Link Communication | Resolve, adjust and invoice 100% of valid GRE queries (not read related) | TPD S4.7 | 2 | reporting ref 10 | G
ASGT-CS SA5-14 | For Class 1 Supply Meters, the validation of a Meter Reading or a Check read | The receipt of a Meter Reading, or Check Read, from the Transporter to be validated, and where applicable to become a Valid Meter Reading or Check Read accepted by the CDSP. The provision of the Valid Daily Meter Reading to the Registered User. | Accepted Valid Meter Reading or Check Read. | Valid Daily Meter Reading to the Registered User by 11:00 hours on Day D+1 | Electronic update to CDSP systems |  | M5.1.6 M5.6.1 M5.12 (except 5.12.9) M6.3.1(c ) | 2 | reporting ref 22 | G
ASGT-CS SA7-02 | Submission of scheduled Invoice Documents for each Invoice Type following the end of each Billing Period | The end of the relevant Billing Period | Send Users an Invoice Document for each applicable Invoice Type for the Billing Period | On the relevant Business Day following the relevant Billing Period, as established in accordance with TPD Section S1.4.2, in the case of an Ancillary Invoice in accordance with TPD Sections S2.4.4 and S2.4.6 and in the case of Ancillary Invoices, Adjustment Invoices and Interest Invoices in accordance with TPD Section S2.5.2 | UK Link Communication | a) Submit 100% of User scheduled Invoice Documents and supporting information for each Invoice Type on the invoice date for the relevant Billing Period | TPD Sections S1.1.2, S1.2.1, S1.2.2, S1.4.1 and S1.4.2 | 1 | reporting ref 3 | G
ASGT-CS SA7-03 | Submission of Ancillary Invoices | Request from Transporter to submit an Ancillary Invoice | Send Users an Ancillary Invoice | In accordance with TPD Section S2.4.2 | UK Link or Conventional Notice | Submit 98% of User Invoice Documents and supporting information for an Ancillary Invoice on dates notified by the CDSP to the User | TPD Sections S2.4.2 | 1 | reporting ref 5 | G
ASGT-CS SA7-04 | Submission of supporting data for Invoice Documents | Submission of an Invoice Document or occurrence of due date for submission of supporting data | Send Users complete and accurate supporting data as specified in the UK Link Manual | On the date of submission of a scheduled Invoice Document or five (5) calendar days in advance of date of submission of unscheduled Invoice Documents | UK Link Communication (or in the case of an Ancillary Invoice, email or Conventional Notice or for Amendment Invoice Documents, publish on the UK Link documents) | a) Submit 100% of User scheduled Invoice Documents and supporting information for each Invoice Type on the invoice date for the relevant Billing Period b) Valid Invoice Queries for calculation errors do not exceed 2% of issued charges, by volume for submitted Invoice Documents in the relevant Billing Period | TPD Sections S1.3.4 and S1.3.6 | 1 | reporting ref 3, 4 and 5 | G
ASGT-CS SA7-05 | Submission of Invoice Document following submission of incorrectly stated Invoice Document | Incorrectly stated Invoice Document submitted to User and the CDSP is made aware Invoice Document incorrect | Send User an Adjustment Invoice or Ancillary Invoice | As soon as reasonably practicable after an invoice query is resolved, and in any event by the end of the second following month | UK Link Communication | a) Submit 100% of User Invoice Documents for an Adjustment Invoice by month+2 following invoice query resolution b) Resolve, adjust and invoice 100% of valid GRE queries (not read related) in accordance with the timescales within the GRE Invoice Query Incentive Scheme Methodology | TPD Section S1.8.1 | 1 | reporting ref 6 and 10 | G
ASGT-CS SA7-06 | Calculation and submission of Invoice Documents for credit interest on invoice adjustments and compensation | Requirement for interest payment in accordance with Uniform Network Code | Submission of an Interest Invoice | As soon as reasonably practicable, and in the case of interest on invoice adjustments arising from Invoice Queries, no later than the end of the third (3rd) month following resolution of the query. | UK Link Communication | Submit 100% of User Invoice Documents for an Adjustment Invoice by month+2 following invoice query resolution | TPD Section S4.3.2, S4.4.2 and V10.3.3 | 1 | reporting ref 6 | G
ASGT-CS SA8-01 | Maintain a record of a User's Secured Credit Limit | Receipt of information from applicant User to support admission requirements | Maintain an up to date and accurate record of a User's current Secured Credit Limit | Ongoing | The CDSP to maintain an up to date and accurate record of a User's Secured Credit Limit | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | TPD Section X2.2.3 | 3 | reporting ref 30 | G
ASGT-CS SA8-02 | Respond to application from a User for an increased Secured Credit Limit | Receipt of application for an increased Secured Credit Limit from a User | Review application and security provided (if any), and where appropriate, revise the User's Secured Credit Limit in accordance with the Energy Balancing Credit Rules | As soon as reasonably practicable following receipt of User's application | Update the record of the User's Secured Credit Limit | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | TPD Section X2.2.5 | 3 | reporting ref 30 | G
ASGT-CS SA8-03 | Revise a User's Secured Credit Limit for TPD Section X2.2.6(a) purposes | Occurrence of one of the events referred to in TPD Section X2.2.6(a) | Review User's Secured Credit Limit and security provided (if any), and where appropriate, revise the User's Secured Credit Limit in accordance with the Energy Balancing Credit Rules | As soon as reasonably practicable following occurrence of the relevant event referred to in TPD Section X2.2.6(a) | Update the record of the User's Secured Credit Limit | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | TPD Section X2.2.6(a) | 3 | reporting ref 30 | G
ASGT-CS SA8-04 | Revise a User's Secured Credit Limit for TPD Section X2.2.6(b) purposes | Occurrence of the event referred to in TPD Section X2.2.6(b) | Review User's Secured Credit Limit and security provided (if any), and where appropriate, revise the User's Secured Credit Limit in accordance with the Energy Balancing Credit Rules | As soon as reasonably practicable following occurrence of the event referred to in TPD Section X2.2.6(b) | Update the record of the User's Secured Credit Limit | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | TPD Section X2.2.6(b) | 3 | reporting ref 30 | G
ASGT-CS SA8-12 | Submission of a Cash Call to a User | User's Outstanding Relevant Balancing Indebtedness exceeds the User's Cash Call Limit | Send the User a Cash Call notice | As soon as reasonably practicable following calculation of the User's Outstanding Relevant Balancing Indebtedness | Facsimile or telephone confirmed by facsimile (in the format set out in the Energy Balancing Credit Rules) | Issue 90% of cash calls by 3pm every Business Day | TPD Section X2.6.1 | 3 | reporting ref 25 | G
ASGT-CS SA8-19 | Notification of non payment by a User of a Cash Call | Non payment of the Cash Call by the User by close of the Business Day following Day on which Cash Call was made by the CDSP | Send notice of non payment to the User and send a copy of the notice to the Authority and suspend credit payments to User | As soon as reasonably practicable following non payment by the User | Telephone confirmed by facsimile and first class pre-paid post | Issue 100% of failure to pay notices on the next Business Day following the Payment Due Date | TPD Sections X2.9.1 and X2.9.4 | 3 | reporting ref 26 | G
ASGT-CS SA8-23 | Notification of the non payment by a User of an Energy Balancing Invoice | Non payment of the net invoice Amount under an Energy Balancing Invoice on the Invoice Due Date | Send notice to the User that a Termination Notice may be issued in the event of the continued non payment of the net invoice Amount and send a copy of the notice to the Authority | As soon as reasonably practicable following the Invoice Due Date | Telephone, confirmed by facsimile or first class pre-paid post | a) Collect 98% of Cash by the Payment Due Date – measured as an average monthly year to date total (January to December of any one year) b) Collect 100% of Cash by the Payment Due Date + 2 Business Days c) Record 95% of receipted payments by D+1 | TPD Sections X3.2.1 and X3.2.3 | 3 | reporting ref 27, 28, 29 | R | 30.11.18 - On track 15/11/2018 Customer did not settle EBI on PDD+2 following Failure to Pay Notice that was issued on 13.11.18 asking for cleared payment by 14.11.18. Emergency EBCC meeting convened on 15.11.18 and customer finally agreed to pay with cash call funds on PDD+3 so was in breach of UNC section X. Invoice now settled in full. 19.11.18 - On track
ASGT CS SA11 02 | Registration of an iGT System | Unless notified of a rejection the iGT System register request is deemed to be approved. | Creation of the iGT System on UK Link system and the allocation of the CSEP Id to the iGT System. Where applicable, the provision of information to the relevant Gas Transporter and Shipper(s) | As soon as reasonably practicable | UK Link | Within 2 Business Days of deemed approval | IGTAD B2.4.1 | 1 | New | G
ASGT-CS SA20-01 | Operation, management and support of Data Centres | Requirement to operate, manage and support Data Centres | Operating, managing and supporting Data Centres | Ongoing | Online access to UK Link Gemini | Provide 99% availability of UK Link Gemini within scheduled service hours at 23 hours per day Monday to Saturday and at 22 hours on Sundays (reflecting Planned Downtime for scheduled maintenance in accordance with UK Link Manual) | UKLink Manual | 1 | reporting ref 1 | G
ASGT-CS SA20-02 | Operation, management and support of Application Servers | Requirement to operate, manage and support Application Servers | Operating, managing and supporting Application Servers, including storage management, systems programming, capacity planning, performance tuning and maintenance | Ongoing | Online access to UK Link Gemini | Provide 99% availability of UK Link Gemini within scheduled service hours at 23 hours per day Monday to Saturday and at 22 hours on Sundays (reflecting Planned Downtime for scheduled maintenance in accordance with UK Link Manual) | UKLink Manual | 1 | reporting ref 1 | G
ASGT-CS SA20-03 | Provision of operations support for Application Servers | Requirement to provide operations support for Application Servers | Providing operations support | Ongoing | Online access to UK Link Gemini | Provide 99% availability of UK Link Gemini within scheduled service hours at 23 hours per day Monday to Saturday and at 22 hours on Sundays (reflecting Planned Downtime for scheduled maintenance in accordance with UK Link Manual) | UKLink Manual | 1 | reporting ref 1 | G
ASGT-NC SA16-01 | Provision of information in relation to gas illegally taken | Receipt of notice of alleged incident of gas illegally taken | Submit notice to User and/or Network Operator for investigation into alleged incident or for safety visit | Within two (2) Business Days of receipt of notice and where safety prejudiced as soon as practicably possible | Contact Management Service (CMS) or Conventional Notice | Notify relevant parties of information for 100% of cases in relation to notification of gas illegally taken within 2 Business Days of receipt (excluding safety visit requirements) | Standard Condition 8 | 4 | reporting ref 44 | G
ASGT-NC SA16-03 | Notification of proposed connection or disconnection of meter to a service pipe | Receipt of notification of proposed connection or disconnection | Send relevant User a copy of the notification together with other relevant information which the CDSP holds in relation to the meter | Within two (2) Business Days of identification of User | UK Link Communication | Submit 100% of effective transfer of ownership and meter asset notification files in accordance with the UK Link Manual to Users by no later than the 5th day before the proposed Supply Point Registration Date | Standard Special Condition A10 paragraph 6 | 2 |  | G
ASGT-NC SA16-06 | Provision of relevant data to domestic customers or persons acting on their behalf (but not gas shippers or their agents) or to any customer of a gas supplier in relation to premises occupied, or to be occupied, by the customer | Receipt of request from a domestic customer or a person acting on their behalf (but not a gas shipper or its agents) or receipt of request from a customer of a gas supplier for any relevant data which relate to the premises occupied, or to be occupied, by the customer. Receipt of a request from a gas customer for the provision of the identity of the GT to the premises in question | Provide the relevant data in relation to which the request related | On receipt of request | Telephone | a) Provide supply point information and relevant data to appropriate customers between Monday to Friday 8.30am to 5pm (excluding bank holiday) b) Answer 90% of Reportable Calls to the M Number service within 30 seconds of the call being offered to a call handler. The performance is measured over a financial year. | Standard Special Condition A31 paragraph 2© and 2€ | 3 | reporting ref 33 and 39 | G
ASGT-NC SA16-10 | Conduct a customer satisfaction survey with shippers on the services provided to shippers on behalf of Networks. | Conduct a customer satisfaction survey twice per year. | Customer satisfaction survey results published to Networks and Shipper. | Within two (2) months of the survey closure. | Email and presentation through operational forum. | Maintain an overall score of the equivalent of 3.5 or above out of 5 |  | 2 | reporting ref 51 | G
ASGT-NC SA18-01 | Provision of information and data held by CDSP following complaint to a Network Operator by a User, the Authority, Consumer Focus or Consumer Direct | Receipt of request from a Network Operator for the relevant information and data | Send the relevant Network Operator the relevant information and data | Within eight (8) Business Days of the receipt of the Network Operator's request | Contact Management Service (CMS) | Support 100% of requests for information and data in relation to complaints to Network Operators within 5 Business Days of receipt for 100% of Network Operators |  | 3 | reporting ref 32 | G
ASGT-NC SA22-08 | Notification of submission of Invoice Documents | Submission to Users of Invoice Documents | Send Network Operator notice and relevant content relating to Invoice Documents that have been submitted to all Users (SIF & SIR) | Within twenty four (24) hours of the submission of the Invoice Documents to Users | File transfer or Conventional Notice | Notify the Network Operators of agreed Invoice Document information for 100% of invoices submitted to Users within D+1 of submission |  | 1 | reporting ref 7 | G
SS SA22 05 | Notification of the failure by a User to obtain a valid Meter Reading for a monthly Read Meter | The failure by the User to provide the CDSP with a valid Meter Reading in accordance with TPD Section M 5 | Send a notice to the relevant Transporter and the User of the failure of the User to provide a valid Meter Reading for the relevant monthly Read Meter | As soon as reasonably practicable following the failure by the User to provide the valid Meter Reading by the required date | Conventional Notice and email |  | TPD M5.10.2 | 4 | reporting ref 46 | G
SS SA22 06 | Notification of the failure by a User to obtain a valid Meter Reading for an Annual Read Meter | The failure by the User to provide the CDSP with a valid Meter Reading in accordance with TPD Section M5 | Send a notice to the relevant Transporter and the User of the failure of the User to provide a valid Meter Reading for the relevant Annual Read Meter | As soon as reasonably practicable following the failure by the User to provide the valid Meter Reading by the required date | Conventional Notice and email |  | TPD M5.10.2 | 4 | reporting ref 46 | G
SS SA22 07 | Submission of the Network Operator meter read to UK Link | Receipt of a read from the Network Operator | Send notice to User of accepted read (Must Read) onto UK Link system. | As soon as reasonably practicable following receipt of read | UK Link communication |  | TPD M5.10.2 | 4 | reporting ref 46 | G
SS SA22 18 | Provision installation and maintenance of an Option 1 IX connection. Single Cisco 2900 router Primary link presented via BGADSL.16 Backup link presented via BGADSL.16 Server running the File Transfer Software | Accepted quotation from the customer | A commissioned and tested Option 1 IX connection | As soon as reasonably practicable | Physical installation | Install 100% of UK Link provided equipment and UK Link provided software within 45 Business Days of receipt | General Terms D | 3 | reporting ref 37 | G
SS SA22 19 | Provision installation and maintenance of an Option 2 IX connection. Single Cisco 2900 Router Primary link presented via 2Mb EFM or PPC Backup link presented via BGADSL.16 Server running the File Transfer Software | Accepted quotation from the customer | A commissioned and tested Option 2 IX connection | As soon as reasonably practicable | Physical installation | Install 100% of UK Link provided equipment and UK Link provided software within 62 Business Days of receipt | General Terms D | 3 | reporting ref 37 | G
SS SA22 20 | Provision installation and maintenance of an Option 3 IX connection. Single Cisco 2900 Router Primary link presented via 2Mb EFM or PPC Backup link presented via 2Mb EFM or PPC Server running the File Transfer Software. | Accepted quotation from the customer | A commissioned and tested Option 3 IX connection | As soon as reasonably practicable | Physical installation | Install 100% of UK Link provided equipment and UK Link provided software within 62 Business Days of receipt | General Terms D | 3 | reporting ref 37 | G
SS SA22 29 | User Telephone Enquiry Service, designed to provide customers with access to specific data held within the UK Link System in relation to specific Meter Point Reference Numbers via a telephone enquiry facility. Chargeable by User Telephone Enquiry Service Volume Band including any excess charges and early termination fees. The Defined Terms for this service are in the Defined Terms worksheet. | User Telephone Enquiry Service Request Acknowledgement | User Telephone Enquiry Service available via a Telephone Call | In accordance with the User Telephone Enquiry Service Request Period as stated in the User Telephone Enquiry Service Request (such period ending in 31 March in a Year) during which the Customer wishes to receive the benefit of the User Telephone Enquiry Service | Via the Telephone Number used to make the Telephone Call | For each calendar month User Telephone Enquiry Service Unplanned Downtime is no more than 5% of Core Hours. Except during periods of User Telephone Enquiry Service Planned Downtime and User Telephone Enquiry Service Unplanned Downtime, for each calendar month; answer 90% of calls within 30 seconds. |  | 3 |  | G
SS SA22 33 | Query Management – Standards of Service monthly report, Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 36 | Registered User Portfolio Statement, Ad Hoc Service (for one monthly scheduled report). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Ad- hoc Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 37 | Registered User Portfolio Report Annual Service. For Customer portfolios not exceeding one million Supply Points). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 40 | CSEPs Portfolio Report Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 42 | Unique Sites Portfolio Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 44 | Annual Asset Portfolio Annual Service (once per Year). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 46 | Transco Asset Portfolio Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 48 | Data Portfolio Snapshot Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 50 | Data Enquiry Service Last Accessed Report Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 51 | Data Enquiry Service Last Accessed Report Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 52 | Data Enquiry Service Last Accessed Report Annual Service (scheduled monthly reports). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Registered User Portfolio Report Request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 54 | Historic asset and read portfolio report Annual Service. The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of an Annual Registered User Portfolio Report Service request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 55 | Historic asset and read portfolio report Annual Service. The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of an Annual Registered User Portfolio Report Service request | Registered User Portfolio Report Acknowledgement and provision of the service | In accordance with Annual Registered User Portfolio Report Service and the dates published by the CDSP on its Website | Electronic delivery |  |  | 3 |  | G
SS SA22 58 | Email Reporting Service designed to provide customers with reports of specific data held in the UK Link System in relation to specific Meter Point Reference Numbers. The Defined Terms for this service are in the Defined Terms worksheet. | A service available at any time Receipt of an Email Reporting Request for an Email Report including Meter Point Reference Numbers | Provision of the Email Reporting Service Email Reporting Request Acknowledgement to confirm CDSP's agreement to provide the requested Email Reporting Service | Ongoing | email |  |  | 4 |  | G
SS SA22 59 | Email Reporting Service up to 999 Meter Point Reference Numbers. The Defined Terms for this service are in the Defined Terms worksheet. | Following receipt of an Email Reporting Request from an Authorised User, the submission of the Email Reporting Request Acknowledgement to the Customer no later than 12:00pm on a Business Day | Email report | No later than the end of the second Business Day following submission of the Email Reporting Request Acknowledgement | email | No later than the end of the second Business Day following submission of the Email Reporting Request Acknowledgement |  | 4 |  | G
SS SA22 60 | Email Reporting Service up to 999 Meter Point Reference Numbers. The Defined Terms for this service are in the Defined Terms worksheet. | Following receipt of an Email Reporting Request from an Authorised User, the submission of the Email Reporting Request Acknowledgement to the Customer after 12:00pm on a Business Day | Email report | No later than the end of the third Business Day following submission of the Email Reporting Request Acknowledgement | email | No later than the end of the third Business Day following submission of the Email Reporting Request Acknowledgement |  | 4 |  | G
SS SA22 61 | Email Reporting Service more than 999 but less than 5000 Meter Point Reference Numbers. The Defined Terms for this service are in the Defined Terms worksheet. | Following receipt of an Email Reporting Request from an Authorised User, the submission of the Email Reporting Request Acknowledgement to the Customer no later than 12:00pm on a Business Day | Email report | No later than the end of the fifth Business Day following submission of the Email Reporting Request Acknowledgement | email | No later than the end of the fifth Business Day following submission of the Email Reporting Request Acknowledgement |  | 4 |  | G
SS SA22 62 | Email Reporting Service more than 999 but less than 5000 Meter Point Reference Numbers. The Defined Terms for this service are in the Defined Terms worksheet. | Following receipt of an Email Reporting Request from an Authorised User, the submission of the Email Reporting Request Acknowledgement to the Customer after 12:00pm on a Business Day | Email report | No later than the end of the sixth Business Day following submission of the Email Reporting Request Acknowledgement | email | No later than the end of the sixth Business Day following submission of the Email Reporting Request Acknowledgement |  | 4 |  | G
SS SA22 63 | Data Enquiry Service. A web based tool designed to be used by the Authorised Users to interrogate certain data relating to a supply meter point. The Defined Terms for this service are in the Defined Terms worksheet. | Ongoing | Provision of the Data Enquiry Service. | Core Hours 08:00 to 18:00 hours Monday to Friday (excluding non Business Days) and on 24 and 31 December where these days are Business Days from 08:00 to 12:00 hours and on Saturday from 08:00 to 12:00 hours (excluding 25 December and 1 January where applicable) | Via the internet, on internet browsers Internet Explorer 6, 7 and 8, and Mozilla Firefox 3 (which list of browsers may change from time to time upon not less than 2 months’ notice by the CDSP to Customers), | Part a - 97% availability during Core Hours. Part b - no Data Enquiry Service Planned Downtime to exceed 4 continuous hours within Core Hours on a day |  | 2 |  | G
SS SA22 64 | Data Enquiry Service data update. The Defined Terms for this service are in the Defined Terms worksheet. | Ongoing | Provision of updated data to the Data Enquiry Service | Data updated within two (2) Business Days following the date of receipt and acceptance by the CDSP of such data | Publication on the Data Enquiry Service |  |  | 2 |  | G
SS SA22 65 | Data Enquiry Service Access Request. The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a Data Enquiry Service Access Request | Data Enquiry Service Access Request Acknowledgement | none specified | email | ???? |  | 3 |  | G
SS SA22 66 | Creation of Data Enquiry Service Account (s). The Defined Terms for this service are in the Defined Terms worksheet. | Data Enquiry Service Access Request Acknowledgement | Created Data Enquiry Service Account (s) | No later than the end of the tenth Business Day following the Business Day on which the CDSP issues its Data Enquiry Service Access Request Acknowledgement, or later upon the date requested by the Customer | email | No later than the end of the tenth Business Day following the Business Day on which the CDSP issues its Data Enquiry Service Access Request Acknowledgement, or later upon the date requested by the Customer. In the event the standard is not met, the no charge shall be levied in respect of that Data Enquiry Service Account from the day following that on which it should have been deleted had the performance standard been satisfied. |  | 3 |  | G
SS SA22 67 | Deletion of a Data Enquiry Service Account (s). The Defined Terms for this service are in the Defined Terms worksheet. | Data Enquiry Service Access Request Acknowledgement | Deleted Data Enquiry Service Account(s) | No later than the end of the tenth Business Day following the Business Day on which the CDSP issues its Data Enquiry Service Access Request Acknowledgement, or later upon the date requested by the Customer | email | No later than the end of the tenth Business Day following the Business Day on which the CDSP issues its Data Enquiry Service Access Request Acknowledgement, or later upon the date requested by the Customer |  | 4 |  | G
SS SA22 68 | Telephone helpline service password re-set. The Defined Terms for this service are in the Defined Terms worksheet. | Request from the Customer for a Data Enquiry Service Account password re-set | Re-set password | No later than the end of the Business Day following the logging of the Customer's request via the telephone helpline | UK Link Helpline | No later than the end of the Business Day following the logging of the Customer's request via the telephone helpline |  | 3 |  | G
SS SA22 69 | Telephone helpline services fault reporting. The Defined Terms for this service are in the Defined Terms worksheet. | Request from the Customer to record a fault | Fault recorded | Ongoing | UK Link Helpline | None |  | 3 |  | G
SS SA22 70 | M Number DVD Service to provide customers with an electronic copy in DVD format of selected items for supply meter point records. An annual service for the period 1st April to 31st March the following year (a Year). The Defined Terms for this service are in the Defined Terms worksheet. | Receipt of a M Number DVD Service Request from an Authorised Requester for the Annual M Number DVD Service | M Number DVD Service Acknowledgement and provision of the Annual M Number DVD Service | Delivery on each of the relevant M Number DVD within 20 Business Days of the relevant M Number Quarter Day; 30 June, 30 Septembers, 31 December, 31 March | M Number DVD sent by first class recorded delivery post | Issue DVD in accordance with the time for delivery of service requirement |  | 3 |  | G
ASiGT-CS SA11-01 | Registration of an iGT System | Receipt of a request from an iGT to register an iGT System and the provision by the iGT of the iGT System registration data | Provision of the iGT System register request to the relevant Gas Transporter, and for information to any other iGT where nested arrangements exist (or are being proposed) | Within 2 Business Days of receipt | UK Link | 100% within 2 Business Days of receipt |  | 1 | New | G
ASiGT-CS SA11-02 | Maintenance of iGT System data | Receipt of a request to update iGT System registration data | Updated iGT System registration data. Where applicable, the provision of update notifications to the relevant Gas Transporter, Shipper(s) and iGTs (where nested arrangements exist) | Within 2 Business Days of receipt | UK Link | 100% within 2 Business Days of receipt |  | 1 | New | G
ASiGT-CS SA11-03 | Provision of opening standing data and opening meter reading information for the IGT System and IGT System Supply Meter Point | Receipt of a request to record opening standing data and opening meter reading information from the iGT | Updated IGT System and IGT System Supply Meter Point data. Where applicable, the provision of an update notifications to the relevant Gas Transporter and Shipper(s) | Within 2 Business Days of receipt | UK Link | 100% within 2 Business Days of receipt |  | 1 | New | R | There has been an issue with the AES file generation since Release 3 Go Live on 3rd November. This issue was caused due to an incorrect field in the AMT service catalogue provided from the AMT vendor, this caused in failure generating the files. This issue was raised by on 15th November | To rectify this the field was corrected 16/11/18 and the backlog of files generated and issued to Shippers (over the weekend 17th/18th November)
ASiGT NC SA2-01 | iGT Queries | Receipt from an iGT of a query in respect of data held on the Supply Point Register | Record, investigate and resolve the query | As soon as reasonably practicable following receipt of the query | Contact Management Service (CMS) | a) Resolve 50% of iGT queries within 10 Xoserve days within the calendar month for 100% of iGTs b) Resolve 70% of iGT queries within 20 Xoserve days within the calendar month for 100% of iGTs c) Resolve 90% of iGT queries within 40 Xoserve days within the calendar month for 100% of iGTs d) Resolve 100% of iGT queries within 80 Xoserve days within the calendar month for 100% of iGTs |  | 3 | New | G
ASiGT NC SA16-01 | Provision of information in relation to gas illegally taken | Receipt of notice of alleged incident of gas illegally taken | Submit notice to User and/or Network Operator for investigation into alleged incident or for safety visit | Within two (2) Business Days of receipt of notice and where safety prejudiced as soon as practicably possible | Contact Management Service (CMS) or Conventional Notice | Notify relevant parties of information for 100% of cases in relation to notification of gas illegally taken within 2 Business Days of receipt (excluding safety visit requirements) |  | 4 | New | G
ASiGT NC SA16-04 | Provision of relevant data to domestic customers or persons acting on their behalf (but not gas shippers or their agents) or to any customer of a gas supplier in relation to premises occupied, or to be occupied, by the customer | Receipt of request from a domestic customer or a person acting on their behalf (but not a gas shipper or its agents) for relevant data or receipt of request from a customer of a gas supplier for any relevant data referred to a which relate to the premises occupied, or to be occupied, by the customer. Receipt of a request from a gas customer for the provision of the identity of the GT to the premises in question | Provide the relevant data in relation to which the request related | On receipt of request | Telephone | a) Provide supply point information and relevant data to appropriate customers between Monday to Friday 8.30am to 5pm (excluding bank holiday) b) Answer 90% of Reportable Calls to the M Number service within 30 seconds of the call being offered to a call handler. The performance is measured over a financial year. |  | 3 | New | G
ASiGT NC SA21-01 | Supply point register daily delta files | Ongoing | Provision of supply point register daily delta file to each iGT | Daily (calendar day) | UK Link Communication | Within 2 Business Days of the update being applied to UK Link |  | 1 | New | G
ASiGT NC SA21-02 | Quarterly re-fresh of iGT supply point and supply meter point portfolio | Quarterly | Provision of supply point register quarterly extract file to each iGT | Quarterly | UK Link Communication or alternative secure means | Following the end of the quarter; within 2 Business Days if via UK Link Communication or 15 business days if via other means |  | 3 | New | G
ASiGT NC SA21-03 | Meter reading report (a report of readings accepted on to UK Link each week) | Weekly | Provision of meter readings report to each iGT | Weekly in arrears | UK Link Communication or alternative secure means | Within 2 Business Days following the end of the relevant week. |  | 4 | New | G
ASiGT NC SA21-04 | Notification of confirmation of the first registration of an iGTS Supply Meter Point | First registration of an iGT Supply Meter Point reaches confirmation status | Provision of a report notifying of the confirmation of the first registration of an iGTS Supply Meter Point | Daily | UK Link communication | Within 2 Business Days of the of the confirmation status being reached. |  | 3 | New | G
ASiGT NC SA21-07 | CSEP Max AQ monitoring and report provision | Where iGT Supply Meter Point annual quantities in aggregate exceed 85% of the CSEP Max AQ. | Provision of a report to the relevant Gas Transporter and independent Gas Transporter | Within 2 Business Days of the CSEP 85% Max Aq tolerance breach | UK Link | Within 2 Business Days of the CSEP 85% Max AQ tolerance breach |  | 4 | New | G

## 3-UK Link Availability
UK Link Availability | Nov 2018
UK Link (Gemini) Availability & Performance
Reporting Month November 2018
Performance measures | Target/max | 2018-11-01 | 2018-10-01 | 2018-09-01 | 2018-08-01
New /old – 1 * 100 |  | 01/11-30/11 | 01/10-31/10 | 01/09-30/09 | 01/08-31/08
Gemini Service | 99% | 99.98% | 100% | 100% | 100%
Gemini Access (IX) | 99% | 100% | 100% | 100% | 100%
Nominations per day | 8300 | 6042 | 6040 | 6022 | 5968
Renominations per day | 4200 |  | 28800 | 28222 | 28289
% of transactions < 4 sec's | 95% | 100% | 100% | 100% | 100%
Transaction response time (in minutes) | n/a | 0.57 | 0.56 | 0.55 | 0.51
Transactions per day | n/a | 952676 | 958846 | 956117 | 955310
% Transaction change | n/a | 0.64% | 0.29% | 0.08% | 5.22%
UK Link (Non-Gemini) Availability & Performance
Reporting Month June 2018
Performance measures | Target/max | 2018-11-01 | 2018-10-01 | 2018-09-01 | 2018-08-01 | 2018-07-01
|  | 01/11–30/11 | 01/10–31/10 | 01/09–30/09 | 01/08–31/08 | 01/07 –31/07
Batch Transfer | 99% | 100% | 100% | 100% | 100% | 100%
Service Desk Availability | 99% | 100% | 100% | 100% | 100% | 100%
IS Faults Logged
Faults Raised | P5 | P4 | P3 | P2 | P1 | Total
2017-12-01 | 0 | 39 | 45 | 1 | 0 | 85
2018-01-01 | 1 | 46 | 62 | 0 | 0 | 109
2018-02-01 | 0 | 22 | 28 | 0 | 0 | 50
2018-03-01 | 0 | 68 | 37 | 0 | 0 | 105
2018-04-01 | 0 | 55 | 22 | 0 | 0 | 77
2018-05-01 | 0 | 17 | 55 | 1 | 0 | 73
2018-06-01 | 0 | 26 | 51 | 3 | 0 | 80
2018-07-01 | 0 | 43 | 106 | 4 | 0 | 153
2018-08-01 | 1 | 20 | 42 | 0 | 0 | 63
2018-09-01 | 0 | 15 | 35 | 2 | 0 | 52
2018-10-01 | 0 | 0 | 53 | 0 | 9 | 62
2018-11-01 | 0 | 0 | 53 | 0 | 9 | 62
Total | 2 | 351 | 589 | 11 | 18 | 971

## 4-TP & AS Services
Third Party and Additional Services |  |  |  |  | Nov 2018
|  | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | Aug | SEP | OCT
| Third Party Services Invoiced Amount | 8804 | 26671 | 13740 | 15678 | 9130 | 10688 | 39076 | 11416 | 10208 | 13298 | 11088 | 10560 | 36300 | 30049 | 5697 | 26303.87 | 15571 | 25524 | 10050
| Additional Services Invoiced Amount | 4120 | 254 | 5242 | 8263 | 44894 | 5230 | 5938 | 18372 | 0 | 5216 | 2226 | 6297 | 4118 | 17155 | 9289 | 2760 | 10868.6 | 0 | 10952
| Rolling Third Party Invoiced Amount | 8804 | 35475 | 49215 | 64893 | 74023 | 84711 | 123787 | 135203 | 145411 | 158709 | 169797 | 180357 | 216657 | 246706 | 252403 | 278706.87 | 294277.87 | 319801.87 | 329851.87
| New Category of Third Party Requesting Third Party Services |  |  |  | None
| CDSP liabilities to a Third Party under a TPS Agreement |  |  |  | None
| Any TPS material breach of a TPS Agreement |  |  |  | None
| 2.5%CDSP overall turnover |  |  | 1786525

## 5-Change Report Summary
Totals by Budget Area (£,000's) | [10 empty] | Current Year Value of Work Done Split By Customer Class
|  |  | Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | RAG Status
Summary (by Budget Area) | Expenditure Type | Approved Budget Value 18/19 | Total Approved Value | Estimated Cost at Completion | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Current Year Total vs Budget | Estimated Cost at Completion vs. Total Approved Value | Transmission Network Operator | Distribution Network Operator | DNs & IGTs | IGT's | Shippers
DSC Change Budget | External | 2206.68 | 2829.2291 | 1739.5522 | 508.504 | 1137.3446 | 102.7886 | 0 | G | G | 589.9635 | 126.4739 | 56.176 | 0 | 364.7313
| Internal |  |  | 395.017 | 119.055 | 248.703 | 27.259 | 0 | NA | NA | 167.18 | 10.4145 | 4.901 | 0 | 66.2075
| Total |  |  | 2175.0442 | 668.034 | 1386.0476 | 130.0476 | 0 | NA | NA | 757.1435 | 136.8884 | 61.0769 | 0 | 430.9388
Note that project expenditure & budget values shown do not include margin | [8 empty] | Green - At or below target
Internal costs are not deducted from budget (unless otherwise notified) | [8 empty] | Red - Above target
Details of Changes
| Values pertaining to the Total Cost of the Project |  | Values pertaining to the cost of the project split by Financial Year
Project Line Level Changes | Change in Total Approved Value | Change in Estimated Total Cost of Project | Change in Previous Year Actuals | Change in Current Year Value of Work Done | Change in Current Year Value of Work Remaining | Change in Future Financial Years Value of Work Remaining
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - External [O] | 0 | 0 | 0 | 0 | 0 | 0
4361 UKL Jun'18 Release [R2] (DSC CB) Programme Summary - Internal [O] | 0 | 0 | 0 | 0 | 0 | 0
This section summarises any value change between this report and the previous report. Positive values indicate an increase since the last report, negative indicates a decrease.

## 6-Change Report Detail
Values in £0,000s | [5 empty] | Values pertaining to the Total Cost of the Project |  |  | Values pertaining to the cost of the project split by Financial Year |  |  |  | Percentage to Customer Class |  |  |  |  | Current Year Actual Cost by Customer Class (£0,000's)
Budget Pot Reference | Project Ref No | Project Title | Senior Project Manager | High Level Process Stage | Expenditure Type | Total Approved Value | Estimated Cost at Completion | RAG | Previous Year Value of Work Done | Current Year Value of Work Done | Current Year Value of Work Remaining | Future Financial Years Value of Work Remaining | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | Shippers | Transmission Network Operator | Distribution Network Operator | DNs & iGTs | Independent Gas Transporters | CCR Status | Comments
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | External [O] | 1449.1201 | 810.0437 | 639.0764 | 468.029 | 351.0997 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 165.0169 | 10.533 | 119.3739 | 56.176 | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Internal [O] | 368.9906 | 149.686 |  | 119.055 | 30.631 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 14.3966 | 0.91893 | 10.4145 | 4.901 | 0
B.BP18-020.1 | 4361 | UKL Jun'18 Release [R2] (DSC CB) Programme Summary | L. Chambers | Closedown | Total [O] | 1818.1107 | 959.7297 |  | 587.084 | 381.7307 | 0 | 0 | 47% | 3% | 34% | 16% | 0% | 179.4134 | 11.4519 | 129.7884 | 61.0769 | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | External | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4635 | Amendments to the DSC service line to enable the Web Service provision of data for the Consumer Enquiry Service | P. Duvvuri | Delivery | Total | 0 | 40.475 |  | 40.475 | 0 | 0 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | External [O] | 903.259 | 903.2585 | 0.0005 | 40.475 | 759.9949 | 102.7886 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 180.5644 | 579.4305 | 0 | 0 | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Internal [O] | 0 | 245.331 |  | 0 | 218.072 | 27.259 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 51.8109 | 166.2611 | 0 | 0 | 0
B.BP18-020.1 | 4572 | UKL Nov '18 Release [R3] (DSC CB) | P. Duvvuri | Delivery | Total [O] | 903.259 | 1148.5895 |  | 40.475 | 978.0669 | 130.0476 | 0 | 23.76% | 76.24% | 0% | 0% | 0% | 232.3753 | 745.6915 | 0 | 0 | 0
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | External | 450 | 0 | 450 | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4665 | EUC | L. Chambers | Closed | Total | 450 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | External | 1.5 | 1.4 | 0.1 | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4542 | Changes to Shipper Portfolio Report | R. Roden | Delivery | Total | 1.5 | 1.4 |  | 0 | 1.4 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 1.4 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | External | 8.75 | 8.75 | 0 | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4525 | Transparency of AQ Process | R. Roden | Delivery | Total | 8.75 | 8.75 |  | 0 | 8.75 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 8.75 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | External | 9.5 | 9 | 0.5 | 0 | 9 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 9 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4328 | iGT Elected Shipper Sites Report | R. Roden | Closedown | Total | 9.5 | 9 |  | 0 | 9 | 0 | 0 | 100% | 0% | 0% | 0% | 0% | 9 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | External | 7.1 | 7.1 | 0 | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Internal | 0 | 0 |  | 0 | 0 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 0 | 0 | 0
B.BP18-020.1 | 4354 | Nested CSEP Report for DNs | R. Roden | Closedown | Total | 7.1 | 7.1 |  | 0 | 7.1 | 0 | 0 | 0% | 0% | 100% | 0% | 0% | 0 | 0 | 7.1 | 0 | 0