

**DSC Business Evaluation Report (BER)**

|  |  |
| --- | --- |
| **Change Title** |  National Grid Test Support & Consultancy  |
| **Xoserve reference number (XRN)** | XRN4706 |
| **Xoserve Project Manager** | Nicola Patmore  |
| **Email address** | Nicola.Patmore@xoserve.com  |
| **Contact number** | 0121 623 2636 |
| **Target Change Management Committee date** | 12/12/18  |
| **Section 1: In Scope** |
| To provide support to establish and test connectivity between Gemini and GCS Fusion via EFT.To provide support during IDR1, IDR2 and Implementation/Cutover to validate end to end flow of files between Gemini and GCS Fusion. |
| **Section 2: Out of Scope** |
| Application, configuration and infrastructure changes |
| **Section 3: Funding required to deliver the change** |
|

|  |  |  |
| --- | --- | --- |
| **Gas Industry Participant** | **% Share of Cost** | **Cost Value** |
| **Shippers** |  |  |
| **iGT’s** |  |  |
| **DNO’s** |  |  |
| **Transmission** | **100%** | **£84,720.00** |
| **DN & iGT** |  |  |
| **Total Cost** |  | **£84,720.00** |

 |
| **Section 4: Estimated impact of the service change on service charges** |
| *Please detail any projected increase or decrease in cost to any of Xoserve’s service areas, and within them any service lines, as a result of this change.*

|  |  |  |
| --- | --- | --- |
| **Xoserve Service Area** | **Xoserve Service Line** | **(+/-) Projected Change in Annual Cost** |
| N/A | N/A | N/A |

*In addition, detail any change in functionality of the Xoserve service areas/service lines associated with this change. Use the following link as a reference to the Xoserve service areas:*[Service Description Table](https://www.gasgovernance.co.uk/sites/default/files/ggf/page/2018-02/Service%20Description%20Table%20V4%20live%20clean%20for%20publication%2016%20Feb%202018.xlsx) |
| **Section 5: Project plan for delivery of the change** |
| The timeline illustrates the testing phases and is based on the dates provided by NGIS.  |
| **Section 6: Additional information relevant to the proposed service change** |
| Constraints This project requires use of a full scale environment. Due to other inflight projects it will be necessary to carry out testing in parallel to other projects. The data required for generating files will need to be discussed and managed carefully in order to avoid any impact to the testing activities of other projects.Risks – None identified Issues – None identified Assumptions There are no functional, infrastructure or configuration changes required as part of this request. |

**Please send completed form to:** **box.xoserve.portfoliooffice@xoserve.com**

**Document Version History**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Version** | **Status** | **Date** | **Author(s)** | **Summary of Changes** |
| 0.1  | Draft  | 22/11/18  | Nicola Patmore  | For approval  |

**Template Version History**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Version** | **Status** | **Date** | **Author(s)** | **Summary of Changes** |
| 1.0 | Approved | 15/06/18 | Rebecca Perkins | Document approved at CHMC External Workgroup |