## Slide 1: Change Assurance Findings for UK Link Release 3 Health-check 2
December 2018

## Slide 2: UK Link – R3 Health-check 2 Summary
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | October 2018 | UK Link Release 3 – Health check | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Other | CA1 CA2 CA3 CA4 | Release 3 is the first in which significant (and complex) external customer-driven changes have been made to the launch UK Link functionality, and the release therefore represents a greater delivery challenge than Release 2. The separation of Cadent (Track 2) and main changes (Track 1) evidences an appropriate approach to reduced delivery plan slippage and increasing contingency, however milestone slippage has still occurred and confidence in delivery needs to improve for some key teams. This assurance report is rated Amber overall due to some concerns needing to be addressed asap: The project needs to align its existing infrastructure and application Security assessment and testing approach with Naveen Vasudeva (CISO) to ensure currency and avoid unplanned security testing action The SME team’s confidence in Track 2, Cadent delivery differed significantly from the Project’s team’s view, and has been addressed urgently I.S. Ops engagement in preparing for Go Live, P.I.S. and BAU support, needs improvement Visibility and closure of key actions with stakeholder teams needs to be improved
0
6
6
9
The health of this project has improved significantly since Health-check 1. All of the health-check 1 findings are now closed.
There are no Red RAG areas in this report.
The summary below represents the key findings at the time of completing the Health Check.
After Health-check completion, the project team have closed all CA2 findings – all others have either been actioned by agreed closure dates or are on target to close.
Testing
I.S. Ops engagement
0
0
3
5
Baseline
Latest

## Slide 3: Change Assurance reporting RAYG definitions
Categorisation of delivery risk is as follows:
Red : indicates issues that could entail significant risk to the success of the Programme. Remedial action fundamental to successful outcome of programme, should be implemented as soon as possible;
Amber : indicates issues that could entail significant risk to the success of the Programme. Remedial action important to programme outcomes, should be implemented as soon as practical;
Yellow : indicates issues within could entail risk to the success of the Programme, but this risk is low Remedial action a good to have for the programme, implementation advised;
Green : indicates very minor to no issues, entailing minimal risk to the success of the Programme. Improvement would reduce risk, but the weakness is unlikely to undermine the success of the programme

## Slide 4: Change Assurance Findings Severity
Category | Description
CA1 | High risk of impacting successful delivery and achieving outcomes – finding needs to be addressed in order for project to succeed
CA2 | Moderate risk of impacting successful delivery and achieving of outcomes – finding needs to be addressed in order to protect time, cost and quality
CA3 | Low risk of impacting successful delivery and outcomes – consider fixing in project and apply to future projects
CA4 | Minor impact to achieving delivery or outcomes – build in as a lessons learnt for efficient and effective delivery for future projects