## Slide 1: XRN4665 – EUC Release
04/12/18 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Design: The Change Pack was distributed to industry, as per the plan, on December 21st. An extraordinary is planned for the 24th to seek approval of the Change Pack following the consultation period. Design workshops are ongoing, a Gemini Impact Assessment is currently being undertaken to understand the consequential changes required to the system as a result of the proposed EUC changes in SAP ISU. The output of which will be distributed as soon as it is known Plan: Initial plan established. Detailed planning of subsequent stages such as Build and Test are ongoing Funding: The Project team are on-track to provide the BER to seek ChMC approval at the 09th January 19 meeting |  |  | 
Risks and Issues | Environment and Resource Constraints – There is a risk that due to multiple deliveries running in parallel (June 19, GB Charging, CSSC and EUC) that environment and resource constraints may become an issue from the Build phase onwards |  |  | 
Cost | The BER is on track to be issued for approval at ChMC at the 09th January 19 meeting |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN 4665 - EUC Release Timelines
Key Milestone Dates:
Design Change Packs, Extraordinary Issue Date – 21st December 18
  10 Day Review Period Completion (Excluding Bank Holidays) – 09th January 19
  5 Day Xoserve Response Period Completion – 16th January 19
  5 Day Notice of ChMC Materials – 17th January 19
Design Change Packs Approved – Plan at 24th January 2019 Extraordinary ChMC
6 Month Notice of proposed 31st July Part A Implementation – 31st January 19
Seeking BER Approval at the 09th January 19 ChMC meeting

## Slide 3: XRN4732 - June 19 Release - Status Update
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Detailed Design: Change Packs were distributed on the 23rd November as per the agreed plan date (XRNs: 4670, 4676 and 4687). The remaining design activities are on track to finish by the 28th of January. Build preparation is underway. Following the conclusion of the Design phase, the proposed implementation date for June 19, of June 28th, will need to be agreed at ChMC Plan: Initial plan established. Detailed planning of subsequent stages, such as Build and Testing, are ongoing as test approaches/scenarios are drafted Funding: The Project team are on-track to provide the BER to seek ChMC approval at the 09th January 19 meeting |  |  | 
Risks and Issues | Environment and Resource Capacity – There is a risk that due to multiple deliveries running in parallel (June 19, GB Charging, CSSC and EUC) that environment and resource constraints may become an issue from the Build phase onwards |  |  | 
Cost | The BER is on track to be issued for approval at ChMC at the 09th January 19 meeting |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 4: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Design Change Packs, Extraordinary Issued – 23rd November 18
  10 Day Review Period Completion – 07th December 18
  5 Day Xoserve Response Period Completion – 14th December 18
  5 Day Notice of ChMC Materials – 04th January 19
Design Change Packs Approved – 09th January 19
6 Month Notice of June 28th Implementation – 09th January 19
Seeking BER Approval at the 09th January 19 ChMC
09/01: Seek BER Approval at ChMC