## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | 03/01/2019 - We are currently investigating whether this intiative can be closed, and we will provide an update at the ChMC meeting in February 2019. Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements. 01/02/2019 - ChMC attendees will be asked for any feedback about this issue at ChMC on 13th February. If no feedback is received, we suggest this action to be closed.
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans. 30/01/2019 - We are currently working on some requirements to include this within a 'phase 2' implementation of the new website.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4770 | 0654S | NDM Sample data | 2198.1 - RJ - ES | 2019-01-11 | 2019-01-25 | 2019-02-01 | X |  |  |  |  | 2218 - RJ - ES | 2019-02-13 | 2019-03-01 | A revised version of this Change Pack was issued in January to address the proposed file format amendments. We received two responses, one supported the change, the other raised some questions which we have addressed within our response.
XRN4806 | N/A | Additional data at National Level to support UIG Allocation validation | N/A | N/A | N/A | N/A | X |  |  |  |  | N/A | 2019-02-13 | 2019-03-01 | ChMC will be asked to permit Xoserve provide the additional information at national level to support customers with the validation of UIG Allocation on a monthly basis for the previous calendar month: 1. National Daily Metered volumes, split Class1 and Class2 (and Class2 split by EUC Band), by Day and by LDZ. o Currently only Total DM by LDZ available from National Grid Data Item explorer. 2. National Product Class 3 & 4 Rolling AQ split by Product Class, EUC Band, Day and LDZ o Currently only one day per month is available through UK Link Secure site 3. Total Market data for the Scottish LDZs LC/LS/LO/LW/LT, for each LDZ for each day  Total Demand kWh  Total Daily Metered KWh, split PC1/2, PC2 split by EUC band  Total NDM Demand kWh  Total NDM Rolling AQ by Product Class 3&4 and EUC Band by Day All data to be closed out D+5 data The information will be published in a secure area.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 9th January 2019
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4802 | N/A | Confirmation of the scope of delivery and planned deployment date of XRN4802 Minor Release Delivery ‘Drop 3’ | 2178.3 - RJ - ES | 2018-12-14 | 2019-01-04 | TBC | X |  |  |  |  | 2192 - RJ - ES | 2019-01-09 | 2019-02-16 | XRN4802 Minor Release Drop 3 (MiR Drop 3) commenced Detailed Design activities back in November 2018 with two changes in scope for full ‘end to end’ delivery. Both XRN4690 (Actual Read Following Estimated Transfer Read Calculating AQ of 1) and XRN4717 (Use of Up to Date Forecast Weather Data in First NDM Nominations Run) are ‘new’ changes that were approved for delivery by ChMC on the 10th October 2018. These two changes in scope for delivery as MiR Drop 3 are currently in progress with a planned deployment date of the 16th February 2019.
XRN4376 | N/A | GB Charging and Incremental (PARCA) Part B - Summary of the External Changes Identified | 2178.1 - RJ - ES | 2018-12-14 | N/A - For Information Only | N/A | X | X | X | X |  | N/A - For Information Only | N/A - For Information Only | 2019-09-08 | This Change Pack was submitted for information to confirm the system implementation date of 8th September 2019 for XRN4376 EU/GB Charging Project ‘Part B’, and to provide an overview of the Change Design Description.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Defect 1052 | N/A | Amendment to the UNC Validation Rules to allow the Central Data Service Provider (CDSP) to derive Round the Clock values where Meter Readings are provided in a non-Chronological Read Date order. | 2178.5 - RJ - ES | 2018-12-14 | 2019-01-04 | TBC | X |  |  |  |  | 2192 - RJ - ES | 2019-01-09 | Adhoc Release - January 2019 | There are no changes proposed to the Interface Definitions (i.e. records / hierarchies) in the UK Link Manual. Where the CDSP have derived an amended RTC value this will not be provided to Shipper Users. A change to the UNC Validation Rules are proposed to allow the Central Data Service Provider (CDSP) to derive Round the Clock values where Meter Readings are provided in a non-Chronological Read Date order.

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
TBC | Service Desk Plus | 2019-03-02 | 5:00 | 2019-03-03 | 9:00 | For the duration of this outage, users of Service Desk Plus are advised to log any tickets via telephone as the Service Desk Plus application will not be available. | 2019-02-13
7445 | Gemini and Gemini Exit Disaster Recovery Test | 2019-04-13 | 3:15 | 2019-04-13 | 7:30 | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit. (Should it be necessary to fail back to the primary site, the outage window will be extended to 12:30 UK BST). | 2019-02-13
7445 | Gemini and Gemini Exit Disaster Recovery Test | 2019-04-14 | 3:00 | 2019-04-14 | 7:30 | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit (Should there be issues failing back to the primary site, the outage window will be extended to 12:30 UK BST). | 2019-02-13