## Slide 1: XRN4828 - Nov 19 Release - Status Update
6th February 2019 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | RFQ (request for quote): Aiming for contract approval by no later than 15/03/19 Plan: Planning for the Design Phase starts. At the end of Detailed Design the proposed Nov 19 implementation date will seek approval by the ChMC Funding: The Project team are on-track to provide the EQR to seek ChMC approval at the 13th February 19 meeting |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | High-level, estimated, costs for each change were provided within the completed HLSOs. The EQR is on track to seek approval by ChMC at the meeting on 13th February 2019. |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing Full project mobilisation to commence on appointment of preferred supplier. |  |  | 

## Slide 2: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Receive supplier responses – 13/02/19
Shortlist preferred supplier – 18/02/19
Supplier contract approval – 15/03/19
Approve and issue EQR – 04/02/19
Gain business Case approval at IRC - 27/02/19
PID approval 18/03/19
Detailed Delivery Plan approved – 22/03/19
Design Change Packs Submitted to Industry –08/05/19
Test Plan approval – 05/04/19
BER Approval – 14/06/19
2020
Feb
Mar
Apr
May
Jun
Jul
Aug
Sept
Oct
Nov
Dec
2019
J
u
n
e
1
9
–
C
h
M
C
A
g
r
e
e
d
S
c
o
p
e
Testing
Build
UT
Imp
Mobilisation
Jan
Design
Build & UT
System Test
SIT
UAT
RT & PT
Market Trials
IMP (Inc IDR)
PIS
Closedown
04/02: EQR Approval
04/06: BER Approval
08/05: Change Pack Submission
Nov-19 Timeline