## Slide 1: Xoserve IX Refresh
Customer Update
05/03/2019

## Slide 2: IX Refresh Customer Update
Welcome to the February update of the IX Refresh Project
We’ve made good progress over the last month, achieving our major program milestones of Proof of Concept testing and the completion of the pilot site on February 19th. Our work on the pilot site has identified a number of potential improvements to our approach which will lead to a more seamless migration and will improve your experience of the process.
As part of the service transition to the new IX platform, alongside our continued line installation activities, we will be working with our suppliers over the next few weeks to make the improvements that we’ve identified and we will test the perfected migration approach on a second site ahead of the rollout. This will be our priority focus this month, however we will continue line and router installations as planned.
Whilst we acknowledge the improvements outlined above will have an impact on the timelines set out in last month’s update, we will look to identify efficiencies during the delivery phases of the program where possible and we will provide further information in future updates.
Our aim is to make this process as seamless as possible to ensure that the installation experience meets your expectations. If you’d like more detailed information about dates relevant to your migration, please email box.xoserve.IXEnquiries@xoserve.com
Finally, thank you for your ongoing support and I look forward to updating you again in March.
Michelle Callaghan
People Platform Director

## Slide 3: Look Forward: IX Program Quarterly Activity
Three Month Timeline
March
Migration approach to be perfected and tested at another site.
Initial line installations to continue across all phases
Router installations to take place at some phase one sites
Prepare April migrations
Continue to engage customers with Disaster Recovery equipment about testing approach
Continue to engage relevant customers requesting additional IP range / addresses for IX End User equipment
April
Rollout begins with Phase One
Relevant sites contacted to have servers installed
Prepare May migrations
Phone line installations to continue
May
Rollout continues for line, router and server installations
Customers contacted to have servers installed
Prepare June migrations
Phone line installations to continue
Please be assured that you will be contacted by Gamma before either your Network survey or phone line installation takes place (dependant on the complexity and IX option required).
If you have any queries answers to the most commonly asked questions can be found on our website in the Q&A section here.

## Slide 4
June
August
February
March
April
May
Pilot Site
Phase One
Network and Router Installation
Server Installation
Phase Two
Phase Three
Phase Four
Remaining Sites
(Where surveys are outstanding)
High level migration plan – Current & future view
Phase Five
July
Migration Amendments
Second Pilot Site