## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | AML Schedule Proposal | 1839.1 | 2018-01-12 | 2018-01-26 | 2018-01-30 | X |  |  |  |  | 14/02/2018 - rejected | 03/01/2019 - We are currently investigating whether this intiative can be closed, and we will provide an update at the ChMC meeting in February 2019. Rejected at ChMC on 14th February. Xoserve to produce additional information - Cost vs benefit for further discussion. Further industry discussions to be held for both defects and requirements. 01/02/2019 - ChMC attendees will be asked for any feedback about this issue at ChMC on 13th February. If no feedback is received, we suggest this action to be closed. 04/03/2019 - This Action was closed at February's ChMC meeting
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | Still undertaking discussions at DSG. We are looking at several distibution mechanisms and will test how the Change Pack process would work for each one. 30/10/2018 - The intention will be to include this within the scope of the new Xoserve website design plans. 30/01/2019 - We are currently working on some requirements to include this within a 'phase 2' implementation of the new website.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4806 | N/A | Additional data at National Level to support UIG Allocation validation | 2234.8 - RJ - ES | 15/0/2019 | 2019-03-01 | 2019-03-01 | X |  |  |  |  | TBC | 2019-03-13 | 2019-03-01 | In February, ChMC permitted Xoserve to provide the additional information at national level to support customers with the validation of UIG Allocation on a monthly basis for the previous calendar month. As agreed at ChMC in February, this Change was sent out in the February Change Pack to confirm the an ad-hoc implementation within March 2019.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 13th February 2019
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4770 | 0654S | NDM Sample data | 2198.1 - RJ - ES | 2019-01-11 | 2019-01-25 | 2019-02-01 | X |  |  |  |  | 2218 - RJ - ES | 2019-02-13 | 2019-03-01 | Change Pack’s 2140.9 and 2198.1 issued on 9th November 2018 and 11th January detailed the requirements on Shipper Users to provide the NDM Sample data from 1st March 2019 as well as the reports expected to be provided by the CDSP to the Performance Assurance Committee (PAC). At the Change Management Committee (ChMC) on 13th February 2019, Change Managers agreed to approve the final format but requested that the Market Sector Code was reinstated. Please note, that this has been added as per the UK Link standard for this data item.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
N/A | EFT | 2019-03-17 | 5:00 | 7:00 | 2019-03-17 | Xoserve will be conducting an Enhanced File Transfer (EFT) Windows Server Patching activity. This will be carried out on Sunday 17th March 2019 during the UK-LINK maintenance window between 05:00 to 07:00 UK GMT. If there are any Production issues identified prior to or on the day the activity will be moved with a contingency date of Sunday 24th March 2019 between 05:00 to 07:00 UK GMT | 2019-03-13
N/A | IX Equipment | 18/03/2019 20/03/2019 | 20:00 20:00 | 19/03/2019 21/03/2019 | 06:00 06:00 | We have been informed that our Information Exchange (IX) supplier, Vodafone, is planning two outage windows to ‘Upgrade Internetwork Operating System (IOS) due to the IOS coming to end of life and support by vendor (Cisco)'. IOS is the operating system software for the Cisco routers used as an important component part of the IX equipment. Please see further information below regarding the outages. • Gemini Access o If any site has both circuits listed then the site is likely to lose network connectivity during the outage. This will impact a user’s Gemini access • EFT – File Transfers o The files will remain on the server at Xoserve and the IX Site until the connection is re-established following the upgrade • Planned activity list which we can give an hour window for the 20 min outage o There are numerous devices; it is not possible to give an hour window for all • What if there are issues after the restart? If the change implementation fails Vodafone have a defined roll back plan. This is to mitigate any challenges that might arise during or after implementation. Vodafone have determined that in the case of a failure the upgrade will be rolled back or an engineer attend site with a ‘new router’. The incident management process with the Vodafone service desk will be followed to manage any failures for immediate resolution. | 2019-03-13
7445 | Gemini and Gemini Exit Disaster Recovery Test | 2019-04-13 | 3:15 | 2019-04-13 | 7:30 | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit. (Should it be necessary to fail back to the primary site, the outage window will be extended to 12:30 UK BST). | 13/02/2019 / 13/03/2019
7445 | Gemini and Gemini Exit Disaster Recovery Test | 2019-04-14 | 3:00 | 2019-04-14 | 7:30 | Annual test to prove disaster recovery capabilities and procedures for Gemini and Gemini Exit (Should there be issues failing back to the primary site, the outage window will be extended to 12:30 UK BST). | 13/02/2019 / 13/03/2019