## Slide 1: XRN4732 - June 19 Release - Status Update
29th October 2018 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Build: Activities have commenced and are continuing to plan to be completed by 15th March Plan: Tracking to plan, detailed testing phases have been drilled down and the timeline has been baselined based on this assessment Funding: The BER was approved by ChMC at the 09th January 19 meeting |  |  | 
Risks and Issues | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, AML/ASP etc) and all requirements are able to be met Environments– There is a risk that multiple projects are running in parallel (EUC, June 19 & GB Charging) a detailed assessment of co-existence in pre-production is in progress |  |  | 
Cost | Project delivery costs are tracking to approved budgets |  |  | 
Resources | Weekly monitoring of SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4732 - June 19 Release Timelines
Key Milestone Dates:
Traceability of Detailed Design to Requirements is complete
Agreement of June 19 Implementation Date to be agreed with ChMC