## Sheet1
Action Reference | Decision /Issue /Risk /Action | Description of Action | Target Date | Owner | Update | Status
01-2901 | Issue | Section 3.26.1 of Mod 0678 and the impact of top-up charges on existing contracts and compliance with the TAR NC Article 35. |  | SSE (JCh) | Workgroup agreed this issue os a subset of action 2901-02. Closed 31 January | Closed
01-2901 | Action | National Grid to consider the impact of top-up charges on existing contracts and compliance with the TAR NC. | 11-Feb-2019 18-Feb-2019 22-Feb-2019 | National Grid Colin Williams (CW) | 31/01 - CW advised no change to view so far, action to remain open. 05/02 - The Workgroup requested a statement from National Grid for the Workgroup Report explaining how adding a top-up change is compliant with Article 35. CW agreed to provide a written response by 11-Feb-19. 14/02 - This will be incorporated into the updated drafting of modification 0678, ready for monday 18 February 18/02 - This will be covered in the updated mod expected by Friday 22 February 25/02 - This is covered in the amended modification 0678 | Closed
02-2901 | Action | Article 35: Joint Office to consider the topic list and confirm whether Article 35 fits into the timetable. Suggested for 31 January meeting under Revenue Recovery. |  | Joint Office | Action discussed within Recovery Topic discussions on 31 January. Action Closed 05 February. | Closed
03-2901 | Action | Workgroup to consider existing contracts and any potential discriminatory aspects relating to storage capacity (reference rules being developed under Modification 0662). | TBC | Workgroup | Action discussed within Recovery Topic discussions on 31 January. 05/02 The Workgroup believed that this needs to be considered further along with dicussiosn on combinied ASEPs. The solution does to cater for this at the moment and further clairty is required within the modification and Workgroup Report. National Grid beleive this is non-discreminatory against certain storage facilities. It was considered that certain elements of Modification 0662 needed to be incorporated into Modification 0678 for combined ASEP storage facilities. It was percieved that the soluton would work dependent on the definition of the ASEP site. There will be no differentaition for storage capacity and non-storage capacity for the importing of abandoned storage facilities. It was suggested there should be one holistic solution and avoid splitting elements out. 14/02 - a header to cover this principle will be placed in the Workgroup Report. 0678B dispences with that issue. 25/02 - More information is required in the Workgroup Report to cover this 04/03 - This is included withink the Workgroup Report | Closed
04-2901 | Action | National Grid to consider the consistent presentation of charges to enable comparative analysis of Alternatives. | 11-Feb-2019 | National Grid Colin Williams (CW) | CW confirmed that the logic will be included in the sensitivity tool template for the output of Entry and Exit prices. This will be provided for the next meeting. RF expressed the importance for the consistent presentation of numbers. CW explained that National Grid will provide a generic set of numbers based on a set of principles, the FCC numbers will be provided without the options. The options will need to be built in. The data can be overidden. Parties will need to approach National Grid for National Grid data. 14/02 - National Grid agreed to provide model for Modification 0678, other results can be added to any table which will be delieverd. | Closed
05-2901 | Issue | Regulatory Impact Assessment – impact on customers. | 14-Feb-2019 to 06-Mar-2019 | Workgroup | This will be covered as the WGR is updated throughout the Workgroup discussions | Closed
05-2901 | Action | Ofgem to consider the requirement to provide a regulatory impact assessment. | TBC | Ofgem David O'Neill (DON) | Action re-allocated to Ofgem from Workgroup. 14/02 - Ofgem will make a decision when the FMR is received. | Closed
06-2901 | Action | National Grid to consider traded capacity contracts and exposure to the capacity uplift charge and when it would attract the revenue recovery charge and if this was intended for this modification | 14-Feb-2019 | National Grid Colin Williams (CW) | CW confirmed that the general approach will be the same as before. More clarity was requested and will be provided within the Modification. Firm position on this subject. Questions encouraged from the Workgroup. CW agreed to provide an update within a presentation slide. 14/02 - This will be clarified in the draft amended Modification 0678 due to be delivered Monday 18 February, 0678A will follow suit. | Closed
07-2901 | Action | Ofgem to provide a formal View on the feasibility of achieving 01 October 2019 implementation date and the impact of not achieving this date and being compliant as soon as possible. (JO to action this) | TBC | Ofgem David O'Neil (DON) | Ofgem have requested as per 12.8.2 for the Workgroup to set out the “views and reasons for seeking a View from the Authority”. Pursuant to rule 12.8.4 “the Modification Proposal should proceed to Workgroup Assessment…” and that any implementation date has no bearing on the urgent process that is currently occurring. The Workgroup wished to have clarity on what methodology the industry will be working to for contract with start dates of 01 October 2019. Further clarity was required to understand the risks associated with the new Gas Year and to allow for correct negoataitions. 14/02 - Ofgem will make a decision when the FMR is received. | Closed
08-2901 | Action | Workgroup to review the draft Workgroup Report at the end of each session and provide any updates ahead of the start of the next session/meeting. | Ongoing | Workgroup | Confirmed that conclusion of conversations will be captured in the Workgroup Report as discussions progress. | Closed
01-3101 | Action | Extra clarity to be added to the Modification to clarify netting-off for existing contracts | 14-Feb-2019 22-Feb-2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - This will be in the draft amended Modification 0678 expected Monday 18 Februray. All other proposers who are mirroring 0678 proposal, this includes 0678A (deadline Fri 25 Feb) and 0678B (no plans to update mod for this). A header will be put in the Workgroup Report gross/net for exisiting contracts under RPM general. Take into account Ofgem's views in 0621 letter 25/02 - More information is required in the Workgroup Report to cover this. 04/03 - This is included within 0678v2. | Closed
02-3101 | Action | Reference Price Methodology - Workgroup to consider the need for a mechanism to allow more equitable recovery | 04-Mar-2019 | Workgroup | 14/02 - J Costa (EDF Energy) to supply wording for Workgroup Report by 18 Feb 04/03 - J Costa will provide this wording on 04 March | Closed
03-3101 | Action | National Grid to add commentary to the Modification as to the decision for choosing the Capacity Weighted Distance (CWD) approach. | 14-Feb-2019 18-Feb-2019 22 Feb 2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - This will be in the draft amended Modification 0678 expected Monday 18 Februray. 18/02 - This will be covered in the updated mod expected by Friday 22 February | Closed
04-3101 | Action | Workgroup to consider Article 7 as part of compliance discussions | 11-Feb-2019 | Workgroup | Considered within Workgroup 4 on 11-Feb-19. Action superceded, Workgroup will consider compliance for the Workgroup Report of all appropriate TAR NC Articles. See New Action 01-1102. | Closed
05-3101 | Action | National Grid to provide a set of principles / algorithm for the FCC methodology, and some back cast analysis. | 14-Feb-2019 20-Feb-2019 25-Feb-2019 05-Mar2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - FCC methodology will be provided by National Grid by 20 feb 20/02 - FCC methodology will be provided by National Grid by 25 feb 25/02 - The updated FCC will be provided by 27 February 2019 04/03 - FCC methodlogy expected Tuesday 05 March 06/03 back cast analysis will be sent (to PY) | Closed
06-3101 | Action | National Grid to provide the FCC methodology and figures | 14-Feb-2019 20-Feb-2019 25-Feb-2019 | National Grid Colin Williams (CW) | In progress expected w/c 11-Feb-19. 14/02 - FCC methodology will be provided by National Grid by 20 feb 20/02 - FCC methodology will be provided by National Grid by 25 feb 25/02 - The updated FCC will be provided by 27 February 2019 | Closed
07-3101 | Action | Anna Shrigley to provide suitable text regarding the existing capacity customer contracts for inclusion in the Workgroup Report | 05-Feb-2019 | Anna Shrigley | Provided. Comments to be captured. 11-Feb-19 update: now captured in WGR by RH | Withdrawn
8-3101 | Issue | Workgroup to review capacity hand-backs (not in scope of 0678) | TBC | Joint Office | Workgroup Report to capture considerations. 14/02 This has been put on the agenda for NTSCMF April 2019. | Closed
9-3101 | Action | Workgroup to consider previous 0621 considerations and Ofgem's Decision Letter | 05-Feb-2019 | Workgroup | Workgroup Report to capture appropriate extracts. | Closed
10-3101 | Action | Alex Nield requested that his views on Interim Contracts are considered and captured within the Workgroup Report | 14-Feb-2019 to 06-Mar-2019 | Workgroup | Interim Representation published. Potential Alternative. 14/02 - Alex Neild to highlight what, if anything, is to go into the Workgroup Report | Closed
01-0502 | Action | Multipliers and Discounts: National Grid (CWi) to provide an illustration of revenue alignment for Interruptible Capacity, including the resulting effect on revenue recovery and top-up charges for existing capacity holders. | 13-Feb-2019 or 14-Feb-2019 20-Feb-2019 22-Feb-2019 | Workgroup | 14/02 - reviewed - target date updated 20/02 - This will be included in the amended 0678 Modification or in supporting material expected Friday 22 Feb or in supporting material 25/02 - This is covered in the amended modification 0678 | Closed
02-0502 | Action | Shorthaul: National Grid to provide some analysis on Shorthaul and the effect of cessation of Shorthaul on existing users and customers currently using Shorthaul services. | 14-Feb-2019 22-Feb-2019 | Workgroup | 14/02 - Confirm aggregate volume of flows that benefit to shorthaul 20/02 - This will be included in the amended 0678 Modification or in supporting material expected Friday 22 Feb or in supporting material 25/02 - This is covered in the amended modification 0678 | Closed
03-0502 | Action | Workgroup Report: Workgroup to ensure that the Relevant Objectives are appropriately assessed when completing the Workgroup Report (14th Feb-6th March) | 14-Feb-2019 to 06-Mar-2019 | Workgroup |  | Closed
01-1102 | Action | Joint Office to formulate a TAR NC Compliance Table for Proposers and Workgroup to assess compliance for the Modification by Article. | 13-Feb-2019 | Joint Office |  | Closed
02-1102 | Action | Ofgem (NRA) to decide and confirm who should undertake the Cost Allocation Assessment under TAR NC Article 5. | 20-Feb-2019 | Ofgem James Thomson (JT) | 14/02 - capture in WGR that CAA will be done after UNC process finishes, Ofgem to update on this | Closed
03-1102 | Action | Ofgem (NRA) to decide and confirm who should undertake the TAR NC Article 26 Consultation. | 15-Feb-2019 20-Feb-2019 | Ofgem James Thomson (JT) David O'Neill (DON) | 14/02 - reviewed - target date updated 20/02 - Ofgem intends to carry out the final consultation for Article 26, National Grid will be asked to carry out the interim Article 26 consultation shortly after the UNC consultation with the same end date as the UNC consultation (05 April 2019). The CAA will be done by National Grid to be used in the final consultation by Ofgem. Letter from Ofgem expected withion the next week. CAA results will be available during the UNC consultation. | Closed
04-1102 | Action | National Grid to provide an update on the FCC methodology no later than 18 February 2019 and to consider using the past 5 Years historical gas flow data opposed to DN forecasted capacity data for offtakes. | 14-Feb-2019 20-Feb-2019 22-Feb-2019 | National Grid Colin Williams (CW) | 14/02 - this will be included in the FCC methodology to be received by 20 February 20/02 - will be included in supporting material expected Friday 22 Feb 25/02 - This was received 22 February | Closed
05-1102 | Action | Northern Gas Networks (EB) to confirm if the DNs 1in20 Demand Forecast data can be made publicy available (as provided by DNs to National Grid under UNC OAD Section H NTS Long Term Demand Forecasting) subject to any confidentiality concerns associated with the data. | 14-Feb-2019 | Northern Gas Networks Emma Buckton (EB) | 14/02 raise new issue for NTSCMF DN as Relevant Points should be publishing. This has been placed on the April 2019 agenda | Closed
06-1102 | Action | Joint Office to feedback concerns to the UNC Panel, that National Grid do not have sufficient resource to support the Workgroup development and the analysis required to satisfy Ofgem's expected robust analysis. | 14-Feb-2019 | Joint Office (RH) | This has been completed - see UNC Panel minutes from 12 February 2019 | Closed
01-1402 | Action | National Grid (CW) to provide clarity on where data is currently published that applies to each Article in the TAR NC. | 28-Feb-2019 04-Mar-2019 | National Grid Colin Williams (CW) | 04/03 - CWi to provide link to the Transparency Platform 04 March 06/03 - Carried Forward 28/03 - Reviewed - Closed | Closed
01-1802 | Action | Any firm statements to be included in the Compliance section for Modifications that are currently live are to be provided by 22 February 2019 | 27-Feb-2019 | All Workgroup |  | Closed
02-1802 | Action | Any firm statements to be included in the Compliance section for Modifications that are NOT currently live are to be provided by 01 March 2019 | 01-Mar-2019 05-Mar-2019 | All Workgroup | 04/03 - Awaiting 0678H compliance statement, expected 05 March 2019 | Closed
01-2502 | Action | Ofgem to provide a statement to clarify the expectations in terms of Legal Text provision (Target date 27 February 2019) | 27-Feb-2019 04-Mar-2019 | Ofgem James Thomson (JT) | 04/03 - JT to send email 04 March 2019 06/03 - Carried Forward 28/03 - Ofgem confirmed they were not expeciting a Compliance Assessment | Closed
02-2502 | Action | National Grid (CWi) to provide a view on the significance of an PARCA Reservations and the possibility of updating the sensitivity tool to incorporate some recent PARCA Reservations (Target date 28 February 2019) | 28-Feb-2019 06-Mar-2019 | National Grid Colin Williams (CW) | 04/03 - changes to distance matrix to incorporate PARCAs, NG view likely to be relatively minor update to sensitivity tool expected possibly after 06 March 2019 06/03 - awaiting Ofgem letter 28/03 - Reviewed - Closed | Closed
01-2602 | Action | EU/GB Project Team (Relevant National Grid project team) to provide a systems cost estimate and issues and feasibility update statement for inclusion in the Workgroup Report (Target date 01 March 2019) | 01-Mar-2019 | National Grid Colin Williams (CW) and Xoserve (Steve Pownall (SP) | 04/03 - Chris Gumbley (NG) to send update 06/03 - CWi to send statement 28/03 - To close - email received 06 March | Closed
01-2702 | Action | ALL Proposers to consider the consequences of a Mid-year implementation and if this would be compliant with TAR NC Article 6.3 and amend their modification accordingly | 04-Mar-2019 | 0678 - Colin Williams National Grid A - RWE Bill Reed B - Centrica Graham Jack C - SSE Jeff Chandler D - Anna Shrigley ENI E - George Grant Gateway F - Benoit Enault Storengy G - Iwan Hughes Vitol H - Alastair Tolley EP UK | 04/03 0678 will be able to be effective on any date, LT therefore written to do this. If 01 Oct is explicit as an effective date, this must be set out in solution section. If a particular Gas Year this must also be set out. If there is any intended flexibility on effective dates, this must be set out clearly in the modification. | Closed
02-2702 | Action | It has been confirmed that Workgroup are not going to see Legal Text for Section S. All Proposers to advise, if referencing section S, please advise why? | 04-Mar-2019 | 0678 - Colin Williams National Grid A - RWE Bill Reed B - Centrica Graham Jack C - SSE Jeff Chandler D - Anna Shrigley ENI E - George Grant Gateway F - Benoit Enault Storengy G - Iwan Hughes Vitol H - Alastair Tolley EP UK |  | Closed
03-2702 | Action | All Proposers to review the 0678 comparison Table and provide any required updates | 04-Mar-2019 | 0678 - Colin Williams National Grid A - RWE Bill Reed B - Centrica Graham Jack C - SSE Jeff Chandler D - Anna Shrigley ENI E - George Grant Gateway F - Benoit Enault Storengy G - Iwan Hughes Vitol H - Alastair Tolley EP UK I - Sinead Obeng Gazprom J - Adam Bates SouthHook | 28/03 - v5 Comparison Table is now published 04/04 - v6 Comparison Table published | Closed
01-2802 | Action | Proposers to provide a comparison appraisal of CWD verses Postage Stamp. | 04-Mar-2019 | All Workgroup |  | Closed
02-2802 | Action | Joint Office to formulate a draft delivery plan by 10am on 04 March 2019 to share and agree with the Workgroup. | 04-Mar-2019 | All Workgroup |  | Closed
01-0403 | Action | DNs to liaise with National Grid to ensure the booking data within the Forecasted Contracts Capacity (FCC) Model is accurate. (Target Date 05 March 2019). | 05-Mar-2019 09-Mar-2019 | DNs and NG | conversation later 05 March 2019 06/03 - (SS Cadent) numbers are 9% lower than DN capacity bookings across all Cadent LDZ. CW forecast is based on Y-2. No new numbers as yet. PY requested impact assessment of any forthcoming change. 28/03 - v3 includes changes as a result of discussions | Closed
02-0403 | Action | DNs to clarify when booking DN capacity if' the gas hasn’t left the NBP when it enters the DN network'.….Target Date 05 March 2019) | 05-Mar-2019 06 Mar 2019 |  |  | Closed
03-0403 | Action | Gazprom to provide an amendment to Modification 0678I with submit the justification 80% for the Ireland discount and any analysis with the Modification. (Target Date 05 March 2019). | 05-Mar-2019 | Gazprom - Sinead Obeng (SO) | 06/03 - discount analysis is internal, will be discussed with NG. Business rulesa round wheeling in next mod amendment for discussion today 6th mar, updated compliance assessment for Art 9 for discussion today 6th mar. | Closed
04-0403 | Action | Joint Office to publish the draft Workgroup Report for Workgroup Participants to review. (Target Date 04 March 2019). | 04-Mar-2019 | Joint Office - Rebecca Hailes (RH) |  | Closed
05-0403 | Action | National Grid to review the forecast elements of the FCC values for Storage Sites IUK and BBL. | 04-Mar-2019 05 Mar 2019 | National Grid - Colin Williams (CWi) | NG clarified that no forecast values exist for these and this will continue. 06/03 - Awaiting Ofgem Letter 28/03 - Reviewed | Closed
06-0403 | Action | National Grid to review a) the treatment of closed sites and b) the effect on the FCC methodology and the potential for adaption in treatment of these sites in the FCC Methodology | 04-Mar-2019 | National Grid - Colin Williams (CWi) | Wil be incorporated into the sensitivity model, closed sites will not be removed from the model. A sense check will be considered and may be included in the FCC Methodology Statement. 06/03 - Awaiting Ofgem Letter 28/03 - Reviewed | Closed
01-2803 | Action | All parties to review the draft Workgroup Report Section 4.6 NTS Optional Charge Arrangements (page 37) and consider providing any required commentary for the Workgroup Report. Proposers to provide clarity of the arrangements for each of the Modifications. (Target Date 02 April 2019). | 02-Apr-2019 | All Workgroup | Due 02 April 2019 02/04 - Required commentary received from Nick Wye and Graham Jack | Closed
02-2803 | Action | Section 4.6 NTS Optional Charge Arrangements (page 37), National Grid to provide a summary to support the URL link provided. (Target Date 02 April 2019). | 02-Apr-2019 | National Grid - James Gudge (JG) | Due 02 April 2019 02/04 - Draft text provided by James Gudge which highlights what the analysis does. Full Optional Charge Analysis to be appended to the WGR Part I. 04/04 - Summary Provided | Closed
03-2803 | Action | National Grid to provide further clarity for the FCC and the technical application of the Demand Forecasting. (Target Date 02 April 2019). | 02-Apr-2019 04-Apr-2019 | National Grid - Colin Williams (CW) | Due 02 April 2019 02/04 - NG will provide text for WGR for Thursday 04 April | Carried Forward
01-0204 | Action | All Proposers to provide the Joint Office with a high-level overview of their analysis, and the key elements they wish to flag within the Part I of the Workgroup Report for Workgroup comments. (Target Date Friday 05 April 2019) | 2019-04-05 | All Workgroup |  | Pending
02-0204 | Action | Joint Office to formulate a table detailing all the additional documents provided by Proposers for reference within the Workgroup Report. (Target Date Monday 08 April 2019) | 2019-04-08 | Joint Office |  | Pending
03-0204 | Action | National Grid and Interconnector (PV) to re-consider Action 06-0403 and consider provide an appropriate update to the FCC Methodology Statement. (Target Date by Thursday 04 April 2019) | 2019-04-04 | National Grid | 03/04 - FCC Methodology Statement updated | Closed
04-0204 | Action | National Grid to provide the NTS OCC distance in Mode and Median Averages. (Target Date by Friday 05 April 2019) | 2019-04-05 | National Grid | 04/04 - Action update chased | Carried Forward
05-0204 | Action | Joint Office and SSE to consider how best to summarise the Customer Impact Analysis provided in Appendix 4 of Modification 0678C within the Workgroup Report. Joint Office and SSE to formulate a high-level overview of the analysis, and the key elements to be captured within Part I. (Target Date Friday 05 April 2019) | 2019-04-05 | Joint Office SSE | 04/04 - Summary received. Joint Office to incorporate text into the draft Workgroup Report. | Carried Forward
06-0204 | Action | DNs to consider and provide any additional commentary for the Workgroup Report to provide clarity on the impact of the change and cost forecasts. (Target Date Monday 08 April 2019) | 2019-04-08 | DNs | 04/04 - Initial Commentary Received and captured within draft Workgroup Report. Additional Commentary being considered. | Carried Forward
01-0304 | Action | National Grid to provide an explanation on how the current form of the FCC has been constructed with references to greatest of the five data sets and a view on why this is considered the best way. (Target Date Friday 05 April 2019) | 2019-04-05 | National Grid |  | Carried Forward
02-0304 | Action | Gazprom (SO) to provide the Joint Office with a high-level overview of the analysis for Modification 0678I, and the key elements they wish to flag within the Part I of the Workgroup Report. (Target Date Friday 05 April 2019) | 2019-04-05 | Gazprom (Sinead Obeng SO) |  | Carried Forward
03-0304 | Action | Centrica (GJ) to provide the link to the RIIO-T2 playback documents for the Workgroup Report Relevant Objective D, relating to maintaining the cost of the network. | 2019-04-05 | Centrica (Graham Jack GJ) |  | Carried Forward
04-0304 | Action | National Grid (PL) to confirm that V5.0 of the Comparison table (dated 27 March 2019) is the most current version and there isn’t a subsequent version to be published, | 2019-04-05 | National Grid (PL) | 03/04 Version 6.0 provided by National Grid on 03/04 and published | Closed
05-0304 | Action | DNs to provide explanation of the impact of interest on the cash flow difference because of the two-year lag when adjusting their charging revenues | 2019-04-05 | DNs |  | Carried Forward
01-0404 | Action | National Grid/Dentons to clarify the definition of ‘Fry’ within Annex B 1.6.1 for the monthly average and check that A&B are the correct way around within the provided formula. (Target Date 10 April 2019) | 2019-04-10 | National Grid/Dentons |  | Pending
02-0404 | Action | National Grid to provide confirmation to where the ‘Updated Forecast’ is defined/referenced. (Target Date 5pm 05 April 2019) | 2019-04-05 | National Grid |  | Pending
03-0404 | Action | Proposers to consider the Modification solutions to ensure the solution and legal text align with regards to the running period (Target Date 5pm 05 April 2019) | 2019-04-05 | All Proposers |  | Pending
04-0404 | Action | National Grid to confirm how they intend to manage the NTS OCC Methodology and the NTS OWC Methodology and whether these will be created and appended to the appropriate Modifications. (Target Date 5pm 05 April 2019) | 2019-04-05 | National Grid |  | Pending
05-0404 | Action | National Grid and the Proposers (0678DGHIJ) to agree and confirm which gas year and what figures should be used for the OCC Methodology. (Target Date 5pm 05 April 2019) | 05/04/2019 (5pm) | National Grid and Proposers of 0678DGHIJ |  | Pending
06-0404 | Action | Proposers to confirm if the Modifications should refer to RPI or CPI for indexation. (Target Date 5pm 05 April 2019) | 05/04/2019 (5pm) | All Proposers |  | Pending
07-0404 | Action | National Grid and Proposers to clarify the Business Rules for the Commitment Charge / Opting-Out of the Optional Rate. (Target Date 5pm 05 April 2019) | 05/04/2019 (5pm) | All Proposers |  | Pending
08-0404 | Action | Clarification required with Storengy (Alex Neild) to the intent of the interest systems within Section B 2.18.1 (b) | 05/04/2019 (5pm) | Storengy |  | Pending

## Lookups
Action
Decision
Issue
Risk