## Slide 1: CSS Consequential Programme Change Assurance March, 2019
Ahead of embedded assurance commencement, Xoserve’s Change Assurance team conducted a Healthcheck with two objectives:
Assess readiness for Stage Gate B (start-up) – no risk was identified and the Gate was passed successfully
With CSS C approaching Detailed Design, look beyond Gate B to overall Programme health
Since agreeing the Healthcheck findings, the CSS C Programme has addressed recommendations made, 4 findings have been closed, and plan-aligned completion dates agreed for all others.
No action is therefore requested from the change Management Committee and the following summary dashboard is provided for information.

## Slide 2: CSS C Programme Early Assurance Summary Dashboard
Area | Date | Change Project | RAYG by Area | CA1 – CA4 | Summary
Programme Delivery | March 2019 | CSS Consequential Programme Change Assurance | Overall Business Case Team Sponsorship Plan Governance Customer Scope and Solution Other | CA1 CA2 CA3 CA4 | A significant number of roles remain open in the Programme org structure. Although a resource model is in place and recruitment is in progress, there is a continuing risk of resources not being available when required, and of contractor engagement for urgently-required roles, in place of planned permanent resource. The Programme’s governance structure alongside existing Platform and functional Xoserve governance, needs to be consolidated and lean, to avoid duplication and unclear escalation and decision-making routes. The decision to bring design forward against a backdrop of requirement and solution uncertainty places risk on the HLD to DD transition, the mitigation and control of which needs to be clear in phase governance. There is a possibility of significant external scope change well into our Detailed Design phase and the Programme will need an effective Change Control process. Engagement of TCS for Detailed Design without significant prior Xoserve solution knowledge gives risk to Detailed Design and may impact response to scope change and delivery. The Programme needed to make clear how it will control the gap between Stage Gate governance and the actual lifecycle phase, which are not due to align until Gate C, end of design. This has been addressed and the finding closed.
2
10
15
0
Assurance was performed ahead of Stage Gate B (Startup), against which only minor gaps were noted, and Gate passed. As the Programme is transitioning from High-Level to Detailed design, the assurance also looked beyond Gate B to the wider health of CSS C, as reflected in the below findings, which have been updated to reflect progress since the Healthcheck.
Info Security
Business Readiness
Suppliers
Finances
Pocurement
Contract Management
2
9
12
0
At Healthcheck
Update 09/04/19