## Slide 1: UIG Task Force Progress Report
Change Management Committee 08/05/19

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  Task Force next steps

## Slide 3: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Attend UIG working group | 25/03/19 | Complete
Attend March Change Management Committee | 13/03/19 | Complete
Attend March Contract Management Committee | 20/03/19 | Complete
Attend UIG work group | 08/04/19 | Complete
Support Modification Development – All draft modifications have allocated sponsors | 08/04/19 - ongoing | Complete
Attend April Change Management Committee | 10/04/19 | Complete
Final walk through of AUG weighting factors (teleconference) for vote | 12/04/19 | Complete
Attend April UIG work group | 29/04/19 | Complete
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Executive Summary Update | w/c 29/04/19 | G
Draft 3.2.5 Modification(s) | 29/04/19 | G
Attend May Contract Management Committee | 01/05/19 | G
Customer Training Day - UIG | 03/05/19 | G
Attend May Change Management Committee | 08/05/19 | G
Attend May Contract Management Committee | 15/05/19 | G
Attend UNC Modification Panel (support draft mods) | 16/05/19 | G
Attend May UIG work group x 2 | 20&21/05/19 | G

## Slide 4: Plan on Page new
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
 | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | 
 | 01/04 | 08/04 | 15/04 | 22/04 | 29/04 | 06/05 | 13/05 | 20/05 | 27/05 | 03/06 | 10/06 | 17/06 | 24/06 | 01/07 | 08/07 | 15/07 | 22/07 | 29/07 | 05/08 | 12/08 | 19/08 | 26/08 | 02/09 | 09/09 | 16/09 | 23/09 | 30/09
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Draft Mods to support recommendations
Support Mod development
I
10/04 DSC ChMC
w/c 29/4 Exec Summary
I
08/05 DSC ChMC
I
12/06 DSC ChMC
03/05 Attend Customer Training Day
I
08/04 UIG WG
I
29/04 UIG WG
I
20&21/05 UIG WG
I
24/06 UIG WG
I
01/05 CoMC
I
15/05 CoMC
I
19/06 CoMC
I
10/07 DSC ChMC
I
07/08 DSC ChMC
I
11/09 DSC ChMC
I
17/07 CoMC
I
14/08 CoMC
I
18/09 CoMC
I
23/07 UIG WG
I
20/08 UIG WG
I
23/09 UIG WG
w/c 01/06/Exec Summary
w/c 01/07 Exec Summary
w/c 01/08 Exec Summary
w/c 02/09 Exec Summary
Review/draft updates to UIG user guide ongoing
w/c 23/09 Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan

## Slide 5: Recommendations - where we are
1 CR4868 in progress - TBC
1 ongoing engagement using existing MI
3 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total, 2 sponsored British Gas 0690 & 0691
25 Future review
4 review May
2 review June
6 review July
4 review August
6 lines PAC /Xoserve – covered under existing changes 4876 & 4795. 4 with Xoserve
3 lines MOD 0681 – EON
43 CLOSED
As at 30/4/19
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored
3 In progress
All future reviews include non task force related changes that are pending, defects with planned resolution dates, other options which may be considered if engagement/PAC reporting does not deliver results. (PAC can look to deliver these when PAC reporting is updated).
11 do nothing
2 BAU
7 completed
23 other options progressed
5 review November
4 review December
14 finding & recommendations = 95 recommendation lines
3 lines Xoserve drafted MODs 3.2.5
1 ongoing 3.2.5 option 3
Notes: 95 lines in recommendation tracker
10 new recommendation options for 3.2.5.
40 lines closed =
10 do nothing: 3.2.1 option 1, 3.2.2 option 1, 1 option 1, 12.1/12.3 option 1, 12.2 option 1, 3.2.8 option 1, 3.1 option1, 13.2.5 option 1, 2 option 1, 13.2.2 option 1.
Bau=2. 3.2.2 option 5. 3.2.8 option2
Completed =7. 2 option 2, 2 option 3, 13.2.2 option 2, 13.2.5 option 2, 13.2.5 option 3. 3.2.1 option 2, 3.1 option 2. CR delivered – 3.2.1 option 2 - CR4867 sites over 58.6m kWh that need reconfirming
Progressed another option =21. 1 option 5,8. 3.2.1 option 5,8,9. 3.2.2 option 2,3,4,7a,8. 12.1/12.3 option 5,7,8,9b. 3.2.8 option 6, 10, 11. 3.1 option 3,4,8,9.
7 lines PAC/Xoserve action = 3.2.1 option 3 & 4 – with Xoserve/pac to deliver. 12.1/12.3 option 6 with xoserve/pac. 3.2.2 option 10 covered under 4876. 1 option 4 covered under 4795. 12.1&12.3 option 3 covered under 4876 . 3.2.8 option 5 covered under 4876.
3 lines EON/Xoserve MOD = 12.1&12.3 option 9a, 10, & 11.
9 lines Scottish power sponsored mod – 12.2 options 2,3,4,5,6,7,8,9&10.
2 lines BG sponsored mod 3.2.1 options 6,7
1 line Total sponsored mod 3.2.1 option10.
2 lines in progress =
1 ongoing engagement 12.1&12.3 option 2,
1 CR in progress – 1 option 2 - CR4868 class 1&2 read rejections
21 lines for future review =
2 review April 3.2.2 option6, 7b.
4 review May 2 option 5 & 6. 1 option 3. 1 option 7 with xoserve/pac to deliver
4 review July 3.2.1 option 11. 3.2.8 option 3 & 4. 12.1&12.3 option 4.
4 review November 3.1 option 6, 2 option 7. 3.1 option 5 & 7. (1 CP in progress – CP4866 removal of validation on uncorrected read – review in Nov 3.1 option 7), (1 CP in progress - 3.1 option 5 – CP4853 manual workaround starts April 2019)
4 review December 3.2.8 option 7, 8 & 9. 2 option 4.
2 review June 3.2.2 option 9. 1 option 9.
1 review August 1 option 6.

## Slide 6: Overview Of Task Force Funding
TO BE PROVIDED REAL TIME ON THE DAY AND WALKED IN

## Slide 7: Task Force Next Steps
Use the UNC UIG Work Group as the mechanism to share progress on all recommendations where options residing with Xoserve.
Provide updates to the “Recommendation Tracker” in line with UNC UIG Work Group timescales.
Continue analysis on investigation lines & publish investigation tracker updates fortnightly.
Publish any new findings/recommendations drawn from investigation lines which are currently “work in progress” when completed.
Engage with customers to find sponsors for draft Modifications in line with recommendation options for 3.2.5 Inaccurate or out of date AQs – impact of rolling AQ.
Continue the customer engagement, progress the CPs & CRs raised to support the recommendation options agreed at 28th January UIG-Recommendation session.
Supporting MOD development to progress all sponsored and draft modifications.
Continue the development of existing non Task Force changes 4876 & 4795 to support the PAC report recommendations.