## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
NA | NA | Change Pack Publication | 2008.2 | 2018-07-13 | 2018-07-27 | 2018-08-03 | X | X | X | X | X | NA | 31/05/2019 - Go Live of the online Change Pack Mechanism was on 10th May 2019; we appreciate there was some formatting errors with the documents; this was caused by training errors. We also need to make a tweak to the response form for one of the Change Pack templates. If you had any feedback on how it works, we would be very interested in hearing it.

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
N/A | N/A | Administrative change required to the UMR File Hierarchy to correct the ‘Direction of file’ travel | 2315.2 - RJ - ES | 2019-05-10 | 2019-05-24 | N/A | X |  |  |  |  | 2334 | N/A - for information | 2019-05-28 | The UMR file format hierarchy is the file we receive from Shippers with their Class 4 meter reads. This file format hierarchy incorrectly states the direction of the file as ‘CDSP to Shipper’ however this should be ‘Shipper to CDSP’. The purpose of this change is to amend the incorrect direction of the file for the UMR hierarchy to ‘Shipper to CDSP’. We received one response which was in support of this change.
N/A | N/A | 2020 Release Implementation Dates | 2315.3 - RJ - ES | 2019-05-10 | 2019-05-24 | N/A | X | X | X | X |  | 2334 | 2019-06-12 | N/A | We sought industry consultation on the proposed Release Implementation Dates for 2020: Friday 28th February 2020; Friday 26th June 2020 ;Friday 6th November 2020 We received one response which was in support of the proposed release dates.

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 8th May 2019
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
4679 | N/A | Requiring a Meter Reading following a change of Local Distribution Zone or Exit Zone | 2293.8 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  |  |  |  | 2309 | 2019-05-08 | 2019-11-08 | This Change is within the scope of the November 2019 Release. The Design Change Pack has closed out and Xoserve seeks approval of the Detail Design specification.
4725 | N/A | New Read Reason type for LIS Estimate Readings | 2293.9 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  |  |  |  | 2309 | 2019-05-08 | 2019-11-08 | This Change is within the scope of the November 2019 Release. The Design Change Pack has closed out and Xoserve seeks approval of the Detail Design specification.
4621 | N/A | Suspension of the Validation between Meter index and Unconverted Index | 2293.7 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  |  |  |  | 2309 | 2019-05-08 | 2019-11-08 | This Change is within the scope of the November 2019 Release. The Design Change Pack has closed out and Xoserve seeks approval of the Detail Design specification.
4376 | 678/597/611 | GB Charging & Incremental (IP PARCA) Capacity Allocation Change Delivery (2019) | 2293.4 - RJ - ES | 2019-04-12 | 2019-04-30 | 2019-04-30 | X |  | X |  |  | 2309 | 2019-05-08 | 2019-09-08 | The purpose of this Change Pack was to notify System Users of the changes that will be deployed on 8th September 2019 in readiness for a 1st October 2019 effective date.
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
TBC | CMS Application DR Outage | 06/07/2019 07/07/2019 | 00:00 BST 00:00 BST | 06/07/2019 07/07/2019 | 07:00 BST 07:00 BST | Xoserve will be carrying out a scheduled Disaster Recovery (DR) exercise for CMS Application which will be carried out during the CMS Maintenance window. The first row is for the fail over; the second row is for the fail back | 2019-06-12
TBC | UK Link Portal and CMS | 2019-08-16 | 23:00 BST | 2019-08-17 | 10:00 BST | The purpose of this notification is to provide Change Management Committee with an early notification of the UK Link Disaster Recovery Tests in 2019. Further communications regarding the impact of the test will be issued shortly. | 2019-05-08
TBC | UK Link Portal | 2019-08-17 | 23:00 BST | 2019-08-18 | 07:00 BST | The purpose of this notification is to provide Change Management Committee with an early notification of the UK Link Disaster Recovery Tests in 2019. Further communications regarding the impact of the test will be issued shortly. | 2019-05-08