## Slide 1: Data Office POAP June/July 2019

## Slide 2: Update on current Data Office change pipeline
There has been significant work carried out in the Data Office with the Customer Change Team and Advocates to focus on the roadmap for delivering high priority Shipper Pack and PARR Reporting changes.
In addition some expertise in the Data Office has been supporting the work in the AML/ASP Taskforce which has resulted in a knock on delay in the delivery of some of the changes currently in the Data Office pipeline for delivery.
In order to ensure that we continue to move forward with changes in the pipeline as quickly as possible, internally Xoserve continue to review the priority of existing changes in the pipeline along with any new changes that are received.

## Slide 3: Data Office POAP
Below shows the Change Proposals or externally impacting change requests that are currently in delivery with the Data Office and have planned releases:
XRN Number | Change Title |  |  | Delivery Month |  |  | RAG Status
 |  | April/ May | June/ July | Aug/ Sept | Oct/ Nov | Dec/Jan | 
XRN4835 | Address Profiling and Reporting (css extract pre go live) |  |  |  |  |  | Due to be complete end of June
XRN4790 | Introduction of winter read/consumption reports (MOD652) PARR reporting element |  |  |  |  |  | Due to be complete end of July
XRN4841 | MAP Access to UKL via API (JMDG Use case 58) – API access on back of a MOD |  |  |  |  |  | Due to be complete end of June
XRN4886 | MAM Reporting (MOD297) supporting report for MOD |  |  |  |  |  | Due to be complete end of June
XRN4898 | Additional data source for UIG visualisation |  |  |  |  |  | Due to be complete end of July
XRN4795 | Amendments to the PARR (520a) reporting |  |  |  |  |  | Due to be complete end of December

## Slide 4: Data Office changes in Capture
The table below shows all change proposals and externally impacting change requests which are currently in capture and are either new requests, we are gathering requirements or we are waiting for solution options from the Data Office:
CP/CR | XRN No | Change Details | Priority | Customer Benefit | Indicative Delivery Date
CR | 4868 | UIG Recommendation – Report for class 1, class 2 read rejections | 1 | To monitor AQ movements and percentage of AQ’s calculated per user per month | December 2019
CP | 4860 | National Temporary UIG | 2 | Information for Shippers to see how reconciliation is affecting UIG over time | December 2019
CP | 4738 | Shipper portfolio update proposed formula year AQ/SOC | 8 | Inform Shippers of their proposed formula year AQ/SOQ values when produced. | December 2019 (based on need date)
CP | 4876 | Changes to PAR Reporting (supporting UIG) | 4 | Provide further data to PAFA to aid analysis on performance reporting and aid in shipper performance as a first indication of any issues before PAC | TBC
CP | 4789 | Shipper packs – glossary updates and reporting changes from AQ to product class | 5 | The shipper packs should align further to PAC reporting and aid shipper performance | TBC
CP | 4779 | MOD0657S – Adding AQ reporting to PARR Reports | 6 | Monitor AQ movements and percentage of Aqs calculated per month by user, can access performance across the industry and engage with the poorer performers with an aim to get industry performance increased. | TBC
CP | 4859 | Increasing MAM access to CDSP data to mitigate reduced MAM appointment timescales | 7 | Provide MAM’s with alternative source for asset data | TBC