## Slide 1: UIG Task Force Progress Report
Change Management Committee 12/06/19

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  Advanced machine learning options
  Task Force next steps

## Slide 3: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Executive Summary Update | w/c 29/04/19 | Complete
Draft 3.2.5 Modification(s) | 29/04/19 | Complete
Attend May Contract Management Committee | 01/05/19 | Complete
Customer Training Day - UIG | 03/05/19 | Complete
Attend May Change Management Committee | 08/05/19 | Complete
Attend May Contract Management Committee (cancelled) | 15/05/19 | Complete
Attend UNC Modification Panel (support draft mods) | 16/05/19 | Complete
Attend May UIG work group x 2 | 20&21/05/19 | Complete
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Executive Summary Update | w/c 03/06/19 | G
Attend May Change Management Committee | 12/06/19 | G
Attend May Contract Management Committee | 19/06/19 | G
Attend June UIG Work Group | 24/06/19 | G
Attend UIG Work Group Mod 0681 | 07/06/19 | G
Support Mod development (All) | June ongoing | G
Development of automated UIG reporting | End of June | G

## Slide 4: Plan on Page new
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
 | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | 
 | 01/04 | 08/04 | 15/04 | 22/04 | 29/04 | 06/05 | 13/05 | 20/05 | 27/05 | 03/06 | 10/06 | 17/06 | 24/06 | 01/07 | 08/07 | 15/07 | 22/07 | 29/07 | 05/08 | 12/08 | 19/08 | 26/08 | 02/09 | 09/09 | 16/09 | 23/09 | 30/09
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Draft Mods to support recommendations
Support Mod development
I
10/04 DSC ChMC
w/c 29/4 Exec Summary
I
08/05 DSC ChMC
I
12/06 DSC ChMC
03/05 Attend Customer Training Day
I
08/04 UIG WG
I
29/04 UIG WG
I
20&21/05 UIG WG
I
24/06 UIG WG
I
01/05 CoMC
I
15/05 CoMC
I
19/06 CoMC
I
10/07 DSC ChMC
I
07/08 DSC ChMC
I
11/09 DSC ChMC
I
17/07 CoMC
I
14/08 CoMC
I
18/09 CoMC
I
23/07 UIG WG
I
20/08 UIG WG
I
23/09 UIG WG
w/c 01/06/Exec Summary
w/c 01/07 Exec Summary
w/c 01/08 Exec Summary
w/c 02/09 Exec Summary
Review/draft updates to UIG user guide ongoing
w/c 23/09 Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan

## Slide 5: Recommendations - where we are
1 ongoing 3.2.5 option 3
2 CR4868 in progress - TBC
1 ongoing engagement using existing MI
3 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total 0692), 2 sponsored British Gas 0690 & 0691
22 Future review
3 review June
6 review July
4 review August
6 lines PAC /Xoserve – covered under existing changes 4876 & 4795. 4 with Xoserve
3 lines MOD 0681 – EON
44 CLOSED
As at 21/05/19
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored
All future reviews include non task force related changes that are pending, defects with planned resolution dates, other options which may be considered if engagement/PAC reporting does not deliver results. (PAC can look to deliver these when PAC reporting is updated).
11 do nothing
2 BAU
8 completed
23 other options progressed
5 review November
4 review December
14 finding & recommendations = 95 recommendation lines
3 lines Xoserve drafted MODs 3.2.5
1 Trigger T51 files - 2 option 5
5 In progress

## Slide 6: Overview Of Task Force Funding

## Slide 7: Machine Learning Next Steps - Overview
The UIG Task Force and the UIG Analytics Partner have demonstrated that using advanced Neural Network Machine Learning models can reduce Base Level UIG by up to 70% and Volatility by up to 30%
  See Investigation Item 13.2.6: NDM Algorithm - Advanced Machine Learning
We have tested this on EUC 01 for 12 LDZs
There are options for where we can go next with this line of investigation
  We will Discuss these with DESC on 10th June 2019.

## Slide 8: Options for Next Steps
Xoserve will host a Machine Leaning Discovery Day to discuss the benefits, considerations and implementation challenges of using Machine Learning algorithms to allocate NDM Energy
We are currently costing these options with our Analytics Partner
  Rerunning the Neural Network performance comparison against the existing NDM algorithm for more recent Gas Days (propose 01/06/2018 – 31/05/2019)
  Construct an API / Sandbox environment for Shippers to test Neural Network predictions using their own data
  Develop Neural Network models for EUCs 2-8 to demonstrate whether the benefit can be seen across the whole market.

## Slide 9: Task Force Next Steps
Use the UNC UIG Work Group as the mechanism to share progress on all recommendations where options residing with Xoserve.
Provide updates to the “Recommendation Tracker” in line with UNC UIG Work Group timescales.
Continue analysis on existing investigation lines, identify any new investigation lines & publish investigation tracker updates as required.
Publish any new findings/recommendations drawn from investigation lines which are currently “work in progress” when completed.
Supporting MOD development to progress all live and draft modifications.
Develop complex machine learning options with industry