## 1. Dashboard Summary
Dashboard Summary for CoMC 17th July 2019
Issue | Customer Impact | Status | Resolution Plan
Amendment Invoice | Exception, esclusion and defect backlog on track to meet new sla's agreed with suppliers |  | Working towards operating within SLA for each areas, as defined in the amendment Invoice delivery status.
UIG | UIG volatility between GFD - GFD+5 |  | All taskforce milestones tracking to plan
AQ | Two new issues raised. Potential impact to transportation rate applied if incorrect AQ moves the MPRN to a different pricing band. May affect FYAQ applied for Class 3 & 4 meter points. |  | Issue 1: affecting approx. 121,000 MPRNs. Plan to correct data during September & re-calc AQs effective from 1st October. Issue 2: Affecting 32 MPRNs in Class 1, 2 & 3. Under analysis to determine cause. Once confirmed plan to correct will be shared.
Data Enquiry / CMS & Portal Services Performance Issues | Unable to access DES and carry out tasks on Portal & CMS. Five P2s relating to system availability & Performance issues raised in June 2019. |  | We are currently undertaking a Service Review of Portal, due to the number of P2s in recent months. The purpose of this review is to collectively review the issues to see if there are any corrolations or proactive steps that can be taken. We are still working through all the information to ensure we have a complete picture. Once known this will be shared including actions & recommendations from review.
Portfolio File issued to DNs & IGTs | Incomplete (for IGTs) and incorrect (DNs) data being issued in portfolio files. |  | Cause confirmed. Code fix implemented to ensure daily delta files are correct. Data fix to be completed by 17th July 2019 & refresh/re-synch files to be issued on 19th July (approach to be agreed with DNs & IGTs individually)
Key:
Issue identified, issue still under analysis before plan can be confirmed.
Issue identified, analysis complete, plan in place but at risk.
Issue identified, analysis complete, plan in place and on target for completion.

## 2. Monthly Reporting Summary
Monthly Reporting Summary- June 19
Transportation Invoices
| Invoice | 2019-05-01 | 2019-04-01 | 2019-03-01 | 2019-02-01 | 2019-01-01 | 2018-12-01 | 2018-11-01 | 2018-10-01 | 2018-09-01 | 2018-08-01 | 2018-07-01 | 2018-06-01 | 2018-05-01
| LDZ Capacity (CAZ) | 326551233.52 | 316051672.36 | 311032408.5 | 280690666.66 | 310573206.23 | 309858247 | 303715362.33 | 313359948.83 | 302866760.19 | 312780813.69 | 312562745.62 | 302299412.99 | 312174512.16
| Commodity (COM) | 27064328.63 | 34196796.84 | 38126303.74 | 40096892.48 | 52085770.33 | 42951905.58 | 37862420.69 | 29476349.27 | 17528307.3 | 15048321.28 | 14290600.7 | 14591606.04 | 19449237
| Amendment (AMS) | -2794686.71 | -2215857.55 | 5789362.28 | 245268.62 | -1327183.91 | 374357.97 | -765656.96 | 58182.64 | -385853.99 | 830443.17 | 1483244.96 | 2213969.29 | 2024085.07
| Meter Asset (MAS & ADP) | £203,714.72, | 160240.77 | 191176.78 | 177134.91 | 196114.87 | 196114.66 | 189786.88 | 196114.17 | 189788.22 | 200263.88 | 200707.69 | 194233.54 | 200707.08
| NTS Entry Capacity (NTE) | 1324966.45 | 1274118.19 | 8064487.69 | 9130603.41 | 10143131.93 | 8796213.72 | 8064487.69 | 8332609.71 | 1760935.51 | 1735803.71 | 1735803.71 | 1621553.61 | 1599795.55
| NTS Exit Capacity (NXC) | 14092535.89 | 13650554.62 | 13789980.96 | 12803012.32 | 13947987.58 | 13770471.59 | 13789980.96 | 13807265.85 | 18113875.74 | 18720256.49 | 18720256.49 | 18117525.2 | 18702620.75
| Contract Management Reporting June 2019 | [8 empty] | Summary of Issues during the Period June 2019
9 P2 Incidents raised during June 2019 ~2 P2's raised relating to Contract Management System (CMS) performance issues & unavailability for 3 hours ~1 P2 raised relating to performance issues with Data Enquiry Service (DES). Service review being carried out ~2 P2s relating to AMT Marketflow of whic one resulted in a KPI failure Class 1 daily reads files not issued to shippers within SLA due to AMT server not processing outgoing files ~2 P2's for Gemini resulting in Gas Allocations & UIG not calculated & visible in Gemini ( GFD 8th and 16th June) ~2 P2's as customers unable to access Xoserve Portal Services Site Emergency Contact details ~Where a shipper is providing new emergency contact details for a site, the National Grid Emergency File (EWS) is being populated witht he updated details as required, however it also contains the previous contact number within the 'Alternative Contact 2' field Where a shipper is providing new emergency contact details for an IGT site, the Daily Delta File (IDL) is not containing any emergency contact details
| Priority 1 KPIs |  |  | 0 |  | Third Party Services Sold |  | 34211
| Priority 2 KPIs |  |  | 1 |  | Additional Services Sold |  | 4000
| UK Link Availability (Gemini) |  |  | 100%
| UK Link Availability (Non-Gemini) |  |  | 100%
Highlights UK Link planned releases - Successful implementation of XRNs 4687, 4687 and 4670 on 29th June Announced details of a Non-Standard Sites Training day to be held on 5th September Class 3 Supply Point Migration Workshop taking place on Friday 12th July
Supply Point Information
| Class | 2019-06-01 | 2019-05-01 | 2019-04-01 | 2019-03-01 | 2019-02-01 | 2019-01-01 | 2018-12-01 | 2018-11-01 | 2018-10-01 | 2018-09-01 | 2018-08-01 | 2018-07-01 | 2018-06-01
| Class 1 | 453 | 446 | 445 | 441 | 441 | 441 | 438 | 437 | 433 | 429 | 427 | 427 | 425
| Class 2 | 606 | 610 | 617 | 620 | 633 | 638 | 639 | 636 | 645 | 650 | 655 | 658 | 668
| Class 3 | 167558 | 127156 | 103966 | 101910 | 98369 | 95568 | 95544 | 95286 | 87615 | 88860 | 78827 | 125491 | 125650
| Class 4 | 24255515 | 24,2758,72 | 24282129 | 24264887 | 24197837 | 24173580 | 24160382 | 24146202 | 24128941 | 24110132 | 24101362 | 24038014 | 24022437
| Smart Meters | 2019-06-01 | 2019-05-01 | 2019-04-01 | 2019-03-01 | 2019-02-01 | 2019-01-01 | 2018-12-01 | 2018-11-01 | 2018-10-01 | 2018-09-01 | 2018-08-01 | 2018-07-01 | 2018-06-01
| % of the total of meters installed that are Smart Meters | 31.65% | 31.04% | 30.59% | 29.98% | 29.65% | 28.89% | 28.29% | 27.85% | 27.01% | 26.37% | 25.57% | 24.88% | 24.17%

## 3. KPI Tracker June 2019
KPI Tracker for June 2019
Section of DSC | Reference | KPI Obligation | Performance Standard | Delivery Mechanism | Volume Constraints | How Service is Delivered | UNC Ref | KPI category (1-4) | Business Area | Incoming File | Outgoing File | Reporting Month | RAG Status | External Comments / Details (Where Failure Has Occurred) | What is remedial action? | Customer contact (Service Desk Ticket / Query / Phone call etc ) | RAG Status updated on | Comments updated on | Remedial action updated on | Last updated on | Column1 | Column2 | Column3
Part A Direct Service - Code Services | DS-CS SA1 - 02 | Following receipt of a Supply Point Enquiry, send Enquiring User a response, acceptance or rejection notification, where accepted, the relevant information | 100% within two (2) Supply Point System Business Days of receipt | File via IX | N/A | UKLink Communication | TPD G1.16 | 1 | Business Operations: CDS | NOM | NMR | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 04 | Following receipt of a Supply Point Nomination, send Proposing User a Supply Point Offer or a rejection notification or send User and the relevant Network Operator a Referral notice. | 100% within two (2) Supply Point System Business Days of receipt | File via IX | N/A | UKLink & Portal | TPD G2.4.1,G2.3.4, G2.3.5, G2.3.6, G2.3.7, G2.3.8, G2.3.9, G5.4.2 G2.1.2(a) | 1 | Business Operations: CDS | NOM | NMR | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 05 | Following receipt of the Referral response from the Network Operator, send Proposing User a Supply Point Offer or rejection notification | 100% within two (2) Supply Point System Business Days of receipt of a response to the Referral from the Network Operator | File via IX | N/A | UKLink Communication | TPD G2.3.4 (b), G2.3.8, G2.3.9 | 1 | Business Operations: CDS |  | NRF | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 06 | Following the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity as a result of a Ratchet at any time prior to the submission of a Confirmation by the Proposing User, send a notification that the Supply Point Offer has lapsed | 100% within two (2) Supply Point Business Days of the prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity (when the Ratchet is valid after GFD+5) | File via IX | N/A | UKLink Communication | TPD G2.4.5 (a) | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 07 | Inform the Proposing User of the Prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity as a result of a Capacity Revision Application | 100% within 5 Supply Point Systems Business Days after the Prevailing Supply Point Capacity becoming greater than the Offered Supply Point Capacity as a result of a Capacity Revision Application | File via IX | N/A | UKLink Communication | TPD G2.4.6 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 08 | Following a change in the Formula Year AQ (FYAQ) or End User Category (EUC) for a Proposed Supply Point where the Offer remains valid, send the Proposing User notification that the FYAQ or EUC has changed | 100% within two (2) Supply Point Systems Business Days of the change to the FYAQ or EUC | File via IX | N/A | UKLink Communication | TPD G2.4.7 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 09 | Following receipt of a Supply Point Confirmation send Proposing User notice of the acceptance or rejection | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX | N/A | UKLink Communication | TPD G2.5.11, G2.5.5, G2.6.2 and G2.6.3 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 11 | Following receipt of a valid Supply Point Confirmation where a Supply Point Withdrawal has not been submitted, send existing User notice of the Confirmation and the Proposed Registration Date | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX | N/A | UKLink Communication | TPD G2.8.1(a) | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 12 | Following receipt of a Supply Point Objection where the User is required to declare their identity, notify the Proposing User of the Objection, identify of the Objecting User and, where the Objection was raised at the request of the Consumer, reason for the Objection | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX | N/A | UKLink Communication | TPD G2.8.3(b), (c ), (d) and G2.8.4(b) | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 13 | Following receipt of a Supply Point Objection, send User notice of acceptance or rejection | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX | N/A | UKLink Communication | TPD G2.8.3(d) | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 14 | Following receipt of Supply Point Objection which has not been withdrawn by the Objection Deadline, send each existing Registered User notice that the Confirmation has lapsed | By not later than one (1) Supply Point Systems Business Day before the Proposed Supply Point Registration Date | File via IX | N/A | UKLink Communication | TPD G2.8.6 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 15 | Where the Supply Point has been withdrawn by the existing User, send Proposing User notice of Supply Point Confirmation being effective and the information in relation to the Supply Point including the Valid Meter Reading for the latest Read Date, in the case of a Class 1 or 2 Supply Point, for which Exit Close-Out has occurred. | By not later than one (1) Supply Point Systems Business Day before the Proposed Supply Point Registration Date | File via IX | N/A | UKLink Communication | TPD G2.8.8(a) & G2.9.2 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 16 | Send Existing Registered User notice of effective Supply Point Confirmation and details of the identity of the new Registered User and Supplier | By not later than one (1) Supply Point Systems Business Day before the Proposed Supply Point Registration Date | File via IX | N/A | UKLink Communication | TPD G2.8.8(b) | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 17 | Following receipt of a Supply Point Withdrawal, send notice of acceptance or rejection. For Shared Supply Meter Points, inform each Sharing Registered User notice of the Withdrawal acceptance. | 100% within two (2) Supply Point Systems Business Days of receipt | Template via email | N/A | UKLink Communication | TPD G3.1.2 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 18 | Following receipt of a withdrawal notification where there is a Confirmation that will become effective, send notification to the Withdrawing User of the Confirmation | 100% within two (2) Supply Point Systems Business Days of acceptance of the Withdrawal Notice | File via IX | N/A | UKLink Communication | TPD G3.1.4 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 19 | Following receipt of a Withdrawal notification for a SSMP, send other Sharing Registered Users notice of the Withdrawal | 100% within two (2) Supply Point Systems Business Days of the receipt of the Withdrawal Notice | Template via email | N/A | UKLink Communication | TPD G3.1.5 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 25 | Following receipt of a SSMP Nomination from Proposed Sharing Users or User Agent, send acceptance or rejection of the request. Where accepted send Supply Point Offers to each Sharing Registered User and the User Agent, if appointed. | 100% within two (2) Supply Point System Business Days of receipt of the request and where submitted to the Network Operator, within two (2) Business Days of receipt from the Network Operator | Template via email | 40 per calendar month | UKLink - conventional Notice | TPD G1.7.1, G1.7.6, G1.7.2(d)(i) G1.7.11 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 29 | Following a request to cancel a Supply Point Confirmation, send Proposing User notice of acceptance or rejection and, for accepted requests, send Registered User notice of the cancellation | 100% within two (2) Supply Point Systems Business Days of receipt of request | File via IX | N/A | UKLink Communication | TPD G2.8.1( c) | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 30 | Following a request to withdraw a Supply Point Objection, send Objecting User notice of acceptance or rejection, and for accepted requests, send notice to the Proposing User of the withdrawn Objection | 100% within two (2) Supply Point Systems Business Days of receipt of request | File via IX | N/A | UKLink Communication | TPD G2.8.5 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 53 | Following receipt of a Shared Supply Meter Point Confirmation from each Sharing Registered User, send each Proposing Sharing Registered User notice of acceptance or rejection and where rejected the reason for rejection | 100% within two (2) Supply Point Systems Business Days of receipt | Template via email | 40 per calendar month | Conventional Notice | G1.7 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA1 - 54 | Following receipt of a Shared Supply Meter Point withdrawal notification from each Sharing Registered User, send each proposing Sharing Registered User notice of acceptance or rejection and where rejected the reason for rejection | 100% within two (2) Supply Point Systems Business Days of receipt | Template via email | 40 per calendar month | Conventional Notice | G1.7.10 | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA2 - 01 | Following receipt of an Operational Standards of Service (SoS) query from a Shipper, record, investigate & resolve the query | a) Resolve 80% of User Standards of Service Queries within 4 Business Days within the calendar month (except where the Query Type is DUP) b) Resolve 80% of User Standards of Service Queries within 4 Business Days within the calendar month (except where the query type is DUP) for 90% of Users c) Resolve 95% of User Standards of Service Queries within 10 Business Days within the calendar month d) Resolve 95% of User Standards of Service Queries within 10 Business Days within the calendar month (except where the query type is DUP) for 95% of Users e) Resolve 98% of User Standards of Service Queries within 20 Business Days within the calendar month f) Resolve 98% of User Standards of Service Queries within 20 Business Days within the calendar month (except where the query type is DUP) for 100% of Users g) Valid re-submitted queries (PSQ's) do not exceed more than 1% within the calendar month | CMS | 3,500 per calendar month | CMS | TPD S4.7 and chapter 5 of the Standard of Services Query Management Operational Guidelines TPD Section G1.9.7, G1.9.8 and G1.1.7 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA2 - 03 | Following receipt of an Operational Non Standards of Service (SoS) query, record, investigate & resolve the query | Resolve 50% of User non standards of Service queries within 10 Business Days within the calendar month for 90% of Users Resolve 90% of User non standards of Service queries within 20 Business Days within the calendar month for 95% of Users Resolve 95% of User non standards of Service queries within 40 Business Days within the calendar month for 100% of Users | CMS | 1,200 per calendar month | CMS | TPD G1.9.8 | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA2 - 04 | Following receipt of a query from a Network Operator relating to data held on the Supply Point Register, record, investigate & resolve the query | a) Resolve 50% of Network Operator queries within 10 Xoserve days within the calendar month for 100% of Network Operators b) Resolve 70% of Network Operator queries within 20 Xoserve days within the calendar month for 100% of Network Operators c) Resolve 90% of Network Operator queries within 40 Xoserve days within the calendar month for 100% of Network Operators d) Resolve 100% of Network Operator queries within 80 Xoserve days within the calendar month for 100% of Network Operators | CMS | 600 per calendar month | CMS | TPD G1.9.8 | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA3 - 01 | Following receipt of data which must be recorded in the Supply Point Register, send notice of acceptance or rejection of the request and for accepted requests, record or update the data | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX |  | UKLink Communication | TPD Sections G, M and Q G2.5.10 G3.7.2 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA5 - 15 | Following receipt of a Class 2 Meter Reading, Updated Meter Reading or Check Read, validate the read & notify the User of the outcome of the validation, for accepted reads, record as a Valid Meter Reading or Check Read | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX |  | UKLink Communication | M5.1.6 M5.3.5(b)(ii) M5.12 (except 5.12.9) M5.14.1 M5.16 M5.13.13 M5.13.14 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA5 - 16 | Following receipt of a Class 3 or 4 Meter Reading, Updated Meter Reading or Check Read, validate the read & notify the User of the outcome of the validation, for accepted reads, record as a Valid Meter Reading or Check Read | 100% within two (2) Supply Point Systems Business Days of receipt | File via IX |  | UKLink Communication | M5.1.6 M5.3.5(b)(ii) M5.12 (except 5.12.9) M5.14.1 M5.16 M5.13.13 M5.13.14 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA5 - 21 | Generate an estimated Opening Meter Reading for a Class 2 Supply Meter Point & provide to the relevant User | 100% on the 6th Day after the Supply Point Registration date | File via IX | 250 per Business Day | UKLink Communication | M5.13.7(b), 5.13.9 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA5 - 22 | Generate an estimated Opening Meter Reading for a Class 3 Supply Meter Point & provide to the relevant User | 100% on the 6th Day or the 15th day after the Supply Point Registration date depending on the outgoing Supply Point Class. | File via IX | 250 per Business Day | UKLink Communication | M5.13.7(c) 5.13.9 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA5 - 23 | Generate an estimated Opening Meter Reading for a Class 4 Supply Meter Point & provide to the relevant User | 100% on the 6th Day or the 15th day after the Supply Point Registration date depending on the outgoing Supply Point Class. | File via IX | 250 per Business Day | UKLink Communication | M5.13.7(c), 5.13.8, 5.13.9, | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA6 - 11 | Following receipt of a LDZ DM Capacity Revision Application, send User notice of acceptance or rejection of the request, for accepted requests send revised Supply Point Capacity or send User and the Network Operator a Referral notice. | Submit 100%; where a capacity reduction is required, within five (5) Supply Point System Business Days of receipt of application from the User; or where a feasibility assessment is required, notify the User if approved or rejected no later than the 2 Supply Point Systems Business Day following receipt of the Referral from the Network Operator | File via IX |  | UKLink Communication | TPD G5.1.7, G5.1.8, G5.1.10, | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA6 - 17 | Notification to the User of the revised AQ and, where applicable, if the AQ has crossed the threshold requirement | 100% by no later than 5 Business Days before the end of the AQ Calculation Month. | File via IX |  | UKLink Communication | TPD G1.6.6 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA6 - 18 | Following receipt of an AQ Correction that has failed validations, notify User that rejected with reason. | 100% within 2 Supply Point Business days of the request | File via IX |  | UKLink Communication | TPD G1.6.23, G1.6.25 and G1.6.26 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA6 - 19 | Following receipt of an AQ Correction that has passed validations, a) notify User confirming acceptance, b) amend the AQ and notify the User of the AQ . | a) 100% of the acceptance notification within 2 Supply Point Business days of the request b) 100% of the new AQ by no later than 5 Business Days before the end of the AQ Calculation Month. | File via IX |  | UKLink Communication | TPD G1.6.23,G1.6.25 and G1.6.27 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA6 - 20 | Amend the AQ & notify the User following receipt of an accepted AQ Correction for a New Supply Meter Point from a User before the Supply Point Registration Date | 100% of the new AQ by no later than 5 Business Days before the end of the AQ Calculation Month. | IX |  | UKLink Communication | TPD G1.6.29 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA12 - 01 | Record the Supply Meter Point Reference Number (MPRN) following receipt of a valid request from a Utility Infrastructure Provider (UIP) | Record 95% of MPRNs within D+1 of receipt (before 3pm) Record 100% of MPRNs within D+3 of receipt (before 3pm) Excluding SSMP and DM CSEPs | CMS | 645 per business day | CMS or conventional Notice | TPD G7.3.1 | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part A Direct Service - Code Services | DS-CS SA17 - 01 | Send all UK Link System Users a list of all Business Days and Supply Point Systems Business Days for the following calendar year | 100% by 30 September in each calendar year |  |  | Conventional Notice or email | TPD G1.10.3 | 3 | Service Development |  |  | 2019-06-01 | On Track
Part B Direct Service - Non Code Services | DS-NCS SA18-06 | Send the Allocation Agent for a SSMP (not telemetered) the allocated volume & energy for the previous day | 100% by 16.30 on the day following the Gas Day | File via IX |  | UKLink Communication |  | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part B Direct Service - Non Code Services | DS-NCS SA18-07 | Send the User notification of the due date for a Meter Inspection | 100% by not later than four (4) months prior to the date by which the meter inspection must be carried out | File via IX | 5,000 per calendar month | UKLink Communication |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA2-01 | Following receipt of a valid Standard of Service financial query; record investigate & resolve the query | a) Resolve 80% of User Standards of Service Queries within 4 Business Days within the calendar month (except where the Query Type is DUP) b) Resolve 80% of User Standards of Service Queries within 4 Business Days within the calendar month (except where the query type is DUP) for 90% of Users c) Resolve 95% of User Standards of Service Queries within 10 Business Days within the calendar month d) Resolve 95% of User Standards of Service Queries within 10 Business Days within the calendar month (except where the query type is DUP) for 95% of Users e) Resolve 98% of User Standards of Service Queries within 20 Business Days within the calendar month f) Resolve 98% of User Standards of Service Queries within 20 Business Days within the calendar month (except where the query type is DUP) for 100% of Users g) Valid re-submitted queries (PSQ's) do not exceed more than 1% within the calendar month | CMS | 3,500 per calendar month | CMS | TPD S4.7 and chapter 5 of the Standard of Services Query Management Operational Guidelines TPD Section G1.9.8 and G1.18 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA2-02 | Following receipt of a valid GRE invoice query; record, investigate & resolve and submit, if appropriate, an Adjustment invoice | 100% of valid queries in accordance with the timescales within the GRE Incentive Scheme Methodology: query resolved and the credits paid by the end of the third month following raising of the invoice query. | CMS | 10 per calendar month | CMS |  | 2 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA5-14 | Validation of the Meter Reading or Check Read and send the Registered User the valid accepted Meter Reading following receipt from the DMSP for Class 1 Supply Meter Points | By 12:00 reasonable endeavours, and 100% by 14:00 on D+1 | File via IX |  | UKLink Communication | M5.1.6 M5.6.1 M5.2.2 M6.3.1(c ) | 2 | Business Operations: CDS |  |  | 2019-06-01 | Missed | 12th June – AMT MarketFlow unavailable therefore incoming and outgoing file relating to gas flow day of 11 June 2019 were not processed. | 8 files were issued by 14:00 on D+1 with a further 9 being sent by 15:00 on D+1. | Incident number 1007415. Customers were notified on 12 June of the delay to them receiving their daily read files.
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA7-02 | Submit scheduled Invoice Documents to Users | a) 100% on the relevant Business Day following the relevant Billing Period b) Valid invoice queries for calculation errors do not exceed 2% of issued charges, by volume for submitted invoice documents | File via IX | N/A | UKLink Communication | TPD Sections S1.1.2, S1.2.1, S1.2.2, S1.4.1 and S1.4.2 | 1 | Business Operations: IC&C |  |  | 2019-06-01 | On Track | Once AMT was restored files were prioritised and the daily read file (DLC) was submitted.
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA7-03 | Submit Users Ancillary Invoice following request from the Transporter | Submit 98% of User Invoice Documents for an Ancillary Invoice | File via IX | N/A | UKLink Communication or Conventional Notice | TPD Sections S2.3.7 | 1 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA7-04 | Submission of complete & accurate supporting data for Invoice documents issued | a) Submit 100% of supporting information for each Invoice Type on the invoice date for the relevant Billing Period, for Ancillary invoice the supporting information may be issued five (5) calendar days in advance of date of submission of unscheduled Invoice Documents b) Valid invoice queries for calculation errors do not exceed 2% of issued charges, by volume for submitted invoice documents | File via IX | N/A | UKLink Communication | TPD Sections S1.3.4 & S2.3.7 | 1 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA7-05 | Send User an Amendment invoice or an Ancillary invoice following the issue of an incorrect invoice | Submit 100% by month +2 following invoice query resolution | File via IX | N/A | UKLink Communication | TPD Section S1.8.1 | 1 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA7-06 | In the case of interest on invoice adjustments arising from Invoice Queries, submit an Interest Invoice | a) 100% by no later than the end of the third (3rd) month following resolution of the query. B) In the case of interest on invoice adjustments arising from invoice queries; no later than third (3rd) month following resolution of the query | File via IX | N/A | UKLink Communication | TPD Section S4.4.2 and V10.3.3 | 1 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-01 | Maintain an up to date and accurate record of a User's current Secured Credit Limit following receipt of information from applicant User to support admission requirements | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | N/A |  |  | TPD Section X2.2.3 | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-02 | Following receipt of an application for an Increased Secured Credit Limit from a User, review application and security provided (if any), and where appropriate, revise the User's Secured Credit Limit in accordance with the Energy Balancing Credit Rules | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | N/A |  |  | TPD Section X2.2.5 | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-03 | Occurrence of one of the events referred to in TPD X2.2.6(a), review User's Secured Credit Limit and security provided (if any), and where appropriate, revise the User's Secured Credit Limit in accordance with the Energy Balancing Credit Rules | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | N/A |  |  | TPD Section X2.2.6(a) | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-04 | Occurrence of one of the events referred to in TPD X2.2.6(b), review User's Secured Credit Limit and security provided (if any), and where appropriate, revise the User's Secured Credit Limit in accordance with the Energy Balancing Credit Rules | Review 100% of existing Security arrangements and obtain replacements (if applicable) annually. | N/A |  |  | TPD Section X2.2.6(b) | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-12 | Send the User a Cash Call notice where the User's Outstanding Relevant Balancing Indebtedness exceeds the User's Cash Call Limit | Issue 90% of cash calls by 3pm every Business Day | N/A |  |  | TPD Section X2.6.1 | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track | [8 empty] | Var
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-19 | Send notice of non payment of the Cash Call to the User by close of the Business Day following Day on which Cash Call was made and send a copy of the notice to the Authority and suspend credit payments to User | Issue 100% of failure to pay notices on the next Business Day following the Payment Due Date | N/A |  |  | TPD Sections X2.9.1 and X2.9.4 | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA8-23 | Send notice to the User that a Termination Notice may be issued in the event of the continued non payment of the net invoice Amount of an Energy Balancing Invoice and send a copy of the notice to the Authority | a) Collect 98% of Cash by the Payment Due Date – measured as an average monthly year to date total (January to December of any one year) b) Collect 100% of Cash by the Payment Due Date + 2 Business Days c) Record 95% of receipted payments by D+1 | N/A |  |  | TPD Sections X3.2.1 and X3.2.3 | 3 | Business Operations: IC&C |  |  | 2019-06-01 | On Track |  |  |  | Due Date | SSC | Shipper Name | Amount
Part C - Agency Services for Transporters - Code Services | ASGT CS SA11 02 | Following receipt of a valid request to register the iGT System, create the iGT System (CSEP Project), and, where applicable, provide the relevant information to the Gas Transporter & Shipper(s) | 100% within 2 Business Days of receipt | File via IX | N/A | UKLink Communication | IGTAD B2.4.1 | 1 | Business Operations: CDS | CIC | CCN | 2019-06-01 | On Track |  |  |  | Due Date | SSC | Shipper Name | Amount
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA20-01 | Operate, manage & support UKLink Gemini Data Centre | Provide 99% availability of UK Link Gemini within scheduled service hours at 23 hours per day Monday to Saturday and at 22 hours on Sundays (reflecting Planned Downtime for scheduled maintenance in accordance with UK Link Manual) | Gemini | N/A | Gemini | UKLink Manual | 1 | IS Operations |  |  | 2019-06-01 | On Track |  |  |  | 12/06/2018 | NGS | Gazprom Marketing and Retail Ltd | -295021.59
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA20-02 | Operating, managing and supporting Application Servers, including storage management, systems programming, capacity planning, performance tuning and maintenance for UKLink Gemini | Provide 99% availability of UK Link Gemini within scheduled service hours at 23 hours per day Monday to Saturday and at 22 hours on Sundays (reflecting Planned Downtime for scheduled maintenance in accordance with UK Link Manual) | Gemini | N/A | Gemini | UKLink Manual | 1 | IS Operations |  |  | 2019-06-01 | On Track |  |  |  | 19/06/2018 | NGS | Gazprom Marketing and Retail Ltd | -203.59
Part C - Agency Services for Transporters - Code Services | ASGT-CS SA20-03 | Provide operations support to UKLink Gemini | Provide 99% availability of UK Link Gemini within scheduled service hours at 23 hours per day Monday to Saturday and at 22 hours on Sundays (reflecting Planned Downtime for scheduled maintenance in accordance with UK Link Manual) | Gemini | N/A | Gemini | UKLink Manual | 1 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | ASGT-NC SA16-01 | Submit notice to User and/or Network Operator for investigation or for safety visit following receipt of alleged incident of gas illegally taken | 100% within two (2) Business Days of receipt of notice and where safety prejudiced as soon as practicably possible (excluding safety visit requirements) | CMS | 500 per calendar month | CMS | Standard Condition 8 | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | ASGT-NC SA16-03 | Record the notification and any other relevant information following receipt of proposed connection or disconnection of the meter | 100% within two (2) Supply Point System Business Days of identification of User | N/A |  | UKLink Communication | Standard Special Condition A10 paragraph 6 & TPD M4.2.3 | 2 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | ASGT-NC SA16-06 | Provide the relevant data following receipt of request from a domestic customer or a person acting on their behalf (but not a gas shipper or its agents) or receipt of request from a customer of a gas supplier for any relevant data which relate to the premises occupied, or to be occupied, by the customer. Receipt of a request from a gas customer for the provision of the identity of the GT to the premises in question | a) Provide supply point information and relevant data to appropriate customers between Monday to Friday 8.30am to 5pm (excluding bank holiday) b) Answer 90% of Reportable Calls to the M Number service within 30 seconds of the call being offered to a call handler. | Telephone | a) 100,000 per calendar month b) 100,000 Reportable Calls per month | Telephone | Standard Special Condition A31 paragraph 2© and 2€ | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | ASGT-NC SA16-10 | Conduct a customer satisfaction survey with Shippers and publish results to Networks and Shippers. | a) Publish within 2 months of the survey closure b) maintain an overall score of the equivalent of 3.5 or above (out of 5) |  | Twice per year |  | N/A | 2 | Customer Engagement |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | ASGT-NC SA18-01 | Following a request from a Network Operator send the relevant Network Operator the relevant information and data | Support 100% of requests for information and data in relation to complaints to Network Operators within 8 Business Days of receipt of the request |  | 35 per calendar month | UKLink Communication | N/A | 3 | Customer Engagement |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | ASGT-NC SA22-08 | Send Network Operators notice of invoice Documents issued | 100% within twenty four (24) hours of the submission of the Invoice Documents to Users (SIF/SIR) | File via IX | N/A | UKLink Communication | N/A | 1 | Business Operations: IC&C |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 05 | Provide Must Read notifications to the relevant Transporter MRA and the User for Monthly Read Meters | 100% where, at the end of any calendar month, a Valid Meter Reading has not been submitted with a Read Date within the proceeding 4 months; a notification issued no earlier than: a) the 10th Supply Point Systems Business Day of the following calendar month; or b) the 80th Supply Point Systems Business Day following the date the User was notified of incorrect Meter information | Email |  | CMS | TPD M5.10.2 | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 06 | Provide Must Read notifications to the relevant Transporter MRA and the User for Annual Read Meters (Non-Monthly Read Meters) | 100% where, at the end of any calendar month, a Valid Meter Reading has not been submitted with a Read Date within the proceeding 24 months; a notification issued no earlier than: a) the 10th Supply Point Systems Business Day of the following calendar month following; or b) the 80th Supply Point Systems Business Day following the date the User was notified of incorrect Meter information | Email |  | CMS | TPD M5.10.2 | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 07 | On receipt of a Valid Must Read from the Transporters MRA, send notice to the User | As soon a reasonably practicable | File via IX |  | UKLink Communication | TPD M5.10.7 | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 18 | Following acceptance of the quote, provide, install, commission, test and maintain an Option 1 IX connection | Install 100% of UK Link provided equipment and UK Link provided software within 45 Business Days of receipt | N/A | 4 per calendar month | IX | General Terms D | 3 | Customer Lifecycle |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 19 | Following acceptance of the quote, provide, install, commission, test and maintain an Option 2 IX connection | Install 100% of UK Link provided equipment and UK Link provided software within 62 Business Days of receipt | N/A | 4 per calendar month | IX | General Terms D | 3 | Customer Lifecycle |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 20 | Following acceptance of the quote, provide, install, commission, test and maintain an Option 3 IX connection | Install 100% of UK Link provided equipment and UK Link provided software within 62 Business Days of receipt | N/A | 4 per calendar month | IX | General Terms D | 3 | Customer Lifecycle |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 29 | Provision of a user Telephone Enquiry Service | For each calendar month User Telephone Enquiry Service Unplanned Downtime is no more than 5% of Core Hours. Except during periods of User Telephone Enquiry Service Planned Downtime and User Telephone Enquiry Service Unplanned Downtime, for each calendar month; answer 90% of calls within 30 seconds. | Telephone | Per Telephone Call up to 3 MPRN and no more than 5 data items for each MPRN | Telephone |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 33 | Registered User Portfolio Report Service. Query Management - Standards of Service, Annual Service (scheduled monthly reports) acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 36 | Registered User Portfolio Report Service. Registered User Portfolio Statement, Ad Hoc Service (for one monthly scheduled report); acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 37 | Registered User Portfolio Report Service. Registered User Portfolio Report Annual Service (for portfolios not exceeding one (1) million Supply Points); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 40 | Registered User Portfolio Report Service. CSEP Portfolio Report, Annual Service (scheduled monthly reports); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 42 | Registered User Portfolio Report Service. Unique Sites Portfolio Report, Annual Service (scheduled monthly reports); Acknowledgement and provision of the report. | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 44 | Registered User Portfolio Report Service. Registered User Portfolio Report Acknowledgement and provision of the Annual Asset Portfolio Report, Annual Service (once per year). | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 46 | Registered User Portfolio Report Service. Transco Asset Portfolio Report, Annual Service (scheduled monthly reports); Acknowledgement and provision of the report. | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 48 | Registered User Portfolio Report Service. Data Portfolio Snapshot, Annual Service (scheduled monthly reports); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 50 | Registered User Portfolio Report Service. Data Enquiry Service Last Accessed Report, Annual Service - Monthly (scheduled monthly reports); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 51 | Registered User Portfolio Report Service. Data Enquiry Service Last Accessed Report, Annual Service - Quarterly (four (4) scheduled reports; April, July, October, January each year); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 52 | Registered User Portfolio Report Service. Data Enquiry Service Last Accessed Report, Annual Service - six monthly (two (2) scheduled reports April & October each year); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 54 | Registered User Portfolio Report Service. Historic Asset & Read Portfolio Report, Annual Service quarterly (four (4) scheduled reports (April, July, October, January each year); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 55 | Registered User Portfolio Report Service. Historic Asset & Read Portfolio Report, Annual Service monthly (scheduled monthly reports); Acknowledgement and provision of the report | As agreed |  |  | BW |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 58 | Acknowledgement to confirm CDSP's agreement to provide the requested Email Reporting Service | As agreed |  | A single email report request may be for no more than 5000 MPRNs. Where the number of Email Reports being prepared by the CDSP at the point in time on which it would ordinarily issue its Email Reporting Requested Acknowledgement exceeds 20 (in aggregate in respect of all Customers), then that Email Reporting Request will not be acknowledged. However, the Customer is notified. If the Customer re-submit their request, the CDSP will use reasonable endeavours to provide the service as soon as reasonably practicable but the performance measures shall not apply |  |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 59 | Submission of the Email Reporting Service for up to 999 Meter Point Reference Numbers. | Where the acknowledgement is issued no later than 12:00 pm on a business day: No later than the end of the second Business Day following submission of the Email Reporting Request Acknowledgement |  |  | BW |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 60 | Submission of the Email Reporting Service for up to 999 Meter Point Reference Numbers. | Where the acknowledgement is issued after 12:00 pm on a business day: No later than the end of the third Business Day following submission of the Email Reporting Request Acknowledgement |  |  | BW |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 61 | Submission of the Email Reporting Service for more than 999 but less than 5,000 Meter Point Reference Numbers. | Where the acknowledgement is issued no later than 12:00 pm on a business day: No later than the end of the fifth Business Day following submission of the Email Reporting Request Acknowledgement |  |  | BW |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 62 | Submission of the Email Reporting Service for more than 999 but less than 5,000 Meter Point Reference Numbers. | Where the acknowledgement is issued after 12:00 pm on a business day: No later than the end of the sixth Business Day following submission of the Email Reporting Request Acknowledgement |  |  | BW |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 63 | Provision of Data Enquiry service | Part a - 97% availability during Core Hours. Part b - no Planned Downtime to exceed 4 continuous hours within Core Hours on a day | Data Enquiry |  | Data Enquiry |  | 2 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 64 | Provision of updated data to the Data Enquiry Service | Data updated within two (2) Business Days following the date of receipt and acceptance of the data | Data Enquiry |  | Data Enquiry |  | 2 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 65 | Data Enquiry Service Access Request Acknowledgement |  |  | No more than 30,000 Data Enquiry Service Accounts in aggregate for all Customer to be available at any one time | Data Enquiry |  | 3 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 66 | Created Data Enquiry Service Account (s) | No later than the end of the tenth (10th) Business Day following the Business Day of the issue of the Data Enquiry Service Access Request Acknowledgement, or later upon the date requested by the Customer. |  |  | Data Enquiry |  | 3 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 67 | Deleted Data Enquiry Service Account(s) | No later than the end of the tenth (10th) Business Day following the Business Day of the issue of the Data Enquiry Service Access Request Acknowledgement, or later upon the date requested by the Customer. |  |  | Data Enquiry |  | 4 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 68 | Data Enquiry Service password re-set | No later than the end of the tenth (10th) Business Day following the logging of the request via the telephone helpline. |  |  | Data Enquiry |  | 3 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 69 | Following request from a customer, record the report of a fault on the Data Enquiry Service System | During Core Hours |  |  |  |  | 3 | IS Operations |  |  | 2019-06-01 | On Track
Part D - Agency Services for Transporters - Non Code Services | SS SA22 70 | M Number DVD Service Acknowledgement and provision of the Annual M Number DVD Service | Delivery on each of the relevant M Number DVD within 20 Business Days of the relevant M Number Quarter Day; 30 June, 30 Septembers, 31 December, 31 March |  |  | BW | N/A | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part H Agency Services for independent Gas Transporters (iGT) - Code Services | ASiGT-CS SA11-01 | Following request to register an iGT System (CSEP) from an iGT, provide the iGT System to the relevant Gas Transporter, and for information to any other iGT where nested arrangements exist (or are being proposed) | 100% within 2 Business Days of receipt | File via IX | N/A | UKLink Communication |  | 1 | Business Operations: CDS | CIC | CIR CCN | 2019-06-01 | On Track
Part H Agency Services for independent Gas Transporters (iGT) - Code Services | ASiGT-CS SA11-02 | Following request to update an iGT System registration data from an iGT, provide the details to the relevant Gas Transporter, Shippers and iGTs (where nested arrangements exist) | 100% within 2 Business Days of receipt | File via IX | N/A | UKLink Communication |  | 1 | Business Operations: CDS | CAI | CAO (iGT) CUN (other parties) | 2019-06-01 | On Track
Part H Agency Services for independent Gas Transporters (iGT) - Code Services | ASiGT-CS SA11-03 | Following request to update an iGT System and iGT Supply Meter Point data from an iGT, provide the details to the relevant Gas Transporter and Shipper(s) | 100% within 2 Business Days of receipt | File via IX | N/A | UKLink Communication |  | 1 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA2-01 | Following receipt of a query from an iGT relating to data held on the Supply Point Register, record, investigate & resolve the query | a) Resolve 50% of iGT queries within 10 Xoserve days within the calendar month for 100% of iGTs b) Resolve 70% of iGT queries within 20 Xoserve days within the calendar month for 100% of iGTs c) Resolve 90% of iGT queries within 40 Xoserve days within the calendar month for 100% of iGTs d) Resolve 100% of iGT queries within 80 Xoserve days within the calendar month for 100% of iGTs | CMS | 600 per calendar month | CMS |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA16-01 | Following receipt of alleged incident of gas illegally taken (TOG), submit notice to User and/or Network Operator for investigation or for safety visit | 100% within two (2) Business Days of receipt of notice and where safety prejudiced as soon as practicably possible (excluding safety visit requirements) | CMS | 500 per calendar month | CMS |  | 4 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA16-04 | Provide the relevant data following receipt of request from a domestic customer or a person acting on their behalf (but not a gas shipper or its agents) or receipt of request from a customer of a gas supplier for any relevant data which relate to the premises occupied, or to be occupied, by the customer. Receipt of a request from a gas customer for the provision of the identity of the GT to the premises in question | a) Provide supply point information and relevant data to appropriate customers between Monday to Friday 8.30am to 5pm (excluding bank holiday) b) Answer 90% of Reportable Calls to the M Number service within 30 seconds of the call being offered to a call handler. | Telephone | a) 00,000 per calendar month b) 100,000 Reportable Calls per month | Telephone |  | 3 | Business Operations: CDS |  |  | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA21-01 | Provision of supply point register daily delta file to each iGT (Supply point register daily delta files - IDL file) | 100% of updated data provided within 2 Business Days of the update being applied to UK Link (IDL file within 2 Business Days of the update being applied to UK Link) | File via IX | N/A | UKLink Communication |  | 1 | Business Operations: CDS | N/A | IDL | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA21-02 | Provision of supply point register quarterly extract file to each iGT | Following the end of the quarter; 100% within 2 Business Days if via UK Link Communication or 15 business days if via other means | File via IX | N/A | UKLink Communication |  | 3 | Business Operations: CDS | N/A | IQL | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA21-03 | Provision of weekly meter readings report to each iGT; 'Meter Read Portfolio Report' | Within 2 Business Days following the end of the relevant week (readings accepted on to UK Link each week) | BW report | N/A | UKLink Communication |  | 4 | Customer Engagement | N/A | Meter Read Portfolio Report | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA21-04 | Provision of a report notifying of the confirmation of the first registration of an iGT's Supply Meter Point | 100% within 2 Business Days of the of the confirmation status is confirmed 'CO'. | File via IX | N/A | UKLink Communication |  | 3 | Business Operations: CDS | N/A | SSR | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA21-07 | Notification to the GT & iGT where iGT Supply Meter Point AQ in aggregate exceed 85% of the CSEP Max AQ. | 100% within 2 Business Days of the CSEP 85% Max AQ tolerance breach | File via IX | N/A | UKLink Communication |  | 4 | Business Operations: CDS | N/A | CGI | 2019-06-01 | On Track
Part I Agency Services for independent Gas Transporters (iGT) - Non Code Services | ASiGT NC SA21-08 | Email notification of delivery / non-delivery of Supply Point Register daily delta files (IDL file) | Email to be sent each business day: a) following delivery of IDL file, but before 11:00hrs; or, b) where the IDL file has not been delivered by 11:00hrs | Email | N/A | Email |  | 3 | TBC | N/A | CGI | 2019-06-01 | On Track

## 4. UKLink Availability
System Stats, Availability & Performance - June 2019
GEMINI Availability
| Target | 2019-06-01 | 2019-05-01 | 2019-04-01 | 2019-03-01 | 2019-02-01 | 2019-01-01
GEMINI Service | 99% | 100% | 100% | 100% | 99.66% | 99.66% | 100%
Nominations per day | 8300 | 6161 | 6098 | 6104 | 6194 | 6105 | 6049
Renominations per day | 4200 | 29613 | 29451 | 29493 | 29281 | 29318 | 29269
% of transactions < 4 sec's | 95% | 100% | 100% | 100% | 100% | 100% | 100%
Transaction response time | n/a | 0.597 | 0.55 | 0.76 | 0.82 | 0.67 | 0.64
Transactions per day | n/a | 828272 | 978690 | 890437 | 909805 | 921895 | 903198
% Transaction change | n/a | -18% | 14% | -7% | 2% | -8% | -9%
UK Link (Non-Gemini) Availability & Performance
Performance measures | Target | 2019-06-01 | 2019-05-01 | 2019-04-01 | 2019-03-01 | 2019-02-01 | 2019-01-01 | 2018-12-01
Batch Transfer | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Service Desk Availability | 99% | 100% | 99.33%* | 100% | 100% | 99.97% | 100% | 100%
* Due to an issue with Cisco phone outage over bank holiday
IS Faults Raised by Customers | P5 | P4 | P3 | P2 | P1 | Total
2018-05-01 | 0 | 17 | 55 | 1 | 0 | 73
2018-06-01 | 0 | 26 | 51 | 3 | 0 | 80
2018-07-01 | 0 | 43 | 106 | 4 | 0 | 153
2018-08-01 | 1 | 20 | 42 | 0 | 0 | 63
2018-09-01 | 0 | 15 | 35 | 2 | 0 | 52
2018-10-01 | 0 | 0 | 53 | 0 | 9 | 62
2018-11-01 | 0 | 0 | 53 | 0 | 9 | 62
2018-12-01 | 0 | 5 | 27 | 0 | 0 | 32
2019-01-01 | 0 | 4 | 48 | 2 | 0 | 54
2019-02-01 | 0 | 10 | 57 | 5 | 0 | 72
2019-03-01 | 0 | 5 | 40 | 1 | 0 | 46
2019-04-01 | 0 | 6 | 29 | 0 | 0 | 35
2019-05-19 | 0 | 13 | 46 | 3 | 1 | 63
2019-06-01 | 0 | 5 | 38 | 0 | 0 | 43
Total | 1 | 169 | 680 | 21 | 19 | 890

## 5. TP & AS Services
Third Party and Additional Services - May 2019
| 2019-04-01 | 2019-05-19 | 2019-06-19 | 2019-07-19 | 2019-08-19 | 2019-09-19 | 2019-10-19 | 2019-11-19 | 2019-12-19 | 2020-01-19 | 2020-02-19 | 2020-03-19 | 2020-04-19
Third Party Services Invoiced Amount | 2019-04-01: 35831; 2019-05-19: 32656; 2019-06-19: 34211
Rolling Third Party Invoiced Amount | 2019-06-19: 102698
Additional Services Invoiced Amount | 2019-04-01: 2159; 2019-05-19: 3978; 2019-06-19: 4000
New Category of Third Party Requesting Third Party Services | 2019-08-19: None
CDSP liabilities to a Third Party under a TPS Agreement | 2019-08-19: None
Any TPS material breach of a TPS Agreement | 2019-08-19: None
2.5% CDSP overall turnover 2019/2020 | 2019-08-19: £2,005,450.00

## 6. Change Budget Update
Change Budget Update - June 219
Budget line | £k | NTS % | GDN % | IGT% | Shipper % | NTS £k | GDN£k | IGT £k | Shipper £k
Change projects Year 1 | 2500 | 2% | 16% | 0.3% | 82% | 40 | 400 | 8 | 2052
| Percentage split |  |  |  |  | Financial split