## Slide 1: UIG Task Force Progress Report
Contract Management Committee 17/07/19

## Slide 2: Background
Modification 0658: ‘CDSP to identify and develop improvements to LDZ settlement processes’ approved by Ofgem on 6th July 2018
  Modification raised to authorise the CDSP to assign resources and incur costs related to a Task Force to investigate the causes and influencers of Unidentified Gas (UIG), with a target of reducing the volatility and scale of UIG and developing a robust predictive model for daily UIG for use by all parties.
BER for Change Reference Number XRN4695: ‘Investigating causes and contributors to levels and volatility of Unidentified Gas’ approved at ChMC on 11th July 2018
  This Change Proposal added an additional service line into the DSC to enable Xoserve access to investigate, using resources and technology, causes and contributors to levels and volatility of Unidentified Gas. Xoserve is to provide monthly update reports and recommend proposals and subsequent changes or modifications for the industry.
The following slides provide:
  Task Force dashboard
  POAP
  Recommendation stats
  Reporting on budget
  Advanced machine learning next steps
  Task Force next steps

## Slide 3: UIG Task Force: Dashboard
G
RAG | 
Time | G
Cost | G
Benefit | N/A
Progress since last month - key milestones | Date | Status
Executive Summary Update | w/c 03/06/19 | Complete
Attend May Change Management Committee | 12/06/19 | Complete
Attend May Contract Management Committee | 19/06/19 | Complete
Attend June UIG Work Group | 24/06/19 | Complete
Attend UIG Work Group Mod 0681 | 07/06/19 | Complete
Attend Work Group 674 | 26/06/19 | Complete
Priorities for next month – key milestones | Date | Status
Overall RAG status:*
Support Mod development (All) | July ongoing | G
Development of automated UIG reporting | End of June | R
Attend July UIG Work Group | 23/07/19 | G
Attend July ChMC | 10/07/19 | G
Attend July CoMC | 17/07/19 | G
Attend DESC | 10/07/19 | G
Commence UIG Task Force close down/extension options | 01/07/19 | Ongoing
Draft new Recommendation options to support 3.2.5 option 3. | July | G

## Slide 4: Plan on Page new
Delivery team milestone
Advanced Analytics
I
Governance
C
Completed activity
 | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | 
 | 01/04 | 08/04 | 15/04 | 22/04 | 29/04 | 06/05 | 13/05 | 20/05 | 27/05 | 03/06 | 10/06 | 17/06 | 24/06 | 01/07 | 08/07 | 15/07 | 22/07 | 29/07 | 05/08 | 12/08 | 19/08 | 26/08 | 02/09 | 09/09 | 16/09 | 23/09 | 30/09
Issue analysis and tracking (Investigation Tracker updated and published bi-weekly)
Develop Findings template and Recommendation Packs
Investigation Analysis
Develop Xoserve owned Recommendation options – update and publish recommendation tracker in line with UIG working group meetings
Draft Mods to support recommendations
Support Mod development
I
10/04 DSC ChMC
w/c 29/4 Exec Summary
I
08/05 DSC ChMC
I
12/06 DSC ChMC
03/05 Attend Customer Training Day
I
08/04 UIG WG
I
29/04 UIG WG
I
20&21/05 UIG WG
I
24/06 UIG WG
I
01/05 CoMC
I
15/05 CoMC
I
19/06 CoMC
I
10/07 DSC ChMC
I
07/08 DSC ChMC
I
11/09 DSC ChMC
I
17/07 CoMC
I
14/08 CoMC
I
18/09 CoMC
I
23/07 UIG WG
I
20/08 UIG WG
I
23/09 UIG WG
w/c 01/06/Exec Summary
w/c 01/07 Exec Summary
w/c 01/08 Exec Summary
w/c 02/09 Exec Summary
Review/draft updates to UIG user guide ongoing
w/c 23/09 Publish UIG Investigation guide V.2
w/c 01/07 create close out activity plan

## Slide 5: Recommendations - where we are
As at 25/06/19
All future reviews include non task force related changes that are pending, defects with planned resolution dates, other options which may be considered if engagement/PAC reporting does not deliver results. (PAC can look to deliver these when PAC reporting is updated).
1 ongoing 3.2.5 option 3
3 lines MOD – (3.2.1) = 3 MODS – 1 sponsored Total 0692), 2 sponsored British Gas 0690 & 0691
26 Future review
7 review July
8 review August
2 lines PAC /Xoserve
4 lines MOD 0681 – EON
47 CLOSED
9 lines MOD – Scottish Power (12.2) = 1 MOD – sponsored 0693R
11 do nothing
2 BAU
9 completed
25 other options progressed
7 review November
4 review December
14 finding & recommendations = 95 recommendation lines
3 lines Xoserve drafted MODs 3.2.5
1 In progress

## Slide 6: Overview Of Task Force Funding

## Slide 7: Task Force Next Analysis Steps
Xoserve will endeavour to produce a Machine Leaning Video to highlight the benefits, considerations and implementation challenges of using Machine Learning algorithms to allocate NDM Energy
We are working with our Analytics Partner to complete:
  Rerunning the Neural Network performance comparison against the existing NDM algorithm for more recent Gas Days for EUC 01 only (propose 01/06/2018 – 31/05/2019).
  Develop improved estimation models for EUCs 2-8 to demonstrate whether the ML benefit can be seen across the whole market.
  Explore using the models and findings developed to date to look at building a UIG predictive model.
  Continue modelling work, focussing on reducing modelled volatility further.
Notes: Do nothing no appetite
Involve our data analytics partner to run a day – cost
Create a ML education pack and issue on line
Xoserve develop a day to run with customers
CC suggested running NN live and compare it to NDM algorithm as a proof of concept – need to understand the amount of months that would be required to fully cost and assess the needs of the customer – we have had expressed interest from one customer for this option. We have to flag that this would due to time be using the updated ALPs only and therefore the previous reductions of 70% base and 20% volatility will be reduced.
Creation of a Sandpit - is there a desire for this or do customers have this capability internally and would not want this to be investigated further? We would also have to make a decision if this was supported or not and consider costs associated with this.
Development of NN for EUCs 2-8 wasn’t recommended by our analytics partner as we have already seen benefits for EUC01 and there is no reason to doubt that it wouldn’t be beneficial across the other EUC’s and also the most UIG is carried in EUC01.

## Slide 8: Task Force Next Steps
Use the UNC UIG Work Group as the mechanism to share progress on all recommendations where options residing with Xoserve.
Provide updates to the “Recommendation Tracker” in line with UNC UIG Work Group timescales.
Continue analysis on existing investigation lines, identify any new investigation lines & publish investigation tracker updates as required.
Publish any new findings/recommendations drawn from investigation lines which are currently “work in progress” when completed.
Supporting MOD development to progress all live and draft modifications.
Complete complex machine learning next steps with Analytics partner & share outputs with the Industry.