## Slide 1: XRN 4927 – MiR Drop 4 - Status Update
1/07/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | System Testing Assurance – System Testing has completed successfully and to plan for all 3 changes Code Merge – Code Merge to Preprod has completed successfully Regression Testing – Regression Testing to start w/c 1/7/19 |  |  | 
Risks and Issues | Environment availability continues to be a risk as several projects are sharing environments through out delivery and test, implementation |  |  | 
Cost | All costs tracked to budget |  |  | 
Resources | There is an ongoing risk that SME’s will not be available when required, this is being closely monitored, currently there has been no issues |  |  | 

## Slide 2: Potential Minor Release Drop 4 Timeline & Scope
Minor Release Drop 4 Key Milestone Dates:
Initiation – 3/5/19
Design – 10/5/19
Build - 7/6/19
Test – 19/7/19
Implementation – 27/7/19
Closedown – 9/8/19
Design
Build
ST & Assurance
CM
PT / RT
IMP
PIS
Dec
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
MiR Drop 4
10/04: Scope Approval
27/7: Go Live