## Slide 1: XRN 4954 – MiR Drop 5 - Status Update
15/07/19 | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | SPA Change Build complete Acceptance Testing in progress , Regression testing to start 4th Aug Ratchet Drill Down Report Build 80% complete |  |  | 
Risks and Issues | Environment availability continues to be a risk as several projects are sharing environments through out delivery and test, implementation. Sharing pre prod with EUC which may impact start of Regression Testing |  |  | 
Cost | All costs tracked to budget |  |  | 
Resources | There is an ongoing risk that SME’s will not be available when required, this is being closely monitored, currently there has been no issues |  |  | 

## Slide 2: Potential Minor Release Drop 5 Timeline & Scope
Minor Release Drop 5 Key Milestone Dates:
SPA Change Drill Down Report
Initiation 14/6/19 23/7/19
Design 29/6/19 23/7/19
Build 12/7/19 3/8/19
Test 9/8/19 30/8/19
Implementation 7/9/19 7/9/19
Closedown 20/9/19 20/9/19
Design
Build
ST & Assurance
CM
RT
IMP
PIS
Dec
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
MiR Drop 5
10/07: Scope Approval
7/9 Go Live