## Slide 1: XRN4828 - Nov 19 Release - Status Update
10th July | Overall Project RAG Status: |  |  | 
 | Schedule | Risks and Issues | Cost | Resources
RAG Status |  |  |  | 
Status Justification |  |  |  | 
Schedule | Start Up and Initiation phases complete Detailed Design commenced on 17th June, design workshops complete with phase on track to complete by 12th July Build to commence w/c 1st July Test plan and scenarios under review Funding: BER for full delivery approved in April 2019, BER for XRN4866 UIG Recommendation approved at ChMC on 12th June. |  |  | 
Risks and Issues | Risk: There is a risk that the Nov 19 Release may be impacted by Pre-Production environment congestion due to multiple deliveries running in parallel Risk: There is a risk that due to multiple UKLink deliveries running in parallel there may be limited access to resources. |  |  | 
Cost | The BER with full delivery costs were approved at ChMC in April 2019, BER for XRN4866 UIG Recommendation approved by ChMC on 12th June |  |  | 
Resources | Weekly monitoring of Xoserve SME resources supporting multiple demands (e.g. BAU defects, Future Releases etc) is ongoing |  |  | 

## Slide 2: XRN4828 - Nov 19 Release Timelines
Key Milestone Dates:
Design Completion – 12/07/19
Build & Unit Test Completion – 02/08/19
System & UAT Completion – 27/09/19
Regression Test Completion - 11/10/19
Implementation – 08/11/19 TBC
PIS Completion – 06/12/19
2019
Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
XRN4828
Nov-19
HLD & Change Pack Production
Design
Build & FUT
ST & SIT
UAT
RT
PT
Test Cont.
PIS
04/02: EQR Approval
10/04: BER Approval
08/05: Change Pack Approval
GO LIVE 08/11/19 - TBC
IDR