## Slide 1: XRN4914 MOD 0651- Retrospective Data Update Provision
ChMC – 10th July 2019

## Slide 2: XRN4914 MOD 0651- Retrospective Data Update Provision – Progress update
Capture Progress update | 
Schedule | Proof of Concept: 13th / 20th June: requirements gathered 24th June: peer and first review 25th June: issued for internal review 1st July: internal walkthrough and approval scheduled 2nd July: ideas/solutions initial discussion 3rd July: start production of high level solutions options Planning continuing
Risks and Issues | Issue -project is behind original draft plan Issue - data team / security team resources not allocated to project; options being discussed internally Risk - that cost required to deliver project is greater than project funding (2017 day rates used) Risk - availability of resources (environments/people) may impact plan for Retro
Cost | Project cost - to be re-confirmed Project funding - £1.5 mill; £700k for 2019 and £800k for 2020
Resources | Project mobilising Resources required for project being identified and seeking allocation Engaged with other programmes of work for consequential impacts / synergies (CSSC, AML/ASP, UIG) SI agreed for project Engagement approach to be agreed with Customers

## Slide 3: XRN4914 MOD 0651- Retrospective Data Update Provision – Proof of Concept Update
Latest update on High Level Solution Options to be provided into ChMC
Proof of Concept (PoC)
Data Cleanse
Enduring Solution
June ‘19
Nov ‘20
Market Trials
Key: dashed line – to be defined
today
13th / 20th June: PoC requirements gathered
24th June: peer and first review
25th June: issued for internal review
1st July: PoC internal walkthrough and approval scheduled
2nd July: ideas/solutions initial discussion
Completed
3rd July: start production of high level solution options
Produce Customer Engagement Schedule
Next Steps

## Slide 4: XRN4914 MOD 0651- Retrospective Data Update Provision – Key points
  Proof of Concept Requirements:
  Walk through on 1st July; resulted in the following
  2 new requirements (FR4 & FR5)
  3 requirements (FR3, FR7 & FR8) pending further discussion; meetings to be arranged
  All other requirements approved
Decision Point: Approval for requirements being sought