## Slide 1: Data Office POAP June/July 2019

## Slide 2: Update on current Data Office change pipeline
Work has started on the development and delivery of Drop 1 for the Shipper Pack changes (Shipper MI – XRN4789). First data drop focuses on alignment of data and topics in the Shipper Packs and PARR Reports and the delivery date for the first drop is 31st July.
Data Office continue to support the work in the AML/ASP Taskforce which has resulted in a knock on delay in the delivery of some of the changes currently in the Data Office pipeline for delivery.
In order to ensure that we continue to move forward with changes in the pipeline as quickly as possible, internally Xoserve continue to review the priority of existing changes in the pipeline along with any new changes that are received.

## Slide 3: Data Office POAP
Below shows the Change Proposals or externally impacting change requests that are currently in delivery with the Data Office and have planned releases:
XRN Number | Change Title |  |  | Delivery Month |  |  | RAG Status
 |  | April/ May | June/ July | Aug/ Sept | Oct/ Nov | Dec/Jan | 
XRN4835 | Address Profiling and Reporting (css extract pre go live) |  |  |  |  |  | Requirements have changed – data office working with CSSC Project to resolve
XRN4841 | MAP Access to UKL via API (JMDG Use case 58) – API access on back of a MOD |  |  |  |  |  | Due to be complete end of June
XRN4886 | MAM Reporting (MOD297) supporting report for MOD |  |  |  |  |  | Due to be complete end of June
XRN4898 | Additional data source for UIG visualisation |  |  |  |  |  | Due to be complete end of July
XRN4795 | Amendments to the PARR (520a) reporting |  |  |  |  |  | Due to be complete end of December

## Slide 4: Data Office changes in Capture
The table below shows all change proposals and externally impacting change requests which are currently in capture and are either new requests, we are gathering requirements or we are waiting for solution options from the Data Office:
CP/CR | XRN No | Change Details | Priority | Customer Benefit | Indicative Delivery Date
CR | 4868 | UIG Recommendation – Report for class 1, class 2 read rejections | 1 | To monitor AQ movements and percentage of AQ’s calculated per user per month | January 2020
CP | 4860 | National Temporary UIG | 2 | Information for Shippers to see how reconciliation is affecting UIG over time | January 2020
CP | 4738 | Shipper portfolio update proposed formula year AQ/SOC | 8 | Inform Shippers of their proposed formula year AQ/SOQ values when produced. | BA available in October for requirements gathering. Delivery date TBC
CP | 4876 | Changes to PAR Reporting (supporting UIG) | 4 | Provide further data to PAFA to aid analysis on performance reporting and aid in shipper performance as a first indication of any issues before PAC | TBC – part of the Shipper MI Project
CP | 4789 | Shipper packs – glossary updates and reporting changes from AQ to product class | 5 | The shipper packs should align further to PAC reporting and aid shipper performance | TBC – part of the Shipper MI Project
CP | 4779 | MOD0657S – Adding AQ reporting to PARR Reports | 6 | Monitor AQ movements and percentage of Aqs calculated per month by user, can access performance across the industry and engage with the poorer performers with an aim to get industry performance increased. | TBC – part of the Shipper MI Project
CP | 4946 | Reporting on installed meters with conversion capability | 8 | Inform Shippers of meters in portfolio with this capability to ensure they are billing the end consumer correctly | TBC