## IP - In Analysis
UK Link Modification Implementation Plan - In Analysis
Functional Changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation changes - In Analysis
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Predicted approval date | Commentary
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - For Approval - Design
UK Link Modification Implementation Plan - For Approval
Functional Changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
XRN4376 |  | XRN4376 - GB Charging and Incremental (PARCA) Part B – Capacity Vs Nominations Report – External Screen Pack linked to Comm Ref 2293.4 – RJ - ES | 2378.2 - RT - PO | 2019-07-12 | 2019-07-26 | 2019-07-26 | X | X | X | X |  | TBC | 2019-08-07 | 8th September 2019 | The Live Capacity vs Nomination Report is a new report which will be available in Gemini to display Live Nominations vs Capacity data for Internal and External users. The report will display data for both IP and Non-IPs and will display records if there is at least either a valid Capacity or Nomination. The attached External Screen Pack demonstrates the new screens in Gemini that have been developed to support the report.
XRN4621 |  | Suspension of the Validation between Meter Index and Unconverted Converter Index – Design Clarification Request | 2378.5 – RT – PO | 2019-07-12 | 2019-07-26 | 2019-07-26 | X |  |  |  |  | TBC | 2019-08-07 | 8th November 2019 | At the DSG on 17th June 2019 we agreed to use the previous validation that had been applied to the meter and converted indexes for the purposes of this warning report – i.e. Class 1 & 2 Supply Meter Points: 0.95 to 1.05 and Class 1 & 2 Supply Meter Points: 0.85 to 1.15. It was proposed that this validation additionally be applied to the meter to unconverted indexes. During further design reviews, we identified that since the unconverted index will no longer be mandatory it is unlikely that we will receive this index in all scenarios, and therefore this validation might be applied across inconsistent periods for the unconverted and converted indexes against the Meter. Since the validation reporting was intended only in order to highlight a potential inconsistency for further investigation DSG were asked on 1st July 2019 to consider their use of this report and whether the validation between the meter and unconverted indexes was necessary.
Documentation changes
XRN | Mod ref | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Predicted approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other

## IP - Approved Last Meeting
UK Link Modification Implementation Plan - Approved on 10th July 2019
Functional Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
Documentation Changes
XRN | Modification reference | Description | Comm ref | Date issued | Representation Close out date | Xoserve representation comments due | Impacted party |  |  |  |  | Reps ref | Approval date | Implementation Date | Comments
[7 empty] | Shipper | DNs | NTS | IGT | Other
N/A | N/A | Important Change Management Committee dates for 2020 including all Business Days and Supply Point Systems Business Days | 2346.2 - RJ - PO | 2019-06-14 | 2019-06-28 | 2019-06-28 | X | X | X | X | X | TBC | 2019-07-10 | 2019-07-10 | The purpose of this Change Pack is to seek confirmation of the Change Management Committee (ChMC) and Delivery Sub-Group (DSG) meeting dates for 2020, and the Change Pack distribution dates. The reps we received during the Change Pack process were in support of the dates, although there was one comment which sought to postpone the ChMC approval of the June 2020 scope from September's meeting to October's (2019). In response, Xoserve attends to raise this response as a discussion point at ChMC in July.
XRN4871 (Part A) | 665 | Changes to Ratchet Regime | 2346.8 - RJ - PO | 2019-06-14 | 2019-06-28 | 2019-06-28 | X | X |  |  |  | TBC | 2019-07-10 | August 2019 (Minor Release Drop 5) | Modification 0665 – ‘Changes to Ratchet Regime’ has been raised and seeks to amend the current Ratchet Charging Arrangement and it allows Transporters to designate Supply Points (Network Designated sites) that should, in addition to existing mandatory Class 1 Supply Points, be subject to existing Ratchet Charges. Class 2 Supply Meter Points will be subject to a lesser Ratchet Charge. Change Proposal XRN4871 has been raised to deliver the system requirements set out within this modification. During the consultation period, four responses were received which supported the Design Specification; however, the responses did include a set of questions which Xoserve will address in the to be distributed June Representation Matrix. The Change Pack did request views from Users on their preference around how certain elements of the change would work (invoicing and rate to calculate SHQ). We will be seeking approval from ChMC on the preferences.

## Outages
Outages
Change Request Number | Impacted System | Outage Duration |  |  |  |  | Committee Notified Date
|  | Start Date | Start Time | End Date | End Time | Brief Description
TBC | Xoserve Portal | 2019-08-04 | 03:00 BST | 2019-08-04 | 05:00 BST | As the Portal will be unavailable, external customers will not be able to log into the Data Enquiry Service during this time. A scrolling message will be placed on the Portal homepage in order to advise users of the extended down-time. The standard maintenance window is 5am-7am, but as there are four servers that need to be patched and they all need to be done at the same time to keep them in sync so we need an additional two hour outage to complete the activity. We will take the additional two hours between 3am-5am in order to minimize the impact to the customer. | 2019-08-07
TBC | UK Link Portal and CMS | 2019-08-16 | 23:00 BST | 2019-08-17 | 10:00 BST | The purpose of this notification is to provide Change Management Committee with an early notification of the UK Link Disaster Recovery Tests in 2019. Further communications regarding the impact of the test will be issued in early August. | 2019-05-08
TBC | UK Link Portal | 2019-08-17 | 23:00 BST | 2019-08-18 | 08:00 BST | The purpose of this notification is to provide Change Management Committee with an early notification of the UK Link Disaster Recovery Tests in 2019. Further communications regarding the impact of the test will be issued in early August. | 2019-05-08
TBC | EFT | 2019-11-02 | TBC | 2019-11-03 | TBC | Cutover from PET/KET Data Centres into Chessignton and Cressex; the outage will be 5-10min while cutover takes place during this time. End users will not be affected, however files will sit in situ till cutover is complete and will then continue processing. Normal applicable testing will be done i.e Sense Checks | 2019-08-07
TBC | DCC Phase 1 | 2019-11-30 | TBC | 2019-12-01 | TBC | DCC phase one & two will not have not have any outages/cutover that will impact the industry as it doesn't go live until the end of phase 3 as it will be in the TCS ECP data centre till all migration activities have been completed | 2019-08-07