## Slide 1: Amendment Invoice Contract Management Committee Update
18th September 2019
Dan Donovan

## Slide 2: Summary Resolution Plan
Apr
May
Jun
Jul
Aug
Sept
Mobilise
Oct
Nov onwards
ASP / AML Mismatches
Exceptions
(LSPs)
Exceptions
(SSPs)
Exclusions
Defects
MI / Reporting
Backlog Clearance
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
RCA activities
Operating within SLA
Mobilise
Backlog Clearance
Operating within SLA
Backlog Clearance
Operating within SLA
Deploy MI solution
Operating within SLA
Today

## Slide 3: Supporting Information Mismatches
SLA
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age.
Target Date to operate within SLA
August 2019
Current SLA RAG Status (ASP only)
Green
RAG Justification
92 MPRNs out of the 180,536 LSPs that were billed incurred an ASP mismatch. The is an increase on last month’s post Nexus low of 65 MPRNs with a mismatch. 92.31% of ASP and 100% of AML mismatch correction files issued to customers within SLA of PDD -3 days. Some customers experienced quality issues with their Jul-19 AML correction file (instances of duplicate file headers).
100% AML offline correction files issued to customers ahead of payment due date
92% ASP offline correction files issued to customers ahead of payment due date
Mismatch instances are at the lowest since Nexus go-live, however failure to issue all correction files to all customers ahead of Payment Due Date minus 3 business days is causing SLA failure.
Provision of a single ASP file, followed by a single AML file remains a delivery target for January 2020.

## Slide 4: Exceptions
SLA
Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Red
RAG Justification
Exception backlog clearance continues to trend downwards. Despite reductions in backlog exceptions, the number of LSP and SSP reconciliations held off the AMS as a result of an exception remains high. Provision of the exception/exclusion MI from 27th Sep’19 will highlight all such exceptions. RAG status to remain at Red until the provision of all exception and exclusion MI to enable tracking of exclusion resolutions in-line with target SLA
What is an exception?
Business or Technical processing errors generated within our system, that cause reconciliations at individual sites, to be held back off the Amendment Invoice until resolved.
241,115 distinct MPRNs currently have unresolved exceptions within our systems (as of 6th September).
(269,920 in May-19, 166,903 in Jun-19)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) in development. Currently at risk of being available for next billing cycle.

## Slide 5: Exclusions
SLA
Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection.
Target Date to operate within SLA
July 2019
Current SLA RAG Status
Amber
RAG Justification
c.18,000 distinct sites released from bill blocks over the last three months. Cataloguing of the majority of exclusion scenarios complete and signed-off by Xoserve business teams. RAG status to remain at Amber until the provision of all exception and exclusion MI to enable tracking of exclusion resolutions in-line with target SLA.
What is an exclusion?
Until permanent system fixes are deployed to address charge calculation errors, monthly profiling of new reconciliations received that relate to the scenario of the open defect is performed, with “bill blocks” applied to that MPRN to safeguard the accuracy of the amendment charge calculations by exclusion from the AMS.
1,733 distinct MPRNs currently have bill blocks placed upon them
(20,466 in May-19, 5,043 in Jun-19)
Customer MI outlining all reconciliations and their status (invoiced, in exception, in exclusion) in development. Currently at risk of being available for next billing cycle.

## Slide 6: Defects
SLA
Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Green
RAG Justification
8 AML/ASP defects currently open of which 7 were raised in July and 1 in August. One defect did not meet the SLA – highly complex with multiple resolution options. May require a design change. For 3 defects now deployed, data fixes are outstanding for completion in mid September. All current known defects, identified pre and post revised commercial agreement, on track to be resolved in-line with SLA.
8 (down from 17)
Defects currently open and awaiting fix deployment

## Slide 7: MI / Reporting
SLA
All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA
August 2019
Current SLA RAG Status
Red
RAG Justification
Testing of exception and exclusion reports complete, awaiting transport of reports to production. All reports, including provision of customer monthly summaries, are being targeted to be available from 27th September.
External exception and exclusion reports will be issued 2 days after the Amendment invoice issue date. For the Aug-19 billing period this is 27th September.
Issues identified in UAT, reports have been updated and are in the process of being retested.

## Slide 8: Summary Resolution One Pager
Mismatches | Exceptions | Exclusions | Defects | MI / Reporting
Mismatches are corrected ‘in cycle’ and associated defects are cleared in time for the second following cycle from detection. Correction of mismatches should be invisible to shippers. During transition to this any correction files issued are delivered within 3 business days of payment due date issue and meet communicated quality and format requirements on first delivery. There should be no unresolved causes to mismatches of more than 2 invoice cycles in age. | Known exceptions are corrected ‘in cycle’; new exceptions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is any defect that caused the exception. Exception backlogs should be no more than 2 invoice cycles old. | Known exclusions are executed ‘in cycle’; new exclusions within the gift of Xoserve and its partners to correct are cleared in time for the second cycle from detection, as is the defect that caused the exclusion. Exclusion backlogs should be no more than 2 invoice cycles old. Correction of billed exclusions should be performed no later than 2 invoice cycles after detection. | Defects, including associated data fixes, within the gift of Xoserve and its partners to resolve should be cleared within 2 invoice cycles of being raised. | All MPRN recs received are accounted for and valued; allocation across invoices, exceptions, exclusions and mismatches is shared at shipper level with individual shippers at the end of each invoice cycle Exceptions, Exclusions and mismatches are communicated within 2 business days following invoice receipt.
Target Date to operate within SLA |  |  |  | 
September 2019 | August 2019 | July 2019 | August 2019 | August 2019
Current SLA RAG Status |  |  |  | 
Green | Red | Amber | Green | Red
RAG Justification |  |  |  | 
92% of ASP and 100% of AML correction file s issued 3 days prior to PDD. Development of merged ASP & AML files has commenced. UAT due to start mid October with merged files available for the Nov-19 billing period (issued 27th December). Merged file will be in line with ASP & AML file formats. High level plan to be shared and key milestones tracked. | Despite reductions in backlog exceptions, the number of LSP and SSP reconciliations held off the AMS as a result of an exception remains high. Provision of the exception/exclusion MI from 27th Sep’19 will highlight all such exceptions. RAG status to remain at Red until the provision of all exception and exclusion MI to enable tracking of exclusion resolutions in-line with target SLA. | c.18,000 distinct sites released from bill blocks over the last three months. Cataloguing of the majority of exclusion scenarios complete and signed-off by Xoserve business teams. RAG status to remain at Amber until the provision of all exception and exclusion MI to enable tracking of exclusion resolutions in-line with target SLA. | 8 AML/ASP defects currently open of which 7 were raised in July and 1 in August. One defect did not meet the SLA – highly complex with multiple resolution options. May require a design change. For 3 defects now deployed, data fixes are outstanding for completion in mid September. All current known defects, identified pre and post revised commercial agreement, on track to be resolved in-line with SLA. | Issues identified in UAT and report changes required. Reports have been updated and are in the process of being retested. All reports, including provision of customer monthly summaries, are being targeted to be available from 27th September. Red status because reports were due to be issued in August 2019 for July billing period.