## Bubbling Under Report
Regulatory Reference | Status | Governance | Proposer/ Sponsor | Name | Proposed Implementation Date | Change Type | Work Around Feasibility | System Impact(s) | Brief description of System Impact(s) | Earliest Need Date | Proposed Platform | Customer Change Lead | Comments
Mod 0662 | With Workgroup | UNC - Transmission | NTS | Revenue Recovery at Combined ASEPs | Oct-19 | Rule & System change | NA | UK Link and Gemini | Potential impacts to UK Link and Gemini. Please note - this is a single event change | NA | Transmission and Shared Services | Steve Pownall | The purpose of this modification is to allow entry capacity booked for the entry of gas into the NTS from storage sites within combined Aggregated System Entry Points (ASEPs), to be treated the same as a “Storage Site” as designated in National Grid’s Licence with respect to the application of any revenue recovery charge based on capacity bookings. The required changes will be captured as part of the EU GB Charging project. Xoserve systems have been impact assessed and the development of the modification solution is relatively simply. The modification is dependent on the 0678 decision.
Mod 0664 | With Workgroup | UNC - UIG | Adopted by SSE | Transfer of sites with low read submission performance from Class 2 and 3 into Class 4 | Oct-19 | Rule & System change | NA | UK Link | Impacts on UK Link to bulk transfer sites from Classes 2 and 3 to Class 4. Invoicing and charging arrangements to be put in place for the CDSP reclassifying sites. Reports required to compare Shipper performance. | NA | Retail & Network | David Addison | Modification looks to create an obligation for Shippers to move Supply Points with low Valid Daily Meter Reading submission performance from Classes 2 and 3 into Class 4 following a consecutive period of poor performance. The CDSP will automatically move any Supply Points note moved by the Shipper in such a scenario (after an allowed period of time). Impacts to UK Link expected. A ROM request is expecting, following finalisation of the business rules during the next WG.
Mod 0667 (Urgent) | Awaiting Ofgem decision Proposed removal from Bubbling Under | UNC - Transmission | South Hook Gas Company Ltd | Inclusion and Amendment of Entry Incremental Capacity Release NPV test in UNC | No implementation specified | Contractual change & potential Rule change | NA | Confirmed as no system impact. | As the modification remains as a contractual change only, there will be no system impacts. | NA | Transmission and Shared Services | Steve Pownall | Modification seeks to insert the Net Present Value test required for Non-IP Entry Incremental Capacity Release into UNC, and amend the mechanics of the test to ensure that it works effectively with the current GB system. Modification should have no impact on central systems as it is purely contractual, moving National Grid methodology into UNC. Transmission WG confirmed that there will be 'no impact' to central systems. Panel members voted to implement modification 0667 at the June Panel meeting. Modification is now with Ofgem for a decision. Proposed removal from Bubbling Under due to no central impacts expected.
Mod 0670R | With Workgroup | UNC - NTSCMF | NTS | Review of the charging methodology to avoid the inefficient bypass of the NTS | Any Modifications as a result of 0670R will be impact assessed and system implications considered. If modification is raised, it is likely to have cross-platform impacts (Gemini and SAP ISU). | [5 empty] | Transmission and Shared Services | Steve Pownall | Review Group requested to conduct an assessment of the charging methodology that is a feature of the overall Gas Transportation Charging framework to avoid the inefficient bypass of the NTS (currently the NTS Optional Commodity charge). The review assesses the objectives, identify requirements, analyse potential options and propose an enduring proportionate solution. Currently 3 ideas for a charging methodology to avoid the inefficient bypass of the NTS. If a modification is raised from the review group, it is likely to have central impacts as any new NTS short haul product will be based on NTS capacity rather than commodity. WG report expected by January 2020.
Mod 0672 | With Workgroup | UNC - UIG | Scottish Power | Target, Measure and Reporting Product Class 4 Read Performance | No implementation specified | Reporting | NA | UK Link | New reports required to measure performance | NA | TBC | David Addison | Modification has changed significantly and removed the incentive element. Focus is now on measuring performance. seeks to reduce Unidentified Gas (UIG) volume by providing a target for read submission performance for Product Class 4 sites against overall portfolio. This modification proposes to target and measure performance against an agreed percentage for Energy reconciled after a defined period and provide PAC with a report which will enable them to target shippers whose performance is below the target threshold. The central system impacts are now around creating new reports to measure performance. ROM request expected shortly once business rules are finalised.
Mod 0674 | With Workgroup | UNC - UIG | Scottish Power on behalf of PAC | Performance Assurance Techniques and Controls | No implementation specified | Reporting and Invoicing | NA | NA | New reports are required and the incentive regime will need to be developed with considerations around the invoicing element. | TBC | NA | Emma Smith | Modification seeks to provide an effective framework for the governance of industry performance that gives industry participants mutual assurance in the accuracy of settlement volume allocation. Developing through the WG. System impacts currently unknown. Reporting is definitely expected but the way sanctions and incentives are to be applied must be developed and system impacts assessed. ROM request expected shortly once business rules are finalised.
Mod 0676R | With Workgroup | UNC - WG | Gazprom Energy | Review of Gas Transporter Joint Office Arrangements | Any modifications as a result of 0676R will be impact assessed and any implications considered. | [5 empty] | NA | TBC | To request a review of the Uniform Network Code (UNC) General, Modification Rules and Joint Gas Transporter Governance arrangements for the Joint Office of Gas Transporters. Output for the Review Group is to assess whether the current arrangements are fit for purpose and recommend modifications where appropriate. WG extension requested and approved by Panel to February 2020.
Mod 0677R | With Workgroup | UNC - WG | First Utility | Shipper and Supplier Theft of Gas Reporting Arrangements | Any Modifications as a result of 0677R will be impact assessed and any implications considered. Potential system impacts are within CMS. | [5 empty] | NA | Ellie Rogers | This request is to review and identify any discrepancies in Shippers and Suppliers theft of gas reporting arrangements. Any changes from the review group will be assessed for central impacts. Central system impacts are likely with the options being recommended. Impacts to CMS are most likely as a recommended solution is the TRAS sending the confirmed thefts directly to the CDSP to be uploaded within CMS. Review Group has been extended for one month to align with the SPAA WG report being completed. Modifications and changes are expected to come out of the Review Group. Modification 0704 has already been raised.
Mod 0678 (A-J) Urgent | Awaiting Ofgem Decision | UNC - WG | Various proposers | Amendments to Gas Transmission Charging Regime | Oct-19 | Rule and System Change | No | UK Link and Gemini | Impact picked up through the Gemini project team | Oct-19 | Transmission and Shared Services | Steve Pownall | Modification proposal is to amend the Gas Transmission Charging regime in order to better meet the relevant charging objectives and customer/stakeholder provided objectives for Gas Transmission Transportation charges and to deliver compliance with relevant EU codes (notably the EU Tariff Code). There are currently 11 alternates. Modifications look to address the issues highlighted in the Ofgem rejection letter for 0621 and the alternatives. Impacts to be picked up as part of the project team. Panel did not recommend that 0678 or any of the alternates should be implemented. Panel also indicated no clear majority view on the preference around which modification better facilitates the Relevant Objectives. Modification and alternates are with Ofgem for a decision. Once decision is confirmed, the central changes will be picked up through the Gemini project team.
Mod 0683 | With Workgroup Proposed removal from Bubbling Under | UNC - Transmission | Cadent | Updating the Offtake Arrangements Document (OAD) with recommendations resulting from UNC Request Workgroup 0646R – Review of the Offtake Arrangements Document – Phase 1 | NA | Documentation Change | NA | No system impacts | No central system impacts. Document change only | NA | NA | NA | This modification seeks to update the OAD in order to bring it in line with industry changes made since 2005. The Request 0646R Review of the Offtake Arrangements Document, Workgroup has since identified a number of areas in OAD that can be updated now (Phase 1), with this being the first in a number of modifications. No central system impacts expected. Proposed removal from Bubbling Under.
Mod 0686 (Urgent) | Awaiting Ofgem decision | UNC - Transmission | Vermilion Energy Ireland Limited | Removal of the NTS Optional Commodity Rate with adequate notice | Oct-19 | Rule and System Change | No | UK Link and Gemini | Impact assessment required | TBC | Transmission and Shared Services | Steve Pownall | Removal of the NTS Optional Commodity Rate1 with adequate notice. “Adequate notice” here means a notice period that is consistent with both the TAR NC and the UNC requirements. As long a notice period as possible is desirable for Users who may be subject to contractual constraints. It is not considered as an alternative to 0678 because the proposer has stated that it will be possible to implement this proposal for effect on the OCR tariff from October 2019 and any one of the 0678 (or alternatives for effect on other tariffs at the same time or any subsequent date. Panel did not recommend the implementation of modification 0686. Currently with Ofgem for a decision. Modification must still be assessed to consider a phased implementation of the 0678.
Mod 0687 | Awaiting Ofgem decision | UNC - DWG | Total Gas & Power (on behalf of ICoSS) | Clarification of Supplier of Last Resort Cost Recovery Process | Nov-19 | System Change | No | UK Link | Changes to introduce a new charge type for domestic and non-domestic sites in a SoLR event | TBC | Retail & Network | Ellie Rogers | Modification seeks to provide clarity on how any costs incurred by the Gas Distribution Networks (Transporters) as part of a Last Resort Supply Payment arising from a Supplier of Last Resort event are recovered from Shippers. It proposes the introduction of a new customer charge (the SoLR customer charge) into the Gas Transportation charging statements in order to provide detail on how these costs are allocated. System impacts expected to introduce a new charge types. High level solution options have been provided with the degree of central system impacts varying depending on the preferred solution option. System delivery is expected by April 2019 which will impact the possible solution. The DSC Change Proposal has been raised (XRN4992). Panel voted to implement the modification and it is currently with Ofgem for a decision.
Mod 0688 | Modification Withdrawn Proposed removal from Bubbling Under | UNC - Transmission | Contract Natural Gas (on behalf of ICoSS) | Recovery of Shipper Losses incurred in Supplier of Last Resort events | TBC | System Change | No | TBC | Impact assessment required as it is currently unknown what and if this has central impacts | TBC | TBC | Steve Pownall | A change is proposed to allow Shippers that have incurred unrecoverable costs from shipping for sites where the Supplier is subject to a Supplier of Last Resort event, to recover such costs via Balancing Neutrality Charges. With WG for development. The proposer withdrew modification 0688 in October. Proposed removal from Bubbling Under.
Mod 0690 | With Workgroup | UNC - WG | British Gas (on behalf of the UIG Taskforce) | Reduce qualifying period for Class 1 | TBC | Rule and Reporting Change | No | UK Link | ROM response indicated that the data items required for the PAC report are already available therefore it is just utilising these data items for new reports | TBC | Data | James Rigby | This modification proposes that the qualifying period for the requirement for a meter point to become Class 1 is reduced, to limit the time period when very large sites are subject to NDM Demand Estimation, as opposed to being Daily Metered. The modification also proposes a new Performance Assurance report of sites which have met the qualifying criteria for Class 1 but are either Class 3 or Class 4. ROM response indicated that the data items required for the PAC report are already available. A DSC CP XRN4867) has been raised to deliver the report.
Mod 0691 | With Workgroup | UNC - UIG | British Gas (on behalf of the UIG Taskforce) | CDSP to convert Class 3 or 4 meter points to Class 1 when G1.6.15 criteria are met | TBC | Rule, System and Reporting Change | No | UK Link | Impact assessment required as system changes will be required to identify and move sites to Class 1 when they meet the qualifying criteria. New reports will be required to identify this. | TBC | Retail & Network, Data | James Rigby | This modification proposes that where the requirement for a Class 2, 3 or 4 meter point to become Class 1 (number of calculations and number of months) has been met, and the Shipper has not taken steps to convert the site to Class 1 within a 28 business day grace period, that the CDSP would take steps to convert the meter point to Class 1. The modification also proposes a new Performance Assurance report of sites where the CDSP has taken action, over the previous 12 months. ROM response has been provided which details two solution options (automated and manual). The automated solution would definitely require a Major Release. It is currently unknown as to whether the manual solution could be a candidate for a Minor Release. A DSC CP is required to deliver the system changes and is expected to be raised shortly.
Mod 0692 IGT131 | With Workgroup | UNC - DWG | Total Gas & Power (on behalf the UIG Taskforce) | Automatic updates to Meter Read Frequency | Jun-20 | Rule and System Change | No | UK Link | System changes required to update the MRF for sites with an AQ over 293,000kWh or with Smart or Advanced Metering equipment in operation | Jun-20 | Retail & Network | Ellie Rogers | To place an obligation on the CDSP to automatically update the Meter Read Frequency of a Class 3 or 4 Supply Meter Point to Monthly, if: a) The AQ increases to 293,000 kWh or above; or b) The Supply Point Register is updated to show that either Smart or Advanced metering equipment is in place. In addition to undertake a one-off exercise to update the Meter Read Frequency of all current registered Supply Meter Points to Monthly, where they meet at least one of the two criteria above. XRN4941 has been raised to deliver the system impacts of the modification and is in scope of June 2020 release pending the outcome of this modification. WG report has been finalised and is due to go to November Panel to be issued out for consultation. .
Mod 0693R | With Workgroup | UNC - UIG | Scottish Power (on behalf of the UIG Taskforce) | Treatment of kWh error arising from statutory volume-energy conversion | Any modifications as a result of 0693R will be impact assessed and system implications considered. | [5 empty] | TBC | James Rigby | The Request is to review the treatment of the error in kWh that arises from statutory volume to-energy conversion factors in order to mitigate the impact on gas settlement, reconciliation and Annual Quantities (AQs). WG are discussing the request. Any potential solutions from the review will need to be assessed for system impacts.
Mod 0694 | With Workgroup | UNC - DWG | WWU | CDSP provision of Class 1 Read service | Any modifications as a result of 0694R will be impact assessed and system implications considered. | [5 empty] | Retail & Network | Ellie Rogers | Modification 0647 proposed that Shippers should become responsible for the provision of Class 1 Reads. Work on that proposal has suggested that a better solution may be some form of central provision by the CDSP. 0694 is to enable exploration of this option and to develop a proposal that can be raised as a modification. Current proposal is to novate the current contract and service as is from the Transporters to the CDSP. System impacts expected to be minimal as it is contractual arrangements which need to be finalised. Modification expected to be raised for the November Panel meeting which will transfer the obligation from Transporters to the CDSP on behalf of Shippers for the provision of the Class 1 read service.
Mod 0695 IGT129 SCP476 | Approved and awaiting implementation Proposed removal from Bubbling Under | UNC - DWG | NGN | Obligations on Shippers to pass Transporter compensation payments on to consumers, via Suppliers | Oct-19 | System Change | NA | UK Link | Potential addition of a new charge type within an existing invoice | TBC | TBC | Ellie Rogers | Introduce new obligations onto Shipper Users to ensure that Transporter compensation aimed at consumers is passed to registered suppliers for onward transmission to consumers. Panel approved the modification and implementation is expected 08 November 2019. Additional charge types required as a result of implementation will be raised via a DSC CP. Proposed removal from Bubbling Under.
Mod 0696 | Awaiting Ofgem decision | UNC - DWG | Gazprom Energy | Addressing inequities between Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule Change | TBC | No system impacts | For the CDSP to correct any capacity charges identified by the Shipper, an offline process would be required. No system changes anticipated | TBC | Retail & Network | Ellie Rogers | To the extent to which a Consumer has entered into a bi-lateral Network Exit Agreement (NExA) with the relevant Transporter then any new or additional capacity charging should only apply from the relevant date set out in the NExA. Modification looks to propose that any new or additional capacity requested under the UNC should only be chargeable from the date set out in the NExA. WG report has been completed. System changes are not expected but a process to correct the capacity charges is necessary. Modification is with Ofgem for a decision. Expected to be considered at the same time as 0701. Depending on Ofgem decision, a DSC CP would be required to put in place the offline process.
Mod 0697 IGT equivalent to be raised | With Workgroup | UNC - DWG | Gazprom Energy | Alignment of the UNC TPD Section V5 and the Data Permissions Matrix | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document and process change only | TBC | N/A | Dave Addison /Ellie Rogers | This modification seeks to rationalise UNC TPD Section V5 and remove inconsistency with the Data Permissions Matrix. No system impacts resulting from this change, just documentational only. WG discussions are continuing.
Mod 0699 | With Workgroup | UNC - DWG | Scottish Power | Incentivise Key Areas of Performance using additional UIG Charges | TBC | Reporting and System Change | N/A | UK Link | New reports required to assess Shipper performance. Arrangements for incentivising performance and invoicing required | N/A | N/A | Dave Addison/ Ellie Rogers | To create a Shipper incentive mechanism, which encourages the achievement of key UNC targets and obligations. A proportion of Unidentified Gas (UIG) charges will be levied each month to Shippers, where performance has not met a set of pre-determined UNC targets. Modification still being developed in WG, concept and business rules would need to be agreed before full central system impacts assessed.
Mod 0701 | With Workgroup | UNC - DWG | NGN | Aligning Capacity booking under the UNC and arrangements set out in relevant NExAs | TBC | Rule and System Change | N/A | UK Link | Changes to UK Link to enhance what is held against NExA sites and add rules for certain data items | TBC | TBC | Ellie Rogers | To improve visibility where a consumer has entered into a bilateral Network Exit Agreement (NExA) with the relevant Transporter, and to link capacity increased with the NExA so that the allowed capacity does not exceed the capacity as agreed in the NExA. System impacts expected to enhance what is currently held in UK Link against NExAs. New rules and logic also to be applied for NExA sites. Discussions due to continue through WG.
Mod 0702 IGT equivalent to be raised | With Workgroup | UNC - DWG | Gazprom Energy | Introducing ‘Research Body’ as a new User type to the Data Permissions Matrix and UNC TPD Section V5 | TBC | Permissions Change | N/A | No system impacts | No central system impacts. Document change only to update the DPM | TBC | N/A | Ellie Rogers | This modification seeks to further realise the benefit of the Data Permissions Matrix reflecting the direction to greater data openness by adding ‘Research Body’ as a new user type to UNC TPD Section V5 and the Data Permissions Matrix. No system impacts expected, only documentational. Modification developing in WG.
Mod 0703 | Approved and awaiting implementation Proposed removal from Bubbling Under | UNC - Transmission | National Grid | Correction to Modification 0698S ‘Improvements to Margins Notice Arrangements’ | TBC | Document Change | N/A | No system impacts | No system impacts. Correction modification to update the wording in UNC | TBC | N/A | N/A | To correct an error in the LNG methodology calculation that was introduced by Modification 0698, ‘Improvements to Margins Notice Arrangements’. Modification issued straight to reduced consultation with 2 responses, both in support. Panel approved implementation of the modification at the Extraordinary meeting on 01 November. Proposed removal from Bubbling Under.
Mod 0704 | With Workgroup | UNC - DWG | SGN | Review of Transporter Theft Reporting | TBC | Reporting Change | N/A | No system impacts | No system impacts expected. Just a change to the theft reports produced by the CDSP | TBC | N/A | Ellie Rogers | This modification amends the existing Transporter theft of gas reporting requirements following discussions at the 0677R Shipper and Supplier Theft of Gas reporting arrangements review group. No system impacts expected. The current theft reports are expected to be updated to align with the final Transporter reporting obligations agreed within this modification. IGT equivalent has been raised (IGT133).
Mod 0705R | Assigned a Review group | UNC - WG | National Grid | NTS Capacity Access Review | Any modifications as a result of 0705R will be impact assessed and system implications considered. | [5 empty] | TBC | Steve Pownall | To review the principles and establish long-term strategy for the NTS capacity access regime. Ensuring the regime is appropriate for commercial behaviours experienced today, simplified and adaptable whilst being consistent with relevant obligations. To make recommendations for change and addressing short-term problems in accordance with the long-term ambition. 12 month Review Group has been set up. Central impacts currently unknown and dependent on the Review Group development which will be monitored.
Mod 0706R | Awaiting Panel Assignment | UNC | Contract Natural Gas | Instances where Shippers can exit commercial agreements with an independent supplier | Any modifications as a result of 0706R will be impact assessed and system implications considered. | [5 empty] | TBC | TBC | A review of the processes and obligations within the UNC and Supply Licence conditions to identify and enable a clear route for the gas Shipper to exit a commercial relationship with a supplier. Review group raised and due to be discussed at the November Panel meeting.
Mod IGT120 | With IGT Panel Proposed removal from Bubbling Under | IGT - Workstream | BUUK | Aligning the IGT UNC with licence changes following the UK leaving the EU with a ‘No deal’ | Jun-20 | Rule Change | N/A | No system impacts | No system impacts. Changes to IGT UNC only | Jun-20 | N/A | Ellie Rogers | Following the triggering of Article 50 and with the potential that the Government is unable to secure a deal on the withdrawal of the UK from the European Union, this modification seeks to amend the IGT UNC to align with the proposed Gas Transporter licence changes proposed by Ofgem which would come effective after the date agreed by Parliament and the EU Commission. No central system impacts. Proposed removal from Bubbling Under.
Mod IGT130 | With Workgroup Proposed removal from Bubbling Under | IGT - Workstream | EON Energy | Applying password protection encryption to electronic communication containing MPRNs | Feb-20 | Document Change | N/A | No system impacts | No system impacts. Changes to a Shipper and IGT document only | Feb-20 | N/A | Ellie Rogers | The purpose of this modification is widening the scope of encryption requirements building on those approved via IGT118. The developments and discussions have been completed through RG007 which was set up to determine the need and scope for this modification. No central system impacts expected. Proposed removal from Bubbling Under.
Mod IGT132 (IPL042 & QPL042) | With IGT Panel Proposed removal from Bubbling Under | IGT - Workstream | BUUK | Introduction of IGT Code Credit Rules | No implementation specified | Rule Change | N/A | No system impacts | No system impacts. Changes to update the Credit Rules in IGT UNC | N/A | N/A | Ellie Rogers | To introduce Code Credit Rules into the IGT UNC, based on the Ofgem guidelines in 2005 which introduced such rules and processes into the DCUSA (Schedule 1) and the UNC (TPD Section V). No system impacts. Proposed removal from Bubbling Under.
Mod IGT133 | With Workgroup | IGT - Workstream | BUUK | Transition of IGT Theft Reporting into the IGT UNC | No implementation specified | Reporting Change | N/A | No system impacts | No system impacts. Changes to the IGT theft reporting | N/A | N/A | Ellie Rogers | Introduction of reporting obligations on Pipeline Operators regarding Theft activities which have previously been held under the SPAA (Supply Point Administration Agreement). No system impacts.
SCP 473 | Out for Impact Assessment | SPAA Change Board | SGN | Reconciliation of Shipperless and Unregistered data by the PPMIP | Nov-19 | Permissions Change | N/A | Potential system impacts | The SCP must be assessed to understand if there are any system impacts | Nov-19 | TBC | James Barlow | This SCP seeks to allow the PPMIP to compare Shipperless and Unregistered Sites data provided by the CDSP against the data that they hold in relation to prepayment Supply Points. Where the PPMIP is able to identify the Supplier for the site, this change will require they return certain data back to the CDSP (including the Supplier ID), to enable the CDSP to register the site within central systems. A DSC CP needs to be raised to assess the system impacts.
SCP 480 | Out for Impact Assessment Proposed removal from Bubbling Under | SPAA Change Board | SGN | Amendments to Schedule 33 Theft Reporting | TBC | Rule Change | N/A | No system impacts | No system impacts, change to remove an obligation from SPAA only | TBC | N/A | James Barlow | This SPAA Change Proposal (SCP) seeks to amend Schedule 33 to remove the annual theft reporting requirements on Suppliers and Transporters. This SCP has been produced following a recommendation from the joint SPAA and Uniform Network Code (UND) Joint Theft Reporting Review Group (JTRR). It seeks to remove the theft reporting obligation from SPAA as it is already in UNC. No system impacts. Proposed removal from Bubbling Under.
SCP 481 | Out for Impact Assessment | SPAA Change Board | British Gas | Amendments to the unallocated payments process | Dec-19 | Rule and Reporting Change | N/A | Potential system impacts | The SCP must be assessed to understand how it impacts current arrangements being provided to SPAA and a change must be raised | Dec-19 | TBC | James Barlow | This SPAA Change Proposal (SCP) seeks to make changes to the annual Unallocated Transaction release process contained within Schedule 43 (section 18 – Unallocated payments) relating to prepayment. There have been previous change proposals (CP17/379 and SCP 436) which were approved but only addressed the allocation of funds in the ‘Unallocatable Transaction Report’. This change seeks to extend the propose to incorporate all non-allocated transactions held by the PPMIP and to distribute across all Suppliers with a Prepayment portfolio based on Market share for the period of allocation. The impacts of this change would need to be assessed to understand how and if it changes the current arrangements.
SCP 482 | Out for Impact Assessment Proposed removal from Bubbling Under | SPAA Change Board | SSE | Defining “Default Interest Rate” within the SPAA. | TBC | Document Change | N/A | No system impacts | No system impacts. Updating a defined term only | TBC | N/A | James Barlow | SCP 482 seeks to include a definition for “Default Interest Rate” into the SPAA. The term already exists within the SPAA, however, the description has been erroneously omitted. Updating a defined term only. No system impacts. Proposed removal from Bubbling Under.
SCP 483 | Out for Impact Assessment Proposed removal from Bubbling Under | SPAA Change Board | Scottish Power | Amending RET, SAR, and NOSI Group Names within DFC Documentation | Implementation no specified | Document Change | N/A | No system impacts | No system impacts. Updating the DFC only | TBC | N/A | James Barlow | SCP 483 seeks to make amendments to the Supplier Data Flow Catalogue (DFC) documentation to correct an inconsistency regarding the Group Names for the Resolution of Erroneous Transfers (RET), Supplier Agreed Reads (SAR) and Notification of Old Supplier Information (NOSI) data flows. Updating the DFC only, no system impacts. Proposed removal from Bubbling Under.